## GPT Review
GPT Executive Workshop Output Pack
GPT-reviewed artefact ¦ 2026-06-03 ¦ Day 1 provisional ¦ Day 2 pending unless explicitly evidenced
Workbook basis | WorkshopPack\Web_Transformation_Workshop Working Doc - 2_export.xlsx
Governing instruction | Agent.md
Spreadsheet tooling note | @oai/artifact-tool was not exposed in the available Node REPL runtime; workbook generated using the existing reviewed .xlsx export as a template and openpyxl fallback.
Executive control points
Overall position | AMBER: scope, capacity, publishing, SEO, secure-web and regional servicing remain open.
Master decision | DEC-001: migration vs transformation vs bounded hybrid remains Proposed / Open.
Critical actions | ACT-001, ACT-003, ACT-004, ACT-017, ACT-028, ACT-012, ACT-013, ACT-015/016.
Top risks | RSK-001, RSK-002, RSK-009, RSK-014, RSK-015, RSK-017, RSK-019, RSK-021.
Day 2 status | No confirmed Day 2 evidence found; Day 2/final outputs remain scaffold or pending.
Source inventory
Agent.md | Governing capture, classification, output, quality, and traceability rules
Documents/Transcirpts/Day 1 Session 1.md | Direct Teams/Otter session export; reconciled against WorkshopPack IDs
Documents/Transcirpts/Day 1 Session 2.md | Direct Teams/Otter session export; S2 deltas and action-item detail
Documents/Transcirpts/Day 1 Session 3.md | Direct Teams/Otter session export; S3 closing, scope, roadmap-prep detail
Documents/_extracted/*.txt | Extracted source text from docx notes and workshop synthesis
Documents/Transcirpts/*.docx | Original Teams notes / summary documents
Documents/Transcirpts/Web Transformation - 2 Day Planning Workshop (Day 1 ).vtt | Raw VTT transcript; duplicate/noisy attribution source
WorkshopPack/ | Structured baseline pack, registers, analysis lenses and executive drafts
WorkshopPack/Web_Transformation_Workshop Working Doc - 2_export.xlsx | Reviewed workbook export with full ACT/RAID/DEP parity
Roadmap/portfolio-exec-2026-06-03.html | Canonical executive roadmap baseline
OUTPUTS/CURSOR/portfolio-exec-2026-06-03.html | Latest generated full-table HTML used as GPT HTML source where available
Roadmap/portfolio-exec-2026-05-25.html | Reference layout and prior executive view
Human validation required
- Faoli Bank spelling / legal brand name and bank-page ownership (QST-017, DEC-013).
- Onkoza / Fullertela / Omkom site-name spelling from session transcript exports.
- Megan, Marlana, Joanne, Orisha and Andre surnames and formal roles.
- Amy / Mary references in S3 transcript; likely transcription artefacts.
- Executive sponsor / Steering Committee names and formal approvers.
- Unconfirmed due dates across most actions and dependencies.
- Final scope choice: migration, transformation or bounded hybrid (DEC-001 / ACT-001 / QST-001 / QST-016).
- Formal RACI, especially design authority, publishing ownership, OMAR responsibilities and go-live approvals.

## Overview
GPT-reviewed artefact ¦ 2026-06-03 ¦ Day 1 provisional ¦ Day 2 pending unless explicitly evidenced | Business Area | Cluster |  |  |  |  | Total Effort
Personal / Bank | OM Bank | Bank / OMF |  |  | Faoli/OM Bank separate brand — own IA & governance (DEC-013); confirm page ownership (QST-017) | Faoli/OM Bank treated as separate brand - own IA & governance (DEC-013); confirm page ownership
Personal / Save | L&S | PF |  |  | TBC — lead input required
Personal / Invest | Wealth | Wealth | Wealth CI may need separate platform/experience (ISS-001) |  | Wealth CI may need separate platform/experience (ISS-001)
Personal / Funeral | L&S | MFC |  | EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9) | EasiPlus depends on Funeral product template + MFC sign-off (DEP-008)
Personal / Insure | OMInsure | OMInsure / iWYZE |  |  | TBC — lead input required
Personal / Rewards | Rewards | Rewards |  |  | TBC — lead input required
Business / Corporate | L&S | Corporate |  |  | Corporate cluster template stress-test (ACT-043)
Adviser / Find an Adviser | GTT | Digital Channels |  | Find an Adviser Beta-ready, subject to DS V2 to Beta (DEP-3); advisor flow into beta (DEP-14)
Tools / Calculators | GTT | Digital Channels |  | PI2 calcs near Beta; Income Tax/Retirement/2-pot ready; Debt/Personal Loans/Budget in progress; ownerless calcs TBC (ACT-052)
Total

## Basic View
Web Transformation Workshop
[6 empty] | 1 |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10
[6 empty] | Scope |  |  | Design Standards |  |  |  |  | Design Delivery |  |  |  |  | Content Readiness |  |  |  |  | Feature Delivery |  |  |  |  | Design Systems |  |  |  |  | Migration |  |  |  |  | Publishing / Release UAT |  |  |  |  | Go Live Readiness |  |  |  |  | OMAR Impacts/ SEO / Analytics
[6 empty] | Keshvi Singh |  |  | Justin Evans | [5 empty] | Sebabatso Mtimkulu / Kameshnee Chetty |  |  |  | Natalie Patel |  |  |  |  | Wayne Moodley / Tebogo Segoje |  |  |  |  | Brent von Zitters |  |  |  |  | Zethembiso /Nithin / Execution |  |  |  |  | Gareth Bew / Bernice / Execution |  |  |  |  | Luvuyo / Keshvi Singh |  |  |  |  | Luvuyo / Keshvi Singh
# | Channel | Domain | Area / Journey | Business Area | Cluster | Status | Inputs | Output | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
1 | Public Web | OMCOZA | Personal / Bank | OM Bank | Bank / OMF | TBC | ** Area for leads to input their specific requirements relating to this business area | Personal / Bank: confirm Faoli/OM Bank separate-brand treatment, IA & bank-section page ownership (DEC-013, QST-017)
2 | Public Web | OMCOZA | Personal / Save | L&S | PF | TBC | Personal / Save (L&S / PF): confirm in/out of scope journeys
3 | Public Web | OMCOZA | Personal / Invest | Wealth | Wealth | TBC | Personal / Invest (Wealth): Wealth CI may be separate experience (ISS-001)
4 | Public Web | OMCOZA | Personal / Funeral | L&S | MFC | TBC | Personal / Funeral (MFC): EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9)
5 | Public Web | OMCOZA | Personal / Insure | OMInsure | OMInsure / iWYZE | TBC | Personal / Insure (OMInsure/iWYZE): stress-test templates vs iWYZE
6 | Public Web | OMCOZA | Personal / Rewards | Rewards | Rewards | TBC | Personal / Rewards: component shared with L&S servicing needs update (Dep-10)
7 | Public Web | OMCOZA | Business / Corporate | L&S | Corporate | TBC | Business / Corporate (L&S): apply template structure to corporate cluster (ACT-043)
8 | Public Web | OMCOZA | Adviser / Find an Adviser | GTT | Digital Channels | TBC | Adviser / Find an Adviser (GTT): Beta-ready subject to DS V2 to Beta (DEP-3)
9 | Public Web | OMCOZA | Tools / Calculators | GTT | Digital Channels | TBC | Tools / Calculators (GTT): confirm V2 completeness, TFSA template & ownerless calcs (ACT-052/053)
[14 empty] | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems
[14 empty] | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller
[14 empty] | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
[14 empty] | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress

## Stream Inputs
Stream | Owner | Deliverable | Activity | Duration | Start Date | End Date | Dependency | Risk | Confidence
Publishing | Natalie Patel | Publishing tracker | Complete page inventory + capacity model |  |  |  | Design/dev/content/URLs | RSK-002 | Low
Publishing | Natalie Patel | URL audit | Map current URLs to new IA |  |  |  | IA approval | RSK-021 | Medium
Design Standards | Justin Evans | Discovery | Analytics, research, stakeholder engagement |  |  |  | SME availability | RSK-005 | Medium
Design Systems | Brent von Zitters | Component audit | Figma audit + Contentstack build |  |  |  | DS capacity | RSK-008 | Low
Execution | Nithin Ramsaroop | Environments | Beta/Staging/Prod strategy |  |  |  | Architecture decision | RSK-010 | Medium
Execution | Nithin Ramsaroop | Automation | Automated testing + DevOps gates |  |  |  | Daniel capacity | RSK-006 | Low
Cross Channels | Wayne Moodley | EasiPlus | Funeral template + MFC sign-off |  |  |  | DEP-008 | RSK-014 | Medium
Cross Channels | Wayne Moodley | Calculators | PI2 Beta; PI3 ownership TBC |  |  |  | Web Platform PI2 | RSK-017 | Medium
Go-Live | Keshvi / Luvuyo | Readiness | Checklist: security, ServiceNow, comms |  |  |  | Multiple | RSK-013 | Low
SEO | Bernice / Luvuyo | SEO plan | Detailed action plan + ≥2mo lead | 2026-06-08 | 2026-06-12 | CMO approval | SEO readiness | RSK-009 | Medium

## Roadmap
Workstream | Milestone | Owner | Start Date | End Date | Dependency | Status | Comments
SEO Engagement | Detailed SEO action plan for rest of year | Luvuyo / Nondalo | 2026-06-08 | 2026-06-12 | CMO officer approval | In Progress | Kick off 27 May
Go Live Readiness | Security Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | CISO Office | In Progress | Pen-test options requested
OMAR Engagement | Re-alignment with OMAR teams | Keshvi / Luvuyo | 2026-06-08 | 2026-06-12 | Irene availability | In Progress | -
Go Live Readiness | QAG Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | QAG Team | In Progress | Pen-test options requested
Scope Definition | Resolve migration vs transformation scope | Gareth Bew / Keshvi | Day 2 | Not confirmed | Sponsor / Steering | Open | RSK-019
Publishing | Confirm dedicated OMAR publishing + tracker | Bernice Bryce | Not confirmed | Not confirmed | Capacity decision | Not started | RSK-002
Design Systems | OMDS operating model + component audit + DS V2 Beta | Brent von Zitters | Not confirmed | Not confirmed | DS capacity | Not started | RSK-008
URL Audit | Map all URLs to new-world IA; redirects | Natalie Patel | Not confirmed | Not confirmed | IA sign-off | Not started | ACT-017
SEO Workshop | Confirm SEO/analytics ownership & standards | Bernice / Programme | Not confirmed | Not confirmed | SEO readiness | Not started | ACT-012
Go-Live | Formal readiness checklist + regional recovery | Keshvi / Programme | Not confirmed | Not confirmed | Multiple streams | Not started | ACT-013/015/016

## Dependencies
ID | Stream | Dependency | Owner | Required By | Impact if Late | Mitigation | Escalation Path | Status
DEP-001 | Publishing | Contentstack dev + content/assets/URLs signed off before publishing | Programme | Not confirmed | Publishing & testing slip | Enforce gates (DEC-007) | Programme / Steering | Open
DEP-002 | Publishing | Testing cannot begin until all pages built in Beta | Programme | Not confirmed | Go-live slip | Track in Basic View | Programme | Open
DEP-003 | Cross Channel | DS V2 deployed to Beta (Find an Advisor + templates) | Brent von Zitters | Not confirmed | Beta readiness blocked | Component roadmap | Programme | Open
DEP-004 | Design | Figma/DS component audit before template scaling | Execution/Design | Not confirmed | Build blocked / rework | ACT-008 | Programme | Open
DEP-005 | Publishing | URL audit before switch-off/redirect decisions | Natalie Patel | Not confirmed | Broken journeys, SEO loss | ACT-017 | Programme | Open
DEP-006 | Publishing | Content packs + cluster/SME content before sign-off | Natalie Patel | Not confirmed | Publishing blocked | ACT-019 | Programme | Open
DEP-007 | Cross Channel | Cross Channels depends on Web Platform for FE from PI2 | Wayne Moodley | End PI2 | FE velocity drops | ACT-021 | Programme | Open
DEP-008 | Cross Channel | EasiPlus depends on Funeral template + MFC sign-off | Wayne Moodley | Not confirmed | EasiPlus blocked | ACT-023 | Programme | Open
DEP-009 | SEO | SEO ≥2 months lead before QA | SEO | ≥2 months pre-QA | Go-live blocked by SEO | DEC-011 | Programme | Open
DEP-010 | Cross Channel | Tax-free & flexi-invest pages link to migrated V2 journeys | Cross Channels | Not confirmed | Journey continuity gaps | - | Programme | Open
DEP-011 | Secure Web | Service tree/dashboard solution for secure web | Service team | Not confirmed | Secure web blocked | ACT-015 | Programme | Open
DEP-012 | SEO | Paid Ads URL requirements from Group Marketing | Group Marketing | Not confirmed | URL/analytics rework | - | Programme | Open
DEP-013 | E-commerce | Notify Nthabi of URL changes for GA tracking | Wayne Moodley | Pre go-live | Broken exec reporting | ACT-046 | Programme | Open
DEP-014 | Cross Channel | Final advisor flow into beta (Luvuyo) | Wayne Moodley | Not confirmed | Find an Advisor slip | - | Programme | Open
DEP-015 | Go-Live | Security pen-test/crowdsource before go-live | Security team | Pre go-live | Go-live blocked | ACT-013 | Steering | Open
DEP-016 | Go-Live | ServiceNow API updates + approvals before prod | Programme | Pre go-live | Prod deployment blocked | ACT-013 | Steering | Open

## Critical Path
Sequence | Activity | Owner | Predecessor | Start Date | End Date | Critical (Y/N) | Notes
1 | Confirm scope (migration vs transformation / tactical option) | Gareth Bew / Keshvi | - | Day 2 | Not confirmed | Y | DEC-001
2 | Define 'as-is' + page-treatment rules | Design / Programme | 1 | Not confirmed | Not confirmed | Y | ACT-004
3 | Design foundations (IA, navigation, templates, standards) | Design / OMDS | 1 | Not confirmed | Not confirmed | Y | DEC-006
4 | DS component audit + build (Nav, Product pages, DS V2) | Brent / Execution | 3 | Not confirmed | Not confirmed | Y | RSK-008
5 | URL audit + structure sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | ACT-017
6 | Content readiness + packs + sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | DEP-006
7 | Complete development in Contentstack | Nithin / Execution | 4 | Not confirmed | Not confirmed | Y | DEP-001
8 | Publishing in Beta (all pages built) | Natalie / Publishing | 7 | Not confirmed | Not confirmed | Y | DEP-002
9 | SEO engagement ≥2 months before QA | Bernice / SEO | 3 | Not confirmed | Not confirmed | Y | DEP-009
10 | Testing → Go-live readiness (security, ServiceNow, decommission) | Programme / Luvuyo | 8 | Not confirmed | Not confirmed | Y | ACT-013

## RAID Log
Type | ID | Stream | Description | Owner | Impact | Probability | Mitigation | Due Date | Status
Risk | RSK-001 | Migration vs transformation scope ambiguity | Business | High | High | Programme (GB) | Formal scope decision (ACT-001) | Day 2 | Open
Risk | RSK-002 | Publishing capacity insufficient (~1,530 pages, 2 publishers) | Resource | High | High | Publishing/Programme | Dedicated OMAR capacity (ACT-003) | Not confirmed | Open
Risk | RSK-003 | 'As-is' definition unclear | Process | High | High | Programme/Design | Define as-is (ACT-004) | Not confirmed | Open
Risk | RSK-004 | URL audit/redirect handling incomplete | Technical | Medium | High | Execution | URL audit (ACT-017) | Not confirmed | Open
Risk | RSK-005 | Regional resources cut | Resource | High | High | Programme/Regional | Resource review (ACT-014) | Not confirmed | Open
Risk | RSK-006 | Daniel limited capacity for automation/testing | Resource | Medium | Medium | Execution | Automation plan (ACT-010) | Not confirmed | Open
Risk | RSK-007 | OMDS treated as UI library not governance | Governance | Medium | High | OMDS | Operating model (ACT-006) | Not confirmed | Open
Risk | RSK-008 | Most components don't exist in Contentstack | Technical | High | High | Execution/OMDS | Component audit (ACT-008) | Not confirmed | Open
Risk | RSK-009 | SEO & analytics ownership not finalised | Governance | High | High | SEO/Programme | SEO workshop (ACT-012) | Not confirmed | Open
Risk | RSK-010 | Environment sequencing not defined | Technical | Medium | High | Execution | Environment strategy (ACT-009) | Not confirmed | Open
Risk | RSK-011 | Observability/analytics tagging added too late | Technical | Medium | Medium | Execution | Embed in delivery (ACT-011) | Not confirmed | Open
Risk | RSK-012 | Component sprawl / design debt | Technical | Medium | Medium | OMDS | Lifecycle register (ACT-007) | Not confirmed | Open
Risk | RSK-013 | Go-live readiness activities open | Governance | High | High | Programme | Readiness checklist (ACT-013) | Not confirmed | Open
Risk | RSK-014 | Secure web migration at risk | Delivery | High | High | Programme/Regional | Mitigation plan (ACT-015) | Not confirmed | Open
Risk | RSK-015 | Servicing transactions at risk (BW 1/9) | Delivery | High | High | Regional | Botswana recovery (ACT-016) | Not confirmed | Open
Risk | RSK-016 | Unstandardised images/assets | Process | Medium | Medium | Content/OMDS | Asset standards (ACT-019) | Not confirmed | Open
Risk | RSK-017 | Front-end resource exit after PI2 | Resource | High | High | CC/Web Platform | Transition plan (ACT-021) | End PI2 | Open
Risk | RSK-018 | BA capacity constrained | Resource | High | Medium | Cross Channels | Interim BA (ACT-022) | Not confirmed | Open
Risk | RSK-019 | Full scope ~2027 vs end-Nov window | Timeline | High | High | Programme (GB) | Scope options (ACT-028) | Day 2 | Open
Risk | RSK-020 | No centralised knowledge system | People | High | Medium | Programme (GB) | Documentation system (ACT-054) | Not confirmed | Open
Risk | RSK-021 | ~95% URLs changing impacts e-commerce/GA | Business | High | High | Execution/E-commerce | URL audit + notify Nthabi (ACT-046) | Pre go-live | Open
Risk | RSK-022 | Security pen-test + ServiceNow not confirmed | Security | Medium | High | Programme/Security | Confirm testing (ACT-013) | Pre go-live | Open
Issue | ISS-001 | Full Brand/CI not approved (interim only) | Design, OMDS, Brand | — | Templates cannot scale confidently | Brand/Group Marketing | CI approval route | Not confirmed | Open
Issue | ISS-002 | No reliable total page count; manual sheet tracking | Publishing, Programme | — | Capacity modelling unreliable | Publishing | Inventory + tracker (ACT-005) | Not confirmed | Open
Issue | ISS-003 | Secure web incomplete; no service-tree solution | CC, Execution, Service | — | Secure journeys cannot fully go live | Programme | Mitigation (ACT-015) | Not confirmed | Open
Issue | ISS-004 | Botswana servicing: 1 of 9 complete | Regional (BW) | — | Regional go-live at risk | Regional | Recovery plan (ACT-016) | Not confirmed | Open
Issue | ISS-005 | Go-live readiness activities open | Programme, Ops | — | Cannot declare go-live readiness | Programme | Checklist (ACT-013) | Not confirmed | Open
Issue | ISS-006 | BA on medical leave; recruitment ongoing | Cross Channels | — | CC requirements slowed | Cross Channels | Interim BA (ACT-022) | Not confirmed | Open
Issue | ISS-007 | Single person covers all publishing | Publishing | — | Throughput bottleneck now | Publishing/Programme | Dedicated capacity (ACT-003) | Not confirmed | Open
Issue | ISS-008 | No centralised knowledge system today | All | — | Delays, repeated work | Programme (GB) | Knowledge system (ACT-054) | Not confirmed | Open

## Governance
Forum | Purpose | Chair | Participants | Cadence | Inputs | Outputs | Escalation Route
Steering Committee | Oversight; scope/budget/risk; shutdown & go-live approvals | Sponsor (TBC) | Exec sponsors, programme leads | TBC | Consolidated RAID, scope options | Decisions, approvals | Sponsor / Exec
Programme Delivery Sync | Track delivery, dependencies, blockers | Gareth Bew | Stream leads | Weekly (TBC) | Basic View, Action Log | Updated tracker | Steering
OMDS / Design Authority | Component governance, standards, exceptions | Brent von Zitters | DS, Design, Group Marketing | TBC | Component requests | Approved components | Head of Design → Programme
Design Handover / Exit-Gate | Definition of Done design→build→publish | Design & Content leads | Design, DS, Dev, Publishing | Per area | Designs, content packs | Handover sign-off | Programme
SEO & Analytics Forum | SEO/analytics ownership, tooling, tagging | Luvuyo / Bernice | SEO, Analytics, Execution | TBC | SEO action plan | Tagging standards | Programme / CMO
Go-Live Readiness Review | Go/no-go; security, ServiceNow, comms, decommission | Keshvi / Luvuyo | Execution, Security, Ops, Comms | Per release | Readiness checklist | Go/no-go | Steering

## Action Log
# | Area / Journey | Workstream | Priority | Issue / Decision / Action | Owner | Due Date | Status | Notes
1 | All | Programme | Critical | Resolve & document scope decision (migration vs transformation vs hybrid) | Gareth Bew / Keshvi | Day 2 | Open | DEC-001, RSK-001 ¦ D1¦S1¦SRC-001
2 | All | Programme | Critical | Define & communicate migration tasks per business area & country | Programme | Not confirmed | Open | DEC-004, QST-007 ¦ D1¦S1¦SRC-001
3 | OMAR / SA | Publishing | Critical | Confirm dedicated OMAR publishing resource; ring-fence BAU | Bernice Bryce / Programme | Not confirmed | Open | DEC-010, RSK-002 ¦ D1¦S1¦SRC-002
4 | All | Design / Programme | Critical | Define & approve 'as-is' migration definition | Programme / Design | Not confirmed | Open | QST-002, RSK-003 ¦ D1¦S1¦SRC-002
5 | OMAR | Publishing | High | Complete page inventory + publishing tracker (vs 1,530 baseline) | Natalie Patel | Not confirmed | In Progress | RSK-002 ¦ D1¦S1¦SRC-002
6 | Design Systems | OMDS | High | Formalise OMDS operating model, design authority, SLAs | Brent von Zitters | Not confirmed | Open | DEC-006, DEC-007 ¦ D1¦S1¦SRC-002
7 | Design Systems | OMDS | High | Define component lifecycle + impact register | Brent von Zitters | Not confirmed | Open | RSK-012 ¦ D1¦S1¦SRC-002
8 | All | Execution | High | Figma & DS component audit (existing / reusable / to-build) | Execution / Design | Not confirmed | Open | DEP-004, RSK-008 ¦ D1¦S1¦SRC-002
9 | All | Execution | High | Beta/Staging/Production environment strategy & ownership | Execution | Not confirmed | Open | QST-006, RSK-010 ¦ D1¦S1¦SRC-002
10 | All | Execution | Medium | Add automated testing + DevOps quality gates | Execution | Not confirmed | Open | DEC-009, RSK-006 ¦ D1¦S1¦SRC-002
11 | All | Execution | Medium | Define observability (Dynatrace, Grafana, analytics tagging) | Execution | Not confirmed | Open | RSK-011 ¦ D1¦S1¦SRC-002
12 | All | SEO | High | SEO & analytics workshop — ownership, tooling, tagging standards | Programme / SEO | Not confirmed | Open | DEC-011, RSK-009 ¦ D1¦S1¦SRC-002
13 | All | Programme | High | Go-live readiness checklist (PGW, QAG, ServiceNow, security, comms) | Programme | Not confirmed | Open | RSK-013 ¦ D1¦S1¦SRC-002
14 | Regional | Programme | High | Resource review; confirm regional delivery capacity | Programme | Not confirmed | Open | RSK-005 ¦ D1¦S1¦SRC-002
15 | Namibia | Regional | High | Mitigation plans secure web + servicing (Namibia) | Programme / Regional | Not confirmed | Open | RSK-014 ¦ D1¦S1¦SRC-002
16 | Botswana | Regional | High | Recovery plan for remaining 8 of 9 servicing transactions | Regional | Not confirmed | Open | RSK-015 ¦ D1¦S1¦SRC-002
17 | All | Execution | Critical | URL audit — map URLs to new IA; redirects & switch-off | Natalie Patel / Execution | Not confirmed | Open | DEP-005, RSK-021 ¦ D1¦S1¦SRC-002
18 | All | Product | Medium | Use success metrics to prioritise sections (essential vs as-is) | Programme / Product | Not confirmed | Suggested | DEC-002 ¦ D1¦S1¦SRC-001
19 | All | Content | High | Content readiness checklist + asset standards pack | Content / OMDS | Not confirmed | Open | DEP-006, RSK-016 ¦ D1¦S1¦SRC-002
20 | All | Design | High | Assign owners: landing, article, carousel, theming | Programme / Design | Not confirmed | Open | QST-010, QST-011 ¦ D1¦S1¦SRC-002
21 | Cross Channels | Programme | High | Front-end transition plan post-PI2; Web Platform capacity model | Programme / CC | Not confirmed | Open | RSK-017, DEP-007 ¦ D1¦S1¦SRC-002
22 | Cross Channels | Cross Channels | High | Secure interim BA capacity during recruitment | Cross Channels | Not confirmed | Open | RSK-018 ¦ D1¦S1¦SRC-002
23 | Funeral / EasiPlus | Cross Channels | High | Escalate MFC sign-off for EasiPlus (Funeral template) | Wayne Moodley | Not confirmed | Open | DEP-008 ¦ D1¦S1¦SRC-002
24 | Calculators | Cross Channels | Medium | Personal Loans Calculator scope; PI3 calculator ownership | Wayne Moodley | Not confirmed | Open | QST-012 ¦ D1¦S1¦SRC-002
25 | All | Programme | Low | Assign second scribe for documentation | Participants | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
26 | All | Programme | High | Translate whiteboard outputs into detailed Excel plan | Gareth Bew | Not confirmed | Open | DEC-005 ¦ D1¦S2-3¦SRC-005
27 | All | Programme | High | Break migration plan into tasks + parallel streams | Gareth, Luvuyo | Not confirmed | Open | ACT-002 ¦ D1¦S2-3¦SRC-005
28 | All | Programme | Critical | Gap analysis: committed scope vs 5-month deliverables | Gareth, Keshvi | Day 2 | Open | RSK-001, RSK-019 ¦ D1¦S2-3¦SRC-006
29 | Cross Channels | Cross Channels | Medium | Wayne & Tebogo prepare & present delivery-plan changes | Wayne, Tebogo | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
30 | All | Design | High | Sequence ideas; draft logical platform roadmap | Design team | Not confirmed | Open | DEC-005 ¦ D1¦S2-3¦SRC-005
31 | All | Programme | Medium | Define standard compliance requirements across BUs | Gareth Bew | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
32 | All | Programme | High | Senior team track features; help define migration scope | Senior team | Not confirmed | Open | RSK-001 ¦ D1¦S2-3¦SRC-005
33 | All | Design | High | Roll out new design templates across foundational pages | Gareth / Design | Not confirmed | Open | DEC-006 ¦ D1¦S2-3¦SRC-005
34 | All | OMDS | Medium | Define standard patterns for platform features | Gareth / OMDS | Not confirmed | Open | QST-014 ¦ D1¦S2-3¦SRC-005
35 | All | Design | High | Clarify governance for design handover (tenant implementations) | Design & Content | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
36 | All | Programme | High | Migration approach for teams not yet on new platform | Gareth, Brent | Not confirmed | Open | RSK-012 ¦ D1¦S2-3¦SRC-005
37 | All | Programme | Medium | Document decision to allow design-phase skip (criteria) | Gareth, Brent | Not confirmed | Open | DEC-014 ¦ D1¦S2-3¦SRC-005
38 | All | Design | High | Definition of Done for design artifacts (incl. SEO input) | Gareth, Brent | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
39 | All | Design | High | Outline approval process for design artifacts | Gareth, Brent | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
40 | All | Design / SEO | High | Clarify copy finalisation + SEO at design→dev handover | Gareth, SEO | Not confirmed | Open | DEP-009 ¦ D1¦S2-3¦SRC-005
41 | All | Design | High | Finalise template structure; hand to build for parallel dev | Gareth Bew | Not confirmed | Open | DEC-008 ¦ D1¦S2-3¦SRC-005
42 | All | Design | High | Non-negotiable rules for category landing-page templates | Gareth, team | Not confirmed | Open | DEC-006 ¦ D1¦S2-3¦SRC-005
43 | Corporate | Design | Medium | Apply template structure to corporate cluster; identify tweaks | Gareth, team | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
44 | All | Content | High | Content audit per section (migrate/consolidate/delete) | Gareth, Natalie | Not confirmed | Open | ACT-004 ¦ D1¦S2-3¦SRC-005
45 | About / Careers | Design | Medium | Review low-traffic pages for consolidation; define stakeholders | Gareth, participants | Not confirmed | Open | QST-003 ¦ D1¦S2-3¦SRC-005
46 | E-commerce | Cross Channels | High | Notify Nthabi of URL changes for GA tracking | Wayne Moodley | Not confirmed | Open | RSK-021, DEP-013 ¦ D1¦S2-3¦SRC-005
47 | All | Design / Execution | High | Tag Figma with DS components; map names to Contentstack | Gareth, team | Not confirmed | Open | ACT-008 ¦ D1¦S2-3¦SRC-005
48 | All | OMDS | Medium | Align definitions: compositions/components/patterns/templates | Gareth, team | Not confirmed | Open | QST-014 ¦ D1¦S2-3¦SRC-005
49 | OMAR | Programme | High | Re-engage OMAR team; confirm scope & partnership mgmt | Megan | Not confirmed | Open | QST-013 ¦ D1¦S2-3¦SRC-005
50 | All | Execution | High | Automated testing framework; enforce DS in DevOps pipelines | Gareth, Daniel | Not confirmed | Open | DEC-009 ¦ D1¦S2-3¦SRC-005
51 | All | Execution | Medium | Integrate analytics tracking fields in CMS; owner Nithin | Nithin | Not confirmed | Open | RSK-011 ¦ D1¦S2-3¦SRC-005
52 | Calculators | Cross Channels | Medium | Review calculator pages; V2 complete vs additional scope | Gareth, Wayne | Not confirmed | Open | QST-012 ¦ D1¦S2-3¦SRC-005
53 | TFSA | Cross Channels | Medium | Clarify TFSA product page: new template vs existing version | Gareth, Wayne | Not confirmed | Open | QST-018 ¦ D1¦S2-3¦SRC-005
54 | All | Programme | High | Centralised documentation / knowledge system | Gareth Bew | Not confirmed | Open | RSK-020, ISS-008 ¦ D1¦S2-3¦SRC-006

## Key Decisions
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
DEC-001 | Scope | Migration vs transformation | Define & bound programme scope: migration, transformation, or hybrid | Gareth Bew / Keshvi | Yes - Critical | Proposed / Open | Day 2 | D1¦S1¦SRC-001¦Master risk RSK-001
DEC-002 | Strategy | Success metrics | Platform + customer success metrics (analytics, DS, <3s, NPS, traffic, etc.) | Gareth Bew | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-003 | Scope | MVP | MVP = new navigation (4 audiences) + secure web IA | Gareth Bew / Keshvi | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦QST-004
DEC-004 | Delivery | Migration dependencies | Identify & communicate dependencies + tasks per business area | Programme | Confirmed (intent) | Confirmed (intent) | - | D1¦S1¦SRC-001¦ACT-002
DEC-005 | Delivery | Whiteboard -> plan | Per-workstream whiteboard → programme plan + RAID | Gareth Bew | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-006 | Design | Design foundations | IA, navigation, templates, content/SEO/brand standards | Design / OMDS | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-007 | Governance | Handover governance | Approval routing & entry/exit gates between teams | Design / Programme | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦ACT-006
DEC-008 | Design | Page treatment | Product pages → new templates; others as-is/restyled | Design / Execution | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦QST-002
DEC-009 | Technical | Automated testing | Automated testing + DevOps pipeline enforcement | Execution | Yes | Proposed | Not confirmed | D1¦S1¦SRC-002¦RSK-006
DEC-010 | Resourcing | Dedicated publisher | Ring-fence dedicated migration publisher from BAU | Publishing / Programme | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦ACT-003
DEC-011 | SEO | SEO lead time | SEO team ≥2 months before QA for tagging & validation | SEO / Programme | Confirmed (intent) | Confirmed (intent) | - | D1¦S1¦SRC-001¦DEP-009
DEC-012 | Migration | Phased decommissioning | Turn off legacy components progressively as migrated | Programme / Execution | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦ASM-011
DEC-013 | Brand | Faoli Bank separate brand | Bank as separate entity with own IA & governance | Programme | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦QST-017
DEC-014 | Governance | Design-phase skip | Allow some teams to skip design phase (dependency-based) | Gareth / Brent | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦RSK-012

## Trade off's
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
TO-1 | Scope | Tactical vs strategic | Navigation-only vs full transformation | Gareth Bew / Keshvi | Choose scope option | Open | Day 2 | QST-016, RSK-019
TO-2 | Delivery | Speed vs rework | Migrate quickly vs wait for foundations | Programme | Accept rework risk? | Open | Not confirmed | DEC-008
TO-3 | Governance | Skip design vs full governance | Direct implementation for some teams | Gareth / Brent | Permit skip + criteria? | Open | Not confirmed | DEC-014
TO-4 | Design | Standardisation vs flexibility | Red zones vs modular green zones / snowflakes | Brent / OMDS | Balance standard vs modular | Open | Not confirmed | QST-014
TO-5 | Quality | Quality vs capacity | Best-practice templates vs available resources | Programme | Hold quality despite capacity? | Open | Not confirmed | GB stated quality must not be cut
TO-6 | Scope | Full vs selective migration | Move all content vs retire low-value pages | Programme / Execution | Confirm migration breadth | Open | Not confirmed | ASM-002

## Lead Prep Artefacts
Preparation, Expected Outputs and Artefacts
Workstream | Lead / Facilitator | What each lead must bring | What the discussion must confirm | Artefact produced | Exit gate | Applies to | Status
Scope | Keshvi Singh | Confirm the business area in scope, journey or property name, current ownership, known in/out-of-scope items, assumptions, decision constraints, and BU approver where known. | Confirm the scope for each area or journey, including what is included, excluded, unresolved, or requiring escalation. | Scope Confirmation Line Item | Scope is confirmed, or marked TBC with a named owner and due date. | All OMCOZA area / journey rows | Partial — Day 1 blockers surfaced
Design Standards | Justin Evans | Bring the relevant design standards, OMDS component rules, existing component options, known component gaps, exceptions, and any standards or content rules that must be applied. | Confirm the standards position for the area or journey: existing component, new component required, exception needed, or no design-system impact. | Design Standards and Component Readiness Log | Component and standards status captured with owner and decision path. | All OMCOZA area / journey rows | TBC
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design work required, design owner, review route, target handover date, and any blockers. | Design Delivery Tracker | Design status and handover date captured, or blocker assigned. | All OMCOZA area / journey rows | TBC
Content Readiness | Natalie Patel | Bring the content inventory, current content quality view, content owner, required content action, approval route, and any compliance needs. | Confirm the content action, content owner, approver, due date, and readiness risk. | Content Readiness Register | Content action and approver captured for the area or journey. | All OMCOZA area / journey rows | All OMCOZA area / journey rows
Design System | Brent von Zitters | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design components ,pages required, review route, target handover date, and any blockers. | Updates to Design Systems | Design systerms updated handover date captured, or blocker assigned. | All OMCOZA area / journey rows
Feature Delivery | Wayne Moodley / Tebogo Segoje | Bring the feature scope, technical or feature needs, feature-team capacity, build dependencies, reusable component needs, delivery confidence, and date constraints. | Confirm whether feature-team involvement is required, the dependency, delivery commitment, and delivery risk. | Feature Delivery Dependency Log | Feature dependency and required date captured, or marked N/A. | All OMCOZA area / journey rows | TBC
Migration | Nithin Ramsaroop / Zethembiso Msomi / Luvuyo Mkumatela | Bring the proposed migration path, current platform position, technical onboarding status, environment dependencies, cross-team dependencies, and as-is versus restructure recommendation. | Confirm the migration pathway: restructure, migrate as-is, partial migration, full migration, no migration, retire, or decommission. | Migration Pathway Decision Sheet | Migration pathway captured with owner, prerequisite, and blocker. | All OMCOZA area / journey rows | TBC
Publishing / Release UAT | Bernice Bryce / BU SME / Execution | Bring the publishing route, CMS workflow, UAT owner, UAT scenarios, content approval status, release-window constraints, and publishing prerequisites. | Confirm the publishing and UAT path, required sign-offs, test ownership, and release hand-off. | Publishing and UAT Readiness Checklist | UAT owner, publishing route, and sign-off path captured. | All OMCOZA area / journey rows | TBC
Go-Live Readiness | Keshvi Singh / Execution | Bring go/no-go criteria, rollback needs, support and hypercare owner, BAU owner, monitoring or reporting owner, release communications, and escalation route. | Confirm release readiness and the operational handover position for the area or journey. | Go-Live and Operationalisation Checklist | Go-live prerequisites and BAU owner captured. | All OMCOZA area / journey rows | TBC