## Overview
Area / Journey | Business Area | Cluster | Design Standards | Design Delivery | Content Readiness | Feature Delivery | Design Systems | Migration | Publishing / Release UAT | Go Live Readiness | OMAR Impacts/ SEO / Analytics | Total Effort
Personal / Bank | OM Bank | Bank / OMF
Personal / Save | L&S | PF
Personal / Invest | Wealth | Wealth
Personal / Funeral | L&S | MFC
Personal / Insure | OMInsure | OMInsure / iWYZE
Personal / Rewards | Rewards | Rewards
Business / Corporate | L&S | Corporate
Adviser / Find an Adviser | GTT | Digital Channels
Tools / Calculators | GTT | Digital Channels
Total

## Basic View
Web Transformation Workshop
[6 empty] | 1 |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10
[6 empty] | Scope |  |  | Design Standards |  |  |  |  | Design Delivery |  |  |  |  | Content Readiness |  |  |  |  | Feature Delivery |  |  |  |  | Design Systems |  |  |  |  | Migration |  |  |  |  | Publishing / Release UAT |  |  |  |  | Go Live Readiness |  |  |  |  | OMAR Impacts/ SEO / Analytics
[6 empty] | Keshvi Singh |  |  | Justin Evans | [5 empty] | Sebabatso Mtimkulu / Kameshnee Chetty |  |  |  | Natalie Patel |  |  |  |  | Wayne Moodley / Tebogo Segoje |  |  |  |  | Brent von Zitters |  |  |  |  | Zethembiso /Nithin / Execution |  |  |  |  | Gareth Bew / Bernice / Execution |  |  |  |  | Luvuyo / Keshvi Singh |  |  |  |  | Luvuyo / Keshvi Singh
# | Channel | Domain | Area / Journey | Business Area | Cluster | Status | Inputs | Output | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
1 | Public Web | OMCOZA | Personal / Bank | OM Bank | Bank / OMF |  | ** Area for leads to input their specific requirements relating to this business area
2 | Public Web | OMCOZA | Personal / Save | L&S | PF
3 | Public Web | OMCOZA | Personal / Invest | Wealth | Wealth
4 | Public Web | OMCOZA | Personal / Funeral | L&S | MFC
5 | Public Web | OMCOZA | Personal / Insure | OMInsure | OMInsure / iWYZE
6 | Public Web | OMCOZA | Personal / Rewards | Rewards | Rewards
7 | Public Web | OMCOZA | Business / Corporate | L&S | Corporate
8 | Public Web | OMCOZA | Adviser / Find an Adviser | GTT | Digital Channels
9 | Public Web | OMCOZA | Tools / Calculators | GTT | Digital Channels
[14 empty] | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems
[14 empty] | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller
[14 empty] | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
[14 empty] | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress

## Stream Inputs
Stream | Owner | Deliverable | Activity | Duration | Start Date | End Date | Dependency | Risk | Confidence
Design Standards |  | Discovery | Analytics
Design Standards |  | Discovery | Research
Design Standards |  | Discovery | Stakeholder Engagement
Design Standards |  | Discovery | Consolidate
Design Standards |  | Discovery | Understand
Design Standards |  | Discovery | SEO
Design Standards |  | Discovery | Copy
Design Standards |  | Discovery | Ecosystem
Design Standards |  | Discovery | Product
Design Standards |  | Discovery | Compliance
Design Standards |  | Discovery | Brand
Design Standards |  | Discovery | OMDS
Design Standards |  | Design | Desktop
Design Standards |  | Design | Mobile
Design Standards |  | Design | Copy Ready
Design Standards |  | Design | SEO ready
Design Standards |  | Design | Stakeholder Review
Design Standards |  | Design | DS review
Design Standards |  | Design | Tech Review
Design Standards |  | Design | Testing
Design Standards |  | Approval | Group marketing
Design Standards |  | Approval | Internal
Design Standards |  | Approval | External
Design Standards |  | Approval | Clusters
Design Standards |  | Handover | Design Ready
Design Standards |  | Handover | DS review
Design Standards |  | Handover | Final copy
Design Standards |  | Handover | Sign-offs
Design Standards |  | Handover | Rules
Design Delivery |  | Foundations | IA + Navigation container
Design Delivery |  | Foundations | Journeys + Audience (generic)
Design Delivery |  | Foundations | Templates (structural)
Design Delivery |  | Foundations | - Fit IA gap
Design Delivery |  | Foundations | - Support findability
Design Delivery |  | Foundations | Landing page audience + sections
Design Delivery |  | Foundations | Category
Design Delivery |  | Foundations | Product
Design Delivery |  | Foundations | Utility - Contact
Design Delivery |  | Foundations | Utility - About
Design Delivery |  | Foundations | Utility - Calculators
Design Delivery |  | Foundations | Content standards
Design Delivery |  | Foundations | OMDS enhancements
Design Delivery |  | Foundations | OMDS new
Design Delivery |  | Foundations | OMDS UI + Brand
Design Delivery |  | Journeys | Findability
Design Delivery |  | Journeys | Intent
Design Delivery |  | Journeys | Access to product info
Design Delivery |  | Journeys | Flow + page principles
Migration | Zee Msomi | Tech Uplift | Automated testing framework
Migration | Zee Msomi | Tech Uplift | DevOps pipelines to enforce delivery quality
Migration | Zee Msomi | Tech Uplift | AI-assisted Development
Migration | Zee Msomi | Operability | Observability, migrating Dynatrace
Migration | Zee Msomi | Operability | Grafana dashboard (OMAR)
Migration | Zee Msomi | Operability | Analytics - co-locating analytics tagging with content
Migration | Zee Msomi | Migration | Ensure all content is moved
Migration | Zee Msomi | Migration | Decon 'old' platform
Migration | Zee Msomi | Migration | Consume Designs for Navigation and Pages
Migration | Zee Msomi | Migration | Audit whats available in Figma
Migration |  | Migration | Templates - similar pages reviewed between sites
Migration |  | Migration | Whats outstanding in OMDS?
Migration |  | Migration | Stkaeholder reviews
Migration |  | Migration | V2 'as-is' migration review
Migration |  | Migration | - OMAR sites
Migration |  | Migration | - L&S, UT, etc
Migration |  | Migration | Information architecture WT & V2 nav components
Migration |  | Environment | Setup environment + staging
Migration |  | Contentstack | Complete development in Contentstack
Migration |  | Beta | Staging in Beta
Migration |  | Move to Prod | Production / testing / tooling
Publishing | Bee Bryce | Update Contentstack | Complete Dev work in Contentstack
Publishing | Bee Bryce | URL structure | Complete URL structure & obtain sign-off
Publishing | Bee Bryce | New Templates | Create new templates in Beta | 2 hours per page
Publishing | Bee Bryce | Build As-Is pages | Rebuild As-Is pages in Beta | 30 min per page
Publishing | Bee Bryce | Navigation + Footer | Complete navigation & footer for As-Is pages
Publishing | Bee Bryce | Testing | Testing all pages in Beta
Feature Delivery | Wayne - Cross Channels | Find an Adviser | Build feature to include design system V2 & deploy to Beta
Feature Delivery | Wayne - Cross Channels | Calculators (in progress) | Complete build on Debt calculator, Personal Loans calculator, Budget calculator
Feature Delivery | Wayne - Cross Channels | Calculators (ready for Beta) | Testing Income Tax calculator, Retirement calculator, 2 pot savings calculator
Feature Delivery | Tebogo Segoje (L&S serv) | Public Web | Funeral & Death Claims
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Transaction tracking
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Lump sum injections
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Change personal details
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Manage contributions
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Switch Funds
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Withdrawals / Disinvestments
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Change premium allocation
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | 2-pot
Go-Live readiness | Luvuyo Mkumatela | Pen test | Pen testing (ZA + OMAR)
Go-Live readiness | Luvuyo Mkumatela | QA | QAG
Go-Live readiness | Luvuyo Mkumatela | ServiceNow updates | SNOW updates
Go-Live readiness | Luvuyo Mkumatela | Approvals | Security Approvals
Go-Live readiness | Luvuyo Mkumatela | Comms | Call Centre Comms
OMAR | Luvuyo Mkumatela / Keshvi | Navigation | Navigation
OMAR | Luvuyo Mkumatela / Keshvi | Page Builds | Page development
SEO |  | SEO (Pre-prod, QA & Beta) | Tools
SEO |  | SEO (Pre-prod, QA & Beta) | Site tagging (current)
SEO |  | Analytics | Google Analytics (new site tagging)
SEO |  | Analytics | Customer experience tool (glassbox)
SEO |  | Analytics | OMAR analytics (country requirements)
SEO |  | Analytics | Tableau integration

## Roadmap
Workstream | Milestone | Owner | Start Date | End Date | Dependency | Status | Comments
SEO Engagement | detailed SEO action plan of what we are working on for the rest of the year | Luvuyo/ Nondalo | 2026-06-08 | 2026-06-12 | CMO officer approval |  | Kick off held meeting held 27 May
Go Live Readiness | Security Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | Engagment wth CISO Office |  | Requested options for Penetratrion Testing
OMAR Engagement | Re ALlignment with OMAR Teams | Keshvi / Luvuyo | 2026-06-08 | 2026-06-12 | Irene Availability and in country teams
Go Live Readiness | QAG Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | QAG Team |  | Requested options for Penetratrion Testing

## Dependencies
ID | Stream | Dependency | Owner | Required By | Impact if Late | Mitigation | Escalation Path | Status
Dep-1 | Publishing | SA - only 2 resources split across BAU and Transformation work
Dep-2 | Publishing | OMAR - no publishers
Dep-3 | Publishing | Publishing can only start once all Dev work has been completed in Contentstack
Dep-4 | Publishing | All content & assets needs to be signed off
Dep-5 | Publishing | Approved URL structure to be provided
Dep-6 | Publishing | Completed Designs, Dev work & Content
Dep-7 | Cross Channel | From end of PI2, cross channel team is dependant on the Web platform team for FE work | Wayne Moodley
Dep-8 | Cross Channel | Easy plus sales journey - journey migration is depedant on the Funeral product page template and requires MFC sign-off | Wayne Moodley
Dep-9 | Cross Channel | Contact Us - analysis & design needs to be planned for | Wayne Moodley
Dep-10 | L&S Servicing | There is a dependency on a component of the journey built by the Rewards team that currently requires updates, as it is causing inconsistencies between the app and web experiences. Alignment is needed with the Rewards team to determine the appropriate approach before the migration can proceed. This dependency may im | Tebogo Segoje
Dep-11 | Web - Execution | Design system components ( Nav and Product Pages) | Zee/ Brent
Dep-12
Dep-13
Dep-14
Dep-15
Dep-16
Dep-17
Dep-18
Dep-19
Dep-20

## Critical Path
Sequence | Activity | Owner | Predecessor | Start Date | End Date | Critical (Y/N) | Notes

## RAID Log
Type | ID | Stream | Description | Owner | Impact | Probability | Mitigation | Due Date | Status
Risk | RSK-001 | Cross Channel | FE resources - dev resources will move out of Cross Channel team
Risk | RSK-002 | Cross Channel | BA capacity (extended medical leave + new recruit)
Risk | RSK-003 | OMAR | Resources that cuts across regions have left t thoe organisation (RTE)
Risk | RSK-004 | OMAR - Nam | Secure Web - Migration at risk due to the fact that 2 resources split across deliveries
Risk | RSK-005 | OMAR - Nam | Team has recently taken over migrating the of servicing transactions. with 2 resources having to manage the Secure Web , and Public Web Migration it is a big RIsk
Risk | RSK-006 | OMAR Botswana | 1 out of 9 Sales journey completed thus far
Risk | RSK-007 | OMAR Overall | Reduced development delivery across the OMAR Region
| RSK-008 | OMAR Publishing of Sites | Publishing SA and OMAR = Bernice

## Governance
Forum | Purpose | Chair | Participants | Cadence | Inputs | Outputs | Escalation Route

## Action Log
# | Area / Journey | Workstream | Priority | Issue / Decision / Action | Owner | Due Date | Status | Notes
1 |  |  |  | URL Audit |  |  | Open
2 | [6 empty] | Open
3 | [6 empty] | Open
4 | [6 empty] | Open
5 | [6 empty] | Open
6 | [6 empty] | Open
7 | [6 empty] | Open
8 | [6 empty] | Open
9 | [6 empty] | Open
10 | [6 empty] | Open
11 | [6 empty] | Open
12 | [6 empty] | Open
13 | [6 empty] | Open
14 | [6 empty] | Open
15 | [6 empty] | Open
16 | [6 empty] | Open
17 | [6 empty] | Open
18 | [6 empty] | Open
19 | [6 empty] | Open
20 | [6 empty] | Open
21 | [6 empty] | Open
22 | [6 empty] | Open
23 | [6 empty] | Open
24 | [6 empty] | Open

## Key Decisions
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes

## Trade off's
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes

## Lead Prep Artefacts
Preparation, Expected Outputs and Artefacts
Workstream | Lead / Facilitator | What each lead must bring | What the discussion must confirm | Artefact produced | Exit gate | Applies to | Status
Scope | Keshvi Singh | Confirm the business area in scope, journey or property name, current ownership, known in/out-of-scope items, assumptions, decision constraints, and BU approver where known. | Confirm the scope for each area or journey, including what is included, excluded, unresolved, or requiring escalation. | Scope Confirmation Line Item | Scope is confirmed, or marked TBC with a named owner and due date. | All OMCOZA area / journey rows | TBC
Design Standards | Justin Evans | Bring the relevant design standards, OMDS component rules, existing component options, known component gaps, exceptions, and any standards or content rules that must be applied. | Confirm the standards position for the area or journey: existing component, new component required, exception needed, or no design-system impact. | Design Standards and Component Readiness Log | Component and standards status captured with owner and decision path. | All OMCOZA area / journey rows | TBC
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design work required, design owner, review route, target handover date, and any blockers. | Design Delivery Tracker | Design status and handover date captured, or blocker assigned. | All OMCOZA area / journey rows | TBC
Content Readiness | Natalie Patel | Bring the content inventory, current content quality view, content owner, required content action, approval route, and any compliance needs. | Confirm the content action, content owner, approver, due date, and readiness risk. | Content Readiness Register | Content action and approver captured for the area or journey. | All OMCOZA area / journey rows | All OMCOZA area / journey rows
Design System | Brent von Zitters | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design components ,pages required, review route, target handover date, and any blockers. | Updates to Design Systems | Design systerms updated handover date captured, or blocker assigned. | All OMCOZA area / journey rows
Feature Delivery | Wayne Moodley / Tebogo Segoje | Bring the feature scope, technical or feature needs, feature-team capacity, build dependencies, reusable component needs, delivery confidence, and date constraints. | Confirm whether feature-team involvement is required, the dependency, delivery commitment, and delivery risk. | Feature Delivery Dependency Log | Feature dependency and required date captured, or marked N/A. | All OMCOZA area / journey rows | TBC
Migration | Nithin Ramsaroop / Zethembiso Msomi / Luvuyo Mkumatela | Bring the proposed migration path, current platform position, technical onboarding status, environment dependencies, cross-team dependencies, and as-is versus restructure recommendation. | Confirm the migration pathway: restructure, migrate as-is, partial migration, full migration, no migration, retire, or decommission. | Migration Pathway Decision Sheet | Migration pathway captured with owner, prerequisite, and blocker. | All OMCOZA area / journey rows | TBC
Publishing / Release UAT | Bernice Bryce / BU SME / Execution | Bring the publishing route, CMS workflow, UAT owner, UAT scenarios, content approval status, release-window constraints, and publishing prerequisites. | Confirm the publishing and UAT path, required sign-offs, test ownership, and release hand-off. | Publishing and UAT Readiness Checklist | UAT owner, publishing route, and sign-off path captured. | All OMCOZA area / journey rows | TBC
Go-Live Readiness | Keshvi Singh / Execution | Bring go/no-go criteria, rollback needs, support and hypercare owner, BAU owner, monitoring or reporting owner, release communications, and escalation route. | Confirm release readiness and the operational handover position for the area or journey. | Go-Live and Operationalisation Checklist | Go-live prerequisites and BAU owner captured. | All OMCOZA area / journey rows | TBC