## Overview
2026-06-04 · Day 1 & Day 2 re-baselined · WorkshopPack SSOT · Phased audience-based delivery (Personal first; foundations end-June, Personal section ~end-July); four-squad resourcing decision | Business Area | Cluster |  |  |  |  | Total Effort
Personal / Bank | OM Bank | Bank / OMF |  |  | Faoli/OM Bank separate brand — own IA & governance (DEC-013); confirm page ownership (QST-017) | Faoli/OM Bank treated as separate brand - own IA & governance (DEC-013); confirm page ownership
Personal / Save | L&S | PF |  |  | TBC — lead input required
Personal / Invest | Wealth | Wealth | Wealth CI may need separate platform/experience (ISS-001) |  | Wealth CI may need separate platform/experience (ISS-001)
Personal / Funeral | L&S | MFC |  | EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9) | EasiPlus depends on Funeral product template + MFC sign-off (DEP-008)
Personal / Insure | OMInsure | OMInsure / iWYZE |  |  | TBC — lead input required
Personal / Rewards | Rewards | Rewards |  |  | TBC — lead input required
Business / Corporate | L&S | Corporate |  |  | Corporate cluster template stress-test (ACT-043)
Adviser / Find an Adviser | GTT | Digital Channels |  | Find an Adviser Beta-ready, subject to DS V2 to Beta (DEP-3); advisor flow into beta (DEP-14)
Tools / Calculators | GTT | Digital Channels |  | PI2 calcs near Beta; Income Tax/Retirement/2-pot ready; Debt/Personal Loans/Budget in progress; ownerless calcs TBC (ACT-052)
Total

## Basic View
Web Transformation Workshop
[6 empty] | 1 |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10
[6 empty] | Scope |  |  | Design Standards |  |  |  |  | Design Delivery |  |  |  |  | Content Readiness |  |  |  |  | Feature Delivery |  |  |  |  | Design Systems |  |  |  |  | Migration |  |  |  |  | Publishing / Release UAT |  |  |  |  | Go Live Readiness |  |  |  |  | OMAR Impacts/ SEO / Analytics
[6 empty] | Keshvi Singh |  |  | Justin Evans | [5 empty] | Sebabatso Mtimkulu / Kameshnee Chetty |  |  |  | Natalie Patel |  |  |  |  | Wayne Moodley / Tebogo Segoje |  |  |  |  | Brent von Zitters |  |  |  |  | Zethembiso /Nithin / Execution |  |  |  |  | Gareth Bew / Bernice / Execution |  |  |  |  | Luvuyo / Keshvi Singh |  |  |  |  | Luvuyo / Keshvi Singh
# | Channel | Domain | Area / Journey | Business Area | Cluster | Status | Inputs | Output | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
1 | Public Web | OMCOZA | Personal / Bank | OM Bank | Bank / OMF | TBC | ** Area for leads to input their specific requirements relating to this business area | Personal / Bank: confirm Faoli/OM Bank separate-brand treatment, IA & bank-section page ownership (DEC-013, QST-017)
2 | Public Web | OMCOZA | Personal / Save | L&S | PF | TBC | Personal / Save (L&S / PF): confirm in/out of scope journeys
3 | Public Web | OMCOZA | Personal / Invest | Wealth | Wealth | TBC | Personal / Invest (Wealth): Wealth CI may be separate experience (ISS-001)
4 | Public Web | OMCOZA | Personal / Funeral | L&S | MFC | TBC | Personal / Funeral (MFC): EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9)
5 | Public Web | OMCOZA | Personal / Insure | OMInsure | OMInsure / iWYZE | TBC | Personal / Insure (OMInsure/iWYZE): stress-test templates vs iWYZE
6 | Public Web | OMCOZA | Personal / Rewards | Rewards | Rewards | TBC | Personal / Rewards: component shared with L&S servicing needs update (Dep-10)
7 | Public Web | OMCOZA | Business / Corporate | L&S | Corporate | TBC | Business / Corporate (L&S): apply template structure to corporate cluster (ACT-043)
8 | Public Web | OMCOZA | Adviser / Find an Adviser | GTT | Digital Channels | TBC | Adviser / Find an Adviser (GTT): Beta-ready subject to DS V2 to Beta (DEP-3)
9 | Public Web | OMCOZA | Tools / Calculators | GTT | Digital Channels | TBC | Tools / Calculators (GTT): confirm V2 completeness, TFSA template & ownerless calcs (ACT-052/053)
[14 empty] | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems
[14 empty] | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller
[14 empty] | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
[14 empty] | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress

## Stream Inputs
Stream | Owner | Deliverable | Activity | Duration | Start Date | End Date | Dependency | Risk | Confidence
Publishing | Natalie Patel | Publishing tracker | Complete page inventory + capacity model |  |  |  | Design/dev/content/URLs | RSK-002 | Low
Publishing | Natalie Patel | URL audit | Map current URLs to new IA |  |  |  | IA approval | RSK-021 | Medium
Design Standards | Justin Evans | Discovery | Analytics, research, stakeholder engagement |  |  |  | SME availability | RSK-005 | Medium
Design Systems | Brent von Zitters | Component audit | Figma audit + Contentstack build |  |  |  | DS capacity | RSK-008 | Low
Execution | Nithin Ramsaroop | Environments | Beta/Staging/Prod strategy |  |  |  | Architecture decision | RSK-010 | Medium
Execution | Nithin Ramsaroop | Automation | Automated testing + DevOps gates |  |  |  | Daniel capacity | RSK-006 | Low
Cross Channels | Wayne Moodley | EasiPlus | Funeral template + MFC sign-off |  |  |  | DEP-008 | RSK-014 | Medium
Cross Channels | Wayne Moodley | Calculators | PI2 Beta; PI3 ownership TBC |  |  |  | Web Platform PI2 | RSK-017 | Medium
Go-Live | Keshvi / Luvuyo | Readiness | Checklist: security, ServiceNow, comms |  |  |  | Multiple | RSK-013 | Low
SEO | Bernice / Luvuyo | SEO plan | Detailed action plan + ≥2mo lead | 2026-06-08 | 2026-06-12 | CMO approval | SEO readiness | RSK-009 | Medium

## Roadmap
Workstream | Milestone | Owner | Start Date | End Date | Dependency | Status | Comments
SEO Engagement | Detailed SEO action plan for rest of year | Luvuyo / Nondalo | 2026-06-08 | 2026-06-12 | CMO officer approval | In Progress | Kick off 27 May
Go Live Readiness | Security Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | CISO Office | In Progress | Pen-test options requested
OMAR Engagement | Re-alignment with OMAR teams | Keshvi / Luvuyo | 2026-06-08 | 2026-06-12 | Irene availability | In Progress | -
Go Live Readiness | QAG Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | QAG Team | In Progress | Pen-test options requested
Scope Definition | Resolve migration vs transformation scope | Gareth Bew / Keshvi | Day 2 | Not confirmed | Sponsor / Steering | Open | RSK-019
Publishing | Confirm dedicated OMAR publishing + tracker | Bernice Bryce | Not confirmed | Not confirmed | Capacity decision | Not started | RSK-002
Design Systems | OMDS operating model + component audit + DS V2 Beta | Brent von Zitters | Not confirmed | Not confirmed | DS capacity | Not started | RSK-008
URL Audit | Map all URLs to new-world IA; redirects | Natalie Patel | Not confirmed | Not confirmed | IA sign-off | Not started | ACT-017
SEO Workshop | Confirm SEO/analytics ownership & standards | Bernice / Programme | Not confirmed | Not confirmed | SEO readiness | Not started | ACT-012
Go-Live | Formal readiness checklist + regional recovery | Keshvi / Programme | Not confirmed | Not confirmed | Multiple streams | Not started | ACT-013/015/016
Design Foundations | Personal IA + core templates + content guidelines sign-off | Design (Seba / Justin) | 2026-06-04 | 2026-06-30 | Stakeholder sign-off | In Progress | DEC-022, DEP-017
Personal Section | Personal section live (templates + content + publishing) | Bernice / Design | 2026-07-01 | 2026-07-31 | Foundations sign-off | Not started | DEC-015
Audience Rollout | Corporate → Business → Wealth (+ Secure) sequence | Programme | 2026-08-01 | Not confirmed | Personal complete | Not started | DEC-015
Resourcing | Four-squad resourcing decision + onboarding | Seba / Programme | 2026-06-08 | Not confirmed | Sponsor capacity approval | Open | DEC-016, ACT-064
Resource Roll-off | Migration/feature team roll-off ~Sept 10; QE roll-off August | Programme / CC (Tebogo) | 2026-08-01 | 2026-09-10 | Knowledge transfer + backfill | Risk | RSK-023
DevOps Quality Gates | Quality gates + Playwright + linting; initial rollout | Execution / Daniel | 2026-06-09 | 2026-06-30 | Daniel capacity | In Progress | DEC-021, RSK-006
Hong Kong | YouTube integration test (June) → go-live (July) | Gareth / OMI / Vallabh | 2026-06-01 | 2026-07-31 | OMI testing | Not started | PRK-012, ACT-079

## Dependencies
ID | Stream | Dependency | Owner | Required By | Impact if Late | Mitigation | Escalation Path | Status
DEP-001 | Publishing | Contentstack dev + content/assets/URLs signed off before publishing | Programme | Not confirmed | Publishing & testing slip | Enforce gates (DEC-007) | Programme / Steering | Open
DEP-002 | Publishing | Testing cannot begin until all pages built in Beta | Programme | Not confirmed | Go-live slip | Track in Basic View | Programme | Open
DEP-003 | Cross Channel | DS V2 deployed to Beta (Find an Advisor + templates) | Brent von Zitters | Not confirmed | Beta readiness blocked | Component roadmap | Programme | Open
DEP-004 | Design | Figma/DS component audit before template scaling | Execution/Design | Not confirmed | Build blocked / rework | ACT-008 | Programme | Open
DEP-005 | Publishing | URL audit before switch-off/redirect decisions | Natalie Patel | Not confirmed | Broken journeys, SEO loss | ACT-017 | Programme | Open
DEP-006 | Publishing | Content packs + cluster/SME content before sign-off | Natalie Patel | Not confirmed | Publishing blocked | ACT-019 | Programme | Open
DEP-007 | Cross Channel | Cross Channels depends on Web Platform for FE from PI2 | Wayne Moodley | End PI2 | FE velocity drops | ACT-021 | Programme | Open
DEP-008 | Cross Channel | EasiPlus depends on Funeral template + MFC sign-off | Wayne Moodley | Not confirmed | EasiPlus blocked | ACT-023 | Programme | Open
DEP-009 | SEO | SEO ≥2 months lead before QA | SEO | ≥2 months pre-QA | Go-live blocked by SEO | DEC-011 | Programme | Open
DEP-010 | Cross Channel | Tax-free & flexi-invest pages link to migrated V2 journeys | Cross Channels | Not confirmed | Journey continuity gaps | - | Programme | Open
DEP-011 | Secure Web | Service tree/dashboard solution for secure web | Service team | Not confirmed | Secure web blocked | ACT-015 | Programme | Open
DEP-012 | SEO | Paid Ads URL requirements from Group Marketing | Group Marketing | Not confirmed | URL/analytics rework | - | Programme | Open
DEP-013 | E-commerce | Notify Nthabi of URL changes for GA tracking | Wayne Moodley | Pre go-live | Broken exec reporting | ACT-046 | Programme | Open
DEP-014 | Cross Channel | Final advisor flow into beta (Luvuyo) | Wayne Moodley | Not confirmed | Find an Advisor slip | - | Programme | Open
DEP-015 | Go-Live | Security pen-test/crowdsource before go-live | Security team | Pre go-live | Go-live blocked | ACT-013 | Steering | Open
DEP-016 | Go-Live | ServiceNow API updates + approvals before prod | Programme | Pre go-live | Prod deployment blocked | ACT-013 | Steering | Open
DEP-017 | Design | Personal IA + core templates + content guidelines complete before dev/build | Design (Seba/Justin) | End June | Build cannot proceed | DEC-022, ACT-065 | Programme | Open
DEP-018 | Cross Channel | Product pages complete before EasiPlus & dependent sales journeys deploy | Web (Gareth) | Not confirmed | EasiPlus blocked (reaffirms DEP-008) | ACT-074 | Programme | Open
DEP-019 | Design | IA sign-off per audience before each downstream stream proceeds (sequential) | Design / Business | Sequential per audience | Downstream streams blocked | DEC-015 | Programme | Open
DEP-020 | Secure Web | Secure-web portfolio-view technical requirements before Sept roll-off | Secure Web | End Sept | Roll-off impact; planning blocked | QST-024, RSK-030 | Programme | Open
DEP-021 | Content | Template handover cadence (~every 2 weeks) feeds content creation & parallel builds | Design | Ongoing | Content creation blocked | ACT-056, DEC-017 | Programme | Open
DEP-022 | Execution | Desktop Figma output (source of truth) for automation & Contentstack mapping | Design | Not confirmed | Automation blocked | ACT-075 | Programme | Open

## Critical Path
Sequence | Activity | Owner | Predecessor | Start Date | End Date | Critical (Y/N) | Notes
1 | Confirm scope (migration vs transformation / tactical option) | Gareth Bew / Keshvi | - | Day 2 | Not confirmed | Y | DEC-001
2 | Define 'as-is' + page-treatment rules | Design / Programme | 1 | Not confirmed | Not confirmed | Y | ACT-004
3 | Design foundations (IA, navigation, templates, standards) | Design / OMDS | 1 | Not confirmed | Not confirmed | Y | DEC-006
4 | DS component audit + build (Nav, Product pages, DS V2) | Brent / Execution | 3 | Not confirmed | Not confirmed | Y | RSK-008
5 | URL audit + structure sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | ACT-017
6 | Content readiness + packs + sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | DEP-006
7 | Complete development in Contentstack | Nithin / Execution | 4 | Not confirmed | Not confirmed | Y | DEP-001
8 | Publishing in Beta (all pages built) | Natalie / Publishing | 7 | Not confirmed | Not confirmed | Y | DEP-002
9 | SEO engagement ≥2 months before QA | Bernice / SEO | 3 | Not confirmed | Not confirmed | Y | DEP-009
10 | Testing → Go-live readiness (security, ServiceNow, decommission) | Programme / Luvuyo | 8 | Not confirmed | Not confirmed | Y | ACT-013
11 | Design foundations sign-off (Personal IA + core templates) | Design (Seba / Justin) | 3 | Not confirmed | End June | Y | DEC-022, DEP-017
12 | Personal templates + content packages ready | Design / Bernice | 11 | Not confirmed | End July | Y | DEC-015, DEP-021
13 | Publishing gatekeeper sign-off (all pages) | Design / Publishing | 12 | Not confirmed | Not confirmed | Y | DEC-019
14 | DevOps quality gates (Playwright + linting) before prod | Execution | 13 | Not confirmed | End June | Y | DEC-021
15 | Personal go-live → Corporate → Business → Wealth (+Secure) | Programme | 14 | Not confirmed | End July+ | Y | DEC-015

## RAID Log
Type | ID | Stream | Description | Owner | Impact | Probability | Mitigation | Due Date | Status
Risk | RSK-001 | Migration vs transformation scope ambiguity | Business | High | High | Programme (GB) | Formal scope decision (ACT-001) | Day 2 | Open
Risk | RSK-002 | Publishing capacity insufficient (~1,530 pages, 2 publishers) | Resource | High | High | Publishing/Programme | Dedicated OMAR capacity (ACT-003) | Not confirmed | Open
Risk | RSK-003 | 'As-is' definition unclear | Process | High | High | Programme/Design | Define as-is (ACT-004) | Not confirmed | Open
Risk | RSK-004 | URL audit/redirect handling incomplete | Technical | Medium | High | Execution | URL audit (ACT-017) | Not confirmed | Open
Risk | RSK-005 | Regional resources cut | Resource | High | High | Programme/Regional | Resource review (ACT-014) | Not confirmed | Open
Risk | RSK-006 | Daniel limited capacity for automation/testing | Resource | Medium | Medium | Execution | Automation plan (ACT-010) | Not confirmed | Open
Risk | RSK-007 | OMDS treated as UI library not governance | Governance | Medium | High | OMDS | Operating model (ACT-006) | Not confirmed | Open
Risk | RSK-008 | Most components don't exist in Contentstack | Technical | High | High | Execution/OMDS | Component audit (ACT-008) | Not confirmed | Open
Risk | RSK-009 | SEO & analytics ownership not finalised | Governance | High | High | SEO/Programme | SEO workshop (ACT-012) | Not confirmed | Open
Risk | RSK-010 | Environment sequencing not defined | Technical | Medium | High | Execution | Environment strategy (ACT-009) | Not confirmed | Open
Risk | RSK-011 | Observability/analytics tagging added too late | Technical | Medium | Medium | Execution | Embed in delivery (ACT-011) | Not confirmed | Open
Risk | RSK-012 | Component sprawl / design debt | Technical | Medium | Medium | OMDS | Lifecycle register (ACT-007) | Not confirmed | Open
Risk | RSK-013 | Go-live readiness activities open | Governance | High | High | Programme | Readiness checklist (ACT-013) | Not confirmed | Open
Risk | RSK-014 | Secure web migration at risk | Delivery | High | High | Programme/Regional | Mitigation plan (ACT-015) | Not confirmed | Open
Risk | RSK-015 | Servicing transactions at risk (BW 1/9) | Delivery | High | High | Regional | Botswana recovery (ACT-016) | Not confirmed | Open
Risk | RSK-016 | Unstandardised images/assets | Process | Medium | Medium | Content/OMDS | Asset standards (ACT-019) | Not confirmed | Open
Risk | RSK-017 | Front-end resource exit after PI2 | Resource | High | High | CC/Web Platform | Transition plan (ACT-021) | End PI2 | Open
Risk | RSK-018 | BA capacity constrained | Resource | High | Medium | Cross Channels | Interim BA (ACT-022) | Not confirmed | Open
Risk | RSK-019 | Full scope ~2027 vs end-Nov window | Timeline | High | High | Programme (GB) | Scope options (ACT-028) | Day 2 | Open
Risk | RSK-020 | No centralised knowledge system | People | High | Medium | Programme (GB) | Documentation system (ACT-054) | Not confirmed | Open
Risk | RSK-021 | ~95% URLs changing impacts e-commerce/GA | Business | High | High | Execution/E-commerce | URL audit + notify Nthabi (ACT-046) | Pre go-live | Open
Risk | RSK-022 | Security pen-test + ServiceNow not confirmed | Security | Medium | High | Programme/Security | Confirm testing (ACT-013) | Pre go-live | Open
Risk | RSK-023 | Key-resource roll-offs — migration/feature team ~Sept 10; most knowledgeable QE August | Resource | High | High | Programme/CC (Tebogo) | Accelerate delivery; knowledge transfer; backfill (ACT-064) | Sept 10 / Aug | Open
Risk | RSK-024 | Linear (current-capacity) delivery will not meet year-end; full scope extends well beyond | Timeline | High | High | Programme (GB) | Four-squad parallel model + resource decision (DEC-016, ACT-064) | Year-end | Open
Risk | RSK-025 | Post-sign-off red-zone template changes cascade across content + code on all affected pages | Technical | Medium | High | Design/Execution | Red/green zones + change control (DEC-017/018) | Not confirmed | Open
Risk | RSK-026 | Single points of failure — only Gareth & Natalie build templates; Bernice overloaded | Resource | High | High | Programme/Publishing | Additional capacity + training + onboarding (ACT-064/067) | Not confirmed | Open
Risk | RSK-027 | Governance/template drift without controls (Contentstack ↔ Figma; new tenants) | Governance | Medium | Medium | Design/OMDS | Gatekeeper gate + Figma source-of-truth + onboarding (DEC-019, ACT-075) | Not confirmed | Open
Risk | RSK-028 | Stakeholder sign-off delays extend template sign-off (esp. sequential Personal outreach) | Business | Medium | High | Programme/Business | Structured engagement; group sign-off by page type (ACT-065, QST-025) | Not confirmed | Open
Risk | RSK-029 | EasiPlus & dependent journeys blocked until Funeral/product pages complete | Delivery | Medium | High | Cross Channels (Tebogo/Wayne) | Sequence product pages; escalate (DEP-018, ACT-074) | Not confirmed | Open
Risk | RSK-030 | Secure-web portfolio-view requirements unclear before Sept roll-off → planning blocked | Delivery | High | High | Secure Web/Migration (Tebogo) | Clarify portfolio-view scope (QST-024, DEP-020) | End Sept | Open
Risk | RSK-031 | Not all year-end goals will be delivered → sponsor expectation-management required | Programme | Medium | Medium | Programme (GB) | Evidence-based scope communication; phased value (DEC-015) | Year-end | Open
Risk | RSK-032 | Country teams without dedicated content/design resources (OMAR) cannot self-migrate | Resource | High | High | Programme/Regional | SA-first rollout + central support + squad extension (DEC-025) | Not confirmed | Open
Issue | ISS-001 | Full Brand/CI not approved (interim only) | Design, OMDS, Brand | — | Templates cannot scale confidently | Brand/Group Marketing | CI approval route | Not confirmed | Open
Issue | ISS-002 | No reliable total page count; manual sheet tracking | Publishing, Programme | — | Capacity modelling unreliable | Publishing | Inventory + tracker (ACT-005) | Not confirmed | Open
Issue | ISS-003 | Secure web incomplete; no service-tree solution | CC, Execution, Service | — | Secure journeys cannot fully go live | Programme | Mitigation (ACT-015) | Not confirmed | Open
Issue | ISS-004 | Botswana servicing: 1 of 9 complete | Regional (BW) | — | Regional go-live at risk | Regional | Recovery plan (ACT-016) | Not confirmed | Open
Issue | ISS-005 | Go-live readiness activities open | Programme, Ops | — | Cannot declare go-live readiness | Programme | Checklist (ACT-013) | Not confirmed | Open
Issue | ISS-006 | BA on medical leave; recruitment ongoing | Cross Channels | — | CC requirements slowed | Cross Channels | Interim BA (ACT-022) | Not confirmed | Open
Issue | ISS-007 | Single person covers all publishing | Publishing | — | Throughput bottleneck now | Publishing/Programme | Dedicated capacity (ACT-003) | Not confirmed | Open
Issue | ISS-008 | No centralised knowledge system today | All | — | Delays, repeated work | Programme (GB) | Knowledge system (ACT-054) | Not confirmed | Open
Issue | ISS-009 | Current under-resourcing across all workstreams; teams beyond capacity | All | — | Year-end delivery at risk; quality/morale pressure | Programme Leadership | Resource allocation decision (ACT-064) | Not confirmed | Open
Issue | ISS-010 | Unclear business ownership for several journeys (compliments, complaints, unclaimed benefits, IR, corporate unclaimed benefits) | Business teams | — | Migration planning blocked for those journeys | Programme (GB/Tebogo) | Identify owners + scope (ACT-073) | Not confirmed | Open
Issue | ISS-011 | Portfolio-view dependencies/requirements unclear for Secure Web; aggravated by Sept roll-off | Secure Web/Migration | — | Secure-web migration planning stalled | Technical teams (Tebogo) | Requirements clarification (QST-024, DEP-020) | Not confirmed | Open

## Governance
Forum | Purpose | Chair | Participants | Cadence | Inputs | Outputs | Escalation Route
Steering Committee | Oversight; scope/budget/risk; shutdown & go-live approvals | Sponsor (TBC) | Exec sponsors, programme leads | TBC | Consolidated RAID, scope options | Decisions, approvals | Sponsor / Exec
Programme Delivery Sync | Track delivery, dependencies, blockers | Gareth Bew | Stream leads | Weekly (TBC) | Basic View, Action Log | Updated tracker | Steering
OMDS / Design Authority | Component governance, standards, exceptions | Brent von Zitters | DS, Design, Group Marketing | TBC | Component requests | Approved components | Head of Design → Programme
Design Handover / Exit-Gate | Definition of Done design→build→publish | Design & Content leads | Design, DS, Dev, Publishing | Per area | Designs, content packs | Handover sign-off | Programme
SEO & Analytics Forum | SEO/analytics ownership, tooling, tagging | Luvuyo / Bernice | SEO, Analytics, Execution | TBC | SEO action plan | Tagging standards | Programme / CMO
Go-Live Readiness Review | Go/no-go; security, ServiceNow, comms, decommission | Keshvi / Luvuyo | Execution, Security, Ops, Comms | Per release | Readiness checklist | Go/no-go | Steering
Leadership Check-in & Playback | Twice-weekly 30-min check-ins + weekly playback via unified Jira construct (DEC-027) | Gareth Bew / Tsoaeli | Stream leads | Twice-weekly + weekly | Single Jira (milestones, deps, confidence) | Updated roadmap, blockers, decisions | Steering

## Action Log
# | Area / Journey | Workstream | Priority | Issue / Decision / Action | Owner | Due Date | Status | Notes
1 | All | Programme | Critical | Resolve & document scope decision (migration vs transformation vs hybrid) | Gareth Bew / Keshvi | Day 2 | Open | DEC-001, RSK-001 ¦ D1¦S1¦SRC-001
2 | All | Programme | Critical | Define & communicate migration tasks per business area & country | Programme | Not confirmed | Open | DEC-004, QST-007 ¦ D1¦S1¦SRC-001
3 | OMAR / SA | Publishing | Critical | Confirm dedicated OMAR publishing resource; ring-fence BAU | Bernice Bryce / Programme | Not confirmed | Open | DEC-010, RSK-002 ¦ D1¦S1¦SRC-002
4 | All | Design / Programme | Critical | Define & approve 'as-is' migration definition | Programme / Design | Not confirmed | Open | QST-002, RSK-003 ¦ D1¦S1¦SRC-002
5 | OMAR | Publishing | High | Complete page inventory + publishing tracker (vs 1,530 baseline) | Natalie Patel | Not confirmed | In Progress | RSK-002 ¦ D1¦S1¦SRC-002
6 | Design Systems | OMDS | High | Formalise OMDS operating model, design authority, SLAs | Brent von Zitters | Not confirmed | Open | DEC-006, DEC-007 ¦ D1¦S1¦SRC-002
7 | Design Systems | OMDS | High | Define component lifecycle + impact register | Brent von Zitters | Not confirmed | Open | RSK-012 ¦ D1¦S1¦SRC-002
8 | All | Execution | High | Figma & DS component audit (existing / reusable / to-build) | Execution / Design | Not confirmed | Open | DEP-004, RSK-008 ¦ D1¦S1¦SRC-002
9 | All | Execution | High | Beta/Staging/Production environment strategy & ownership | Execution | Not confirmed | Open | QST-006, RSK-010 ¦ D1¦S1¦SRC-002
10 | All | Execution | Medium | Add automated testing + DevOps quality gates | Execution | Not confirmed | Open | DEC-009, RSK-006 ¦ D1¦S1¦SRC-002
11 | All | Execution | Medium | Define observability (Dynatrace, Grafana, analytics tagging) | Execution | Not confirmed | Open | RSK-011 ¦ D1¦S1¦SRC-002
12 | All | SEO | High | SEO & analytics workshop — ownership, tooling, tagging standards | Programme / SEO | Not confirmed | Open | DEC-011, RSK-009 ¦ D1¦S1¦SRC-002
13 | All | Programme | High | Go-live readiness checklist (PGW, QAG, ServiceNow, security, comms) | Programme | Not confirmed | Open | RSK-013 ¦ D1¦S1¦SRC-002
14 | Regional | Programme | High | Resource review; confirm regional delivery capacity | Programme | Not confirmed | Open | RSK-005 ¦ D1¦S1¦SRC-002
15 | Namibia | Regional | High | Mitigation plans secure web + servicing (Namibia) | Programme / Regional | Not confirmed | Open | RSK-014 ¦ D1¦S1¦SRC-002
16 | Botswana | Regional | High | Recovery plan for remaining 8 of 9 servicing transactions | Regional | Not confirmed | Open | RSK-015 ¦ D1¦S1¦SRC-002
17 | All | Execution | Critical | URL audit — map URLs to new IA; redirects & switch-off | Natalie Patel / Execution | Not confirmed | Open | DEP-005, RSK-021 ¦ D1¦S1¦SRC-002
18 | All | Product | Medium | Use success metrics to prioritise sections (essential vs as-is) | Programme / Product | Not confirmed | Suggested | DEC-002 ¦ D1¦S1¦SRC-001
19 | All | Content | High | Content readiness checklist + asset standards pack | Content / OMDS | Not confirmed | Open | DEP-006, RSK-016 ¦ D1¦S1¦SRC-002
20 | All | Design | High | Assign owners: landing, article, carousel, theming | Programme / Design | Not confirmed | Open | QST-010, QST-011 ¦ D1¦S1¦SRC-002
21 | Cross Channels | Programme | High | Front-end transition plan post-PI2; Web Platform capacity model | Programme / CC | Not confirmed | Open | RSK-017, DEP-007 ¦ D1¦S1¦SRC-002
22 | Cross Channels | Cross Channels | High | Secure interim BA capacity during recruitment | Cross Channels | Not confirmed | Open | RSK-018 ¦ D1¦S1¦SRC-002
23 | Funeral / EasiPlus | Cross Channels | High | Escalate MFC sign-off for EasiPlus (Funeral template) | Wayne Moodley | Not confirmed | Open | DEP-008 ¦ D1¦S1¦SRC-002
24 | Calculators | Cross Channels | Medium | Personal Loans Calculator scope; PI3 calculator ownership | Wayne Moodley | Not confirmed | Open | QST-012 ¦ D1¦S1¦SRC-002
25 | All | Programme | Low | Assign second scribe for documentation | Participants | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
26 | All | Programme | High | Translate whiteboard outputs into detailed Excel plan | Gareth Bew | Not confirmed | Open | DEC-005 ¦ D1¦S2-3¦SRC-005
27 | All | Programme | High | Break migration plan into tasks + parallel streams | Gareth, Luvuyo | Not confirmed | Open | ACT-002 ¦ D1¦S2-3¦SRC-005
28 | All | Programme | Critical | Gap analysis: committed scope vs 5-month deliverables | Gareth, Keshvi | Day 2 | Open | RSK-001, RSK-019 ¦ D1¦S2-3¦SRC-006
29 | Cross Channels | Cross Channels | Medium | Wayne & Tebogo prepare & present delivery-plan changes | Wayne, Tebogo | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
30 | All | Design | High | Sequence ideas; draft logical platform roadmap | Design team | Not confirmed | Open | DEC-005 ¦ D1¦S2-3¦SRC-005
31 | All | Programme | Medium | Define standard compliance requirements across BUs | Gareth Bew | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
32 | All | Programme | High | Senior team track features; help define migration scope | Senior team | Not confirmed | Open | RSK-001 ¦ D1¦S2-3¦SRC-005
33 | All | Design | High | Roll out new design templates across foundational pages | Gareth / Design | Not confirmed | Open | DEC-006 ¦ D1¦S2-3¦SRC-005
34 | All | OMDS | Medium | Define standard patterns for platform features | Gareth / OMDS | Not confirmed | Open | QST-014 ¦ D1¦S2-3¦SRC-005
35 | All | Design | High | Clarify governance for design handover (tenant implementations) | Design & Content | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
36 | All | Programme | High | Migration approach for teams not yet on new platform | Gareth, Brent | Not confirmed | Open | RSK-012 ¦ D1¦S2-3¦SRC-005
37 | All | Programme | Medium | Document decision to allow design-phase skip (criteria) | Gareth, Brent | Not confirmed | Open | DEC-014 ¦ D1¦S2-3¦SRC-005
38 | All | Design | High | Definition of Done for design artifacts (incl. SEO input) | Gareth, Brent | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
39 | All | Design | High | Outline approval process for design artifacts | Gareth, Brent | Not confirmed | Open | DEC-007 ¦ D1¦S2-3¦SRC-005
40 | All | Design / SEO | High | Clarify copy finalisation + SEO at design→dev handover | Gareth, SEO | Not confirmed | Open | DEP-009 ¦ D1¦S2-3¦SRC-005
41 | All | Design | High | Finalise template structure; hand to build for parallel dev | Gareth Bew | Not confirmed | Open | DEC-008 ¦ D1¦S2-3¦SRC-005
42 | All | Design | High | Non-negotiable rules for category landing-page templates | Gareth, team | Not confirmed | Open | DEC-006 ¦ D1¦S2-3¦SRC-005
43 | Corporate | Design | Medium | Apply template structure to corporate cluster; identify tweaks | Gareth, team | Not confirmed | Open | - ¦ D1¦S2-3¦SRC-005
44 | All | Content | High | Content audit per section (migrate/consolidate/delete) | Gareth, Natalie | Not confirmed | Open | ACT-004 ¦ D1¦S2-3¦SRC-005
45 | About / Careers | Design | Medium | Review low-traffic pages for consolidation; define stakeholders | Gareth, participants | Not confirmed | Open | QST-003 ¦ D1¦S2-3¦SRC-005
46 | E-commerce | Cross Channels | High | Notify Nthabi of URL changes for GA tracking | Wayne Moodley | Not confirmed | Open | RSK-021, DEP-013 ¦ D1¦S2-3¦SRC-005
47 | All | Design / Execution | High | Tag Figma with DS components; map names to Contentstack | Gareth, team | Not confirmed | Open | ACT-008 ¦ D1¦S2-3¦SRC-005
48 | All | OMDS | Medium | Align definitions: compositions/components/patterns/templates | Gareth, team | Not confirmed | Open | QST-014 ¦ D1¦S2-3¦SRC-005
49 | OMAR | Programme | High | Re-engage OMAR team; confirm scope & partnership mgmt | Megan | Not confirmed | Open | QST-013 ¦ D1¦S2-3¦SRC-005
50 | All | Execution | High | Automated testing framework; enforce DS in DevOps pipelines | Gareth, Daniel | Not confirmed | Open | DEC-009 ¦ D1¦S2-3¦SRC-005
51 | All | Execution | Medium | Integrate analytics tracking fields in CMS; owner Nithin | Nithin | Not confirmed | Open | RSK-011 ¦ D1¦S2-3¦SRC-005
52 | Calculators | Cross Channels | Medium | Review calculator pages; V2 complete vs additional scope | Gareth, Wayne | Not confirmed | Open | QST-012 ¦ D1¦S2-3¦SRC-005
53 | TFSA | Cross Channels | Medium | Clarify TFSA product page: new template vs existing version | Gareth, Wayne | Not confirmed | Open | QST-018 ¦ D1¦S2-3¦SRC-005
54 | All | Programme | High | Centralised documentation / knowledge system | Gareth Bew | Not confirmed | Open | RSK-020, ISS-008 ¦ D1¦S2-3¦SRC-006
55 | All | Programme | High | Populate shared Roadmap with stream-level work items, owners, milestones, deps & confidence; consolidate & circulate (raw dataset Fri midday) | Gareth + stream leads | This week | Open | DEC-027, ACT-026 ¦ D2¦S1¦SRC-008
56 | Personal | Content | High | Deliver Personal content package (content + QA) so pages/templates are build-ready | Bernice / Content | End July | Open | DEC-015, DEP-021 ¦ D2¦S1¦SRC-008
57 | All | Content / IA | High | Map current article/site URL structure & propose consolidated structure (/articles; news-vs-articles rules) | Justin, Bernice | End June | Open | DEC-024, ACT-017 ¦ D2¦S1¦SRC-008
58 | Personal | Publishing | High | Migrate ~140-150 Personal article pages to new structure once URL structure & packages ready | Bernice | June | Open | DEC-023 ¦ D2¦S1¦SRC-008
59 | All | Content / Design | Medium | Retrofit 'news' onto the article template & migrate news content | Bernice / Design | June | Open | DEC-023 ¦ D2¦S1¦SRC-008
60 | All | Execution | High | Implement content + analytics co-location automation in Contentstack | Rey, Nithin | June | Open | DEC-020, RSK-011 ¦ D2¦S1¦SRC-008
61 | All | Execution | High | Implement DevOps quality gates + CI/CD checks (test/automation reports, linting); begin reporting | Gareth, Daniel | End June | Open | DEC-021, RSK-006 ¦ D2¦S1¦SRC-008
62 | All | Programme | Medium | Set up workstream-lead cadence (twice-weekly 30-min) + weekly playback; circulate invite | Gareth | This week | Open | DEC-027 ¦ D2¦S1¦SRC-008
63 | Regional | Programme / Regional | High | Prepare options & rollout approach for country/site migrations (like-for-like vs full template rework) with effort/cost | Gareth / Regional | Not confirmed | Open | DEC-025 ¦ D2¦S1¦SRC-008
64 | All | Programme | Critical | Produce resourced four-squad view (full-squad resourcing plan + immediate hires/onboarding) | Seba / Programme | Not confirmed | Open | DEC-016, RSK-024 ¦ D2¦S1-2¦SRC-008/009
65 | Personal | Design | Critical | Finalise Personal design foundations (IA, core templates, content guidelines, sign-off); prepare buildable templates | Gareth, Bertus, Design | End June | Open | DEC-022, DEP-017 ¦ D2¦S1¦SRC-008
66 | All | Content | High | Conduct comprehensive content audit + URL mapping per section (added/consolidated/rewritten/removed) | Gareth, Natalie | Not confirmed | Open | DEC-024, ACT-044 ¦ D2¦S1¦SRC-008
67 | All | Programme | High | Define onboarding process & deliverables for new team members/tenants joining in June | Gareth | June | Open | DEC-019, RSK-027 ¦ D2¦S1¦SRC-008
68 | All | Design | High | Finalise & hand over four production-ready template sections to dev within 1-2 sprints (incl. content setup) | Gareth / Design | ≤2 weeks | Open | DEC-017, DEP-017 ¦ D2¦S1¦SRC-008
69 | All | Programme | High | Integrate all team boards into a single Jira construct for unified tracking | Tsoaeli | Not confirmed | Open | DEC-027 ¦ D2¦S1¦SRC-008
70 | All | Programme | High | Each stream lead enters milestones, priorities, deadlines, confidence & owners into the spreadsheet | Brent, Zee, Justin (all leads) | By Fri | Open | DEC-027, ACT-055 ¦ D2¦S1¦SRC-008
71 | All | Execution | Medium | Include decommissioning tasks in the project plan; coordinate timing by deployment stage | Nithin | Not confirmed | Open | DEC-012 ¦ D2¦S1¦SRC-008
72 | All | Security | High | Clarify pen-test scope for public web (content + journeys) with Nzama | Gareth | Not confirmed | Open | RSK-022, DEP-019 ¦ D2¦S1¦SRC-008
73 | All | Business / Programme | High | Identify business owners for additional journeys (compliments, complaints, unclaimed benefits, IR, corporate unclaimed benefits); assess in/out of scope | Gareth, Tebogo | This week | Open | ISS-010, QST-022 ¦ D2¦S1-2¦SRC-008/009
74 | Regional | Programme / Regional | High | Assess feature/journey completion per country (Kenya confirm; Malawi/South Sudan tasks); sequence migration/publishing by readiness | Gareth | Not confirmed | Open | DEC-025, ACT-002 ¦ D2¦S1¦SRC-008
75 | All | Design | High | Provide desktop Figma output as source of truth for automation; tag Figma → Contentstack | Gareth / Design | Not confirmed | Open | ACT-047, DEP-022 ¦ D2¦S1¦SRC-008
76 | Bank | Programme | Medium | Clarify whether OM finance pages move to the bank; define next steps | Gareth | Not confirmed | Open | DEC-028, QST-021 ¦ D2¦S1¦SRC-008
77 | All | Design / Content | Low | Clarify naming/structure for financial toolkit & news sections (rename financial toolkit) | Gareth | Not confirmed | Open | QST-023 ¦ D2¦S1¦SRC-008
78 | All | Programme | High | Book consolidation time with Baptist (Jun 5) + Friday (Jun 7) leads review to hand over refined outputs | Gareth, Bertus, Baptist | Jun 5-7 | Open | DEC-027, ACT-055 ¦ D2¦S1¦SRC-008
79 | Hong Kong | Regional | Medium | Begin Hong Kong YouTube integration testing (June) → go-live (July); OMI testing June; Vallabh review July | Gareth / OMI / Vallabh | Jun-Jul | Open | PRK-012 ¦ D2¦S1¦SRC-008
80 | All | Programme | Medium | Clarify ownership models & formal agreements for migrated tenant sites (business owner + funding) | Gareth, Reza | Not confirmed | Open | DEC-026 ¦ D2¦S1¦SRC-008
81 | All | Programme | Medium | Identify & confirm owners for unclear assets (fund tables, Bulletin); define working model | Gareth, Reza | Not confirmed | Open | PRK-011 ¦ D2¦S1¦SRC-008
82 | All | Design | Medium | Schedule weekly template playback sessions for early technical-team visibility | Gareth | Weekly | Open | DEC-017 ¦ D2¦S1¦SRC-008
83 | Regional | Programme / Regional | Medium | Document the migration process & run a workshop with country teams to align requirements/next steps | Gareth | Not confirmed | Open | DEC-025 ¦ D2¦S1¦SRC-008
84 | All | Programme | Low | Collect written + virtual participant feedback on the two days; capture improvement suggestions | All participants | This week | Open | - ¦ D2¦S1¦SRC-008

## Key Decisions
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
DEC-001 | Scope | Migration vs transformation | Define & bound programme scope: migration, transformation, or hybrid | Gareth Bew / Keshvi | Yes - Critical | Proposed / Open | Day 2 | D1¦S1¦SRC-001¦Master risk RSK-001
DEC-002 | Strategy | Success metrics | Platform + customer success metrics (analytics, DS, <3s, NPS, traffic, etc.) | Gareth Bew | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-003 | Scope | MVP | MVP = new navigation (4 audiences) + secure web IA | Gareth Bew / Keshvi | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦QST-004
DEC-004 | Delivery | Migration dependencies | Identify & communicate dependencies + tasks per business area | Programme | Confirmed (intent) | Confirmed (intent) | - | D1¦S1¦SRC-001¦ACT-002
DEC-005 | Delivery | Whiteboard -> plan | Per-workstream whiteboard → programme plan + RAID | Gareth Bew | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-006 | Design | Design foundations | IA, navigation, templates, content/SEO/brand standards | Design / OMDS | Confirmed | Confirmed | - | D1¦S1¦SRC-001¦
DEC-007 | Governance | Handover governance | Approval routing & entry/exit gates between teams | Design / Programme | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦ACT-006
DEC-008 | Design | Page treatment | Product pages → new templates; others as-is/restyled | Design / Execution | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦QST-002
DEC-009 | Technical | Automated testing | Automated testing + DevOps pipeline enforcement | Execution | Yes | Proposed | Not confirmed | D1¦S1¦SRC-002¦RSK-006
DEC-010 | Resourcing | Dedicated publisher | Ring-fence dedicated migration publisher from BAU | Publishing / Programme | Yes | Proposed | Not confirmed | D1¦S1¦SRC-001¦ACT-003
DEC-011 | SEO | SEO lead time | SEO team ≥2 months before QA for tagging & validation | SEO / Programme | Confirmed (intent) | Confirmed (intent) | - | D1¦S1¦SRC-001¦DEP-009
DEC-012 | Migration | Phased decommissioning | Turn off legacy components progressively as migrated | Programme / Execution | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦ASM-011
DEC-013 | Brand | Faoli Bank separate brand | Bank as separate entity with own IA & governance | Programme | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦QST-017
DEC-014 | Governance | Design-phase skip | Allow some teams to skip design phase (dependency-based) | Gareth / Brent | Yes | Proposed | Not confirmed | D1¦S2-3¦SRC-005¦RSK-012
DEC-015 | Delivery | Phased audience-based delivery | Personal first (foundations end-June, section ~end-July), then Corporate → Business → Wealth (+Secure) | GB / Programme | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦DEC-001, QST-016, RSK-031
DEC-016 | Resourcing | Four-squad parallel model | Four concurrent squads (one per audience): lead designer + designer + content + tech support | Programme Leadership | Yes | Proposed (resource-gated) | Not confirmed | D2¦S1-2¦SRC-008/009¦QST-020, ACT-064, RSK-024, TO-7
DEC-017 | Design | Red/green-zone templates | Modular templates: red zones (fixed/governed) + green zones (variable); 2-3 standardised product templates | Design / Dev (Seba / Rey) | Confirmed | Confirmed | - | D2¦S1-2¦SRC-008/009¦TO-8, RSK-025
DEC-018 | Design | Template change-control | Post-sign-off red-zone changes trigger change management across content + code on all affected pages | Design / Programme | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦RSK-025
DEC-019 | Governance | Publishing gatekeeper gate | Design & publishing teams gatekeep; every page signed off before go-live; only trained builders publish; tenants onboarded to standards | Design / Publishing (GB / Natalie / Bernice) | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦DEC-007, RSK-027
DEC-020 | Technical | Content + analytics co-location | Co-locate content + analytics tagging in Contentstack to enable automation & SEO | Execution (Rey / Nithin) | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦ACT-060, RSK-011
DEC-021 | Technical | DevOps quality gates + Playwright | DevOps quality gates + automated testing (Playwright) + linting before production; rollout end-June with reporting | Execution | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦DEC-009
DEC-022 | Design | Personal foundations end-June | Sign off Personal IA + core templates + generic content guidelines by end-June | Design (Seba / Justin) | Confirmed | Confirmed | End June | D2¦S1¦SRC-008¦DEC-006, DEP-017
DEC-023 | Design | Article & news handling | Single consolidated article page; interim background-colour variant; news distinct (~1-yr retention, stays in footer) | Design / Content (GB / Justin) | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦DEC-024, QST-027
DEC-024 | Migration | Defer article/news URL structure | Defer article/news URL structure pending IA (target end-June); content audit + URL mapping per section as discovery deliverable | IA / Content (Justin / Bernice) | Yes | Deferred | End June | D2¦S1-2¦SRC-008/009¦ACT-057, ACT-066, DEP-005
DEC-025 | Migration | Country/site delivery model | Country teams own migration, depend on central for design/IA/nav/content; South Sudan = decommission-only; SA-first then roll out; small sites quick nav+footer retrofit | Programme / Regional (GB / Reza) | Confirmed (intent) | Confirmed (intent) | - | D2¦S1¦SRC-008¦ACT-063, ACT-074, ACT-083
DEC-026 | Governance | Tenant operating model | Post-migration tenants fund & manage own sites under formal partnership agreements | Programme (GB / Reza) | Yes | Proposed | Not confirmed | D2¦S1¦SRC-008¦ACT-080
DEC-027 | Governance | Unified Jira + cadence | Single Jira construct; leads enter milestones/priorities/deps/confidence; twice-weekly 30-min leadership check-ins + weekly playback | Programme (GB / Tsoaeli) | Confirmed | Confirmed | - | D2¦S1¦SRC-008¦ACT-055, ACT-062, ACT-069, ACT-070
DEC-028 | Brand | Bank owns its pages | Bank builds its own web pages; team involved only on bank-initiated redesign; confirm if OM finance pages move to bank | Programme | Confirmed (intent) | Confirmed (intent) | - | D2¦S1¦SRC-008¦DEC-013, QST-021, ACT-076

## Trade off's
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
TO-1 | Scope | Tactical vs strategic | Navigation-only vs full transformation | Gareth Bew / Keshvi | Choose scope option | Open | Day 2 | QST-016, RSK-019
TO-2 | Delivery | Speed vs rework | Migrate quickly vs wait for foundations | Programme | Accept rework risk? | Open | Not confirmed | DEC-008
TO-3 | Governance | Skip design vs full governance | Direct implementation for some teams | Gareth / Brent | Permit skip + criteria? | Open | Not confirmed | DEC-014
TO-4 | Design | Standardisation vs flexibility | Red zones vs modular green zones / snowflakes | Brent / OMDS | Balance standard vs modular | Open | Not confirmed | QST-014
TO-5 | Quality | Quality vs capacity | Best-practice templates vs available resources | Programme | Hold quality despite capacity? | Open | Not confirmed | GB stated quality must not be cut
TO-6 | Scope | Full vs selective migration | Move all content vs retire low-value pages | Programme / Execution | Confirm migration breadth | Open | Not confirmed | ASM-002
TO-7 | Resourcing | Parallel squads vs linear delivery | Four parallel squads vs current linear capacity | Programme Leadership | Approve squad capacity vs accept slip | Open | Not confirmed | DEC-016, RSK-024
TO-8 | Design | Red-zone stability vs green-zone flexibility | Fixed governed zones vs variable content zones | Design / Dev | Balance stability vs flexibility | Open | Not confirmed | DEC-017
TO-9 | Scope | Personal-first focus vs spreading thin | Focus Personal first vs spread across all segments | Programme | Focus vs spread across segments | Open | Not confirmed | DEC-015

## Lead Prep Artefacts
Preparation, Expected Outputs and Artefacts
Workstream | Lead / Facilitator | What each lead must bring | What the discussion must confirm | Artefact produced | Exit gate | Applies to | Status
Scope | Keshvi Singh | Confirm the business area in scope, journey or property name, current ownership, known in/out-of-scope items, assumptions, decision constraints, and BU approver where known. | Confirm the scope for each area or journey, including what is included, excluded, unresolved, or requiring escalation. | Scope Confirmation Line Item | Scope is confirmed, or marked TBC with a named owner and due date. | All OMCOZA area / journey rows | Partial — Day 1 blockers surfaced
Design Standards | Justin Evans | Bring the relevant design standards, OMDS component rules, existing component options, known component gaps, exceptions, and any standards or content rules that must be applied. | Confirm the standards position for the area or journey: existing component, new component required, exception needed, or no design-system impact. | Design Standards and Component Readiness Log | Component and standards status captured with owner and decision path. | All OMCOZA area / journey rows | TBC
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design work required, design owner, review route, target handover date, and any blockers. | Design Delivery Tracker | Design status and handover date captured, or blocker assigned. | All OMCOZA area / journey rows | TBC
Content Readiness | Natalie Patel | Bring the content inventory, current content quality view, content owner, required content action, approval route, and any compliance needs. | Confirm the content action, content owner, approver, due date, and readiness risk. | Content Readiness Register | Content action and approver captured for the area or journey. | All OMCOZA area / journey rows | All OMCOZA area / journey rows
Design System | Brent von Zitters | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design components ,pages required, review route, target handover date, and any blockers. | Updates to Design Systems | Design systerms updated handover date captured, or blocker assigned. | All OMCOZA area / journey rows
Feature Delivery | Wayne Moodley / Tebogo Segoje | Bring the feature scope, technical or feature needs, feature-team capacity, build dependencies, reusable component needs, delivery confidence, and date constraints. | Confirm whether feature-team involvement is required, the dependency, delivery commitment, and delivery risk. | Feature Delivery Dependency Log | Feature dependency and required date captured, or marked N/A. | All OMCOZA area / journey rows | TBC
Migration | Nithin Ramsaroop / Zethembiso Msomi / Luvuyo Mkumatela | Bring the proposed migration path, current platform position, technical onboarding status, environment dependencies, cross-team dependencies, and as-is versus restructure recommendation. | Confirm the migration pathway: restructure, migrate as-is, partial migration, full migration, no migration, retire, or decommission. | Migration Pathway Decision Sheet | Migration pathway captured with owner, prerequisite, and blocker. | All OMCOZA area / journey rows | TBC
Publishing / Release UAT | Bernice Bryce / BU SME / Execution | Bring the publishing route, CMS workflow, UAT owner, UAT scenarios, content approval status, release-window constraints, and publishing prerequisites. | Confirm the publishing and UAT path, required sign-offs, test ownership, and release hand-off. | Publishing and UAT Readiness Checklist | UAT owner, publishing route, and sign-off path captured. | All OMCOZA area / journey rows | TBC
Go-Live Readiness | Keshvi Singh / Execution | Bring go/no-go criteria, rollback needs, support and hypercare owner, BAU owner, monitoring or reporting owner, release communications, and escalation route. | Confirm release readiness and the operational handover position for the area or journey. | Go-Live and Operationalisation Checklist | Go-live prerequisites and BAU owner captured. | All OMCOZA area / journey rows | TBC