## Overview
Area / Journey | Business Area | Cluster |  |  |  | Total Effort
Personal / Bank | OM Bank | Bank / OMF |  |  | Faoli/OM Bank treated as separate brand - own IA & governance (DEC-013); confirm page ownership
Personal / Save | L&S | PF
Personal / Invest | Wealth | Wealth | Wealth CI may need separate platform/experience (ISS-001)
Personal / Funeral | L&S | MFC |  | EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9)
Personal / Insure | OMInsure | OMInsure / iWYZE
Personal / Rewards | Rewards | Rewards
Business / Corporate | L&S | Corporate
Adviser / Find an Adviser | GTT | Digital Channels |  | Find an Adviser Beta-ready, subject to DS V2 to Beta (DEP-3); advisor flow into beta (DEP-14)
Tools / Calculators | GTT | Digital Channels |  | PI2 calcs near Beta; Income Tax/Retirement/2-pot ready; Debt/Personal Loans/Budget in progress; ownerless calcs TBC (ACT-052)
Total

## Basic View
Web Transformation Workshop
[6 empty] | 1 |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10
[6 empty] | Scope |  |  | Design Standards |  |  |  |  | Design Delivery |  |  |  |  | Content Readiness |  |  |  |  | Feature Delivery |  |  |  |  | Design Systems |  |  |  |  | Migration |  |  |  |  | Publishing / Release UAT |  |  |  |  | Go Live Readiness |  |  |  |  | OMAR Impacts/ SEO / Analytics
[6 empty] | Keshvi Singh |  |  | Justin Evans | [5 empty] | Sebabatso Mtimkulu / Kameshnee Chetty |  |  |  | Natalie Patel |  |  |  |  | Wayne Moodley / Tebogo Segoje |  |  |  |  | Brent von Zitters |  |  |  |  | Zethembiso /Nithin / Execution |  |  |  |  | Gareth Bew / Bernice / Execution |  |  |  |  | Luvuyo / Keshvi Singh |  |  |  |  | Luvuyo / Keshvi Singh
# | Channel | Domain | Area / Journey | Business Area | Cluster | Status | Inputs | Output | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
1 | Public Web | OMCOZA | Personal / Bank | OM Bank | Bank / OMF | TBC | ** Area for leads to input their specific requirements relating to this business area | Personal / Bank: confirm Faoli/OM Bank separate-brand treatment, IA & bank-section page ownership (DEC-013, QST-017)
2 | Public Web | OMCOZA | Personal / Save | L&S | PF | TBC | Personal / Save (L&S / PF): confirm in/out of scope journeys
3 | Public Web | OMCOZA | Personal / Invest | Wealth | Wealth | TBC | Personal / Invest (Wealth): Wealth CI may be separate experience (ISS-001)
4 | Public Web | OMCOZA | Personal / Funeral | L&S | MFC | TBC | Personal / Funeral (MFC): EasiPlus depends on Funeral product page template + MFC sign-off (DEP-9)
5 | Public Web | OMCOZA | Personal / Insure | OMInsure | OMInsure / iWYZE | TBC | Personal / Insure (OMInsure/iWYZE): stress-test templates vs iWYZE
6 | Public Web | OMCOZA | Personal / Rewards | Rewards | Rewards | TBC | Personal / Rewards: component shared with L&S servicing needs update (Dep-10)
7 | Public Web | OMCOZA | Business / Corporate | L&S | Corporate | TBC | Business / Corporate (L&S): apply template structure to corporate cluster (ACT-043)
8 | Public Web | OMCOZA | Adviser / Find an Adviser | GTT | Digital Channels | TBC | Adviser / Find an Adviser (GTT): Beta-ready subject to DS V2 to Beta (DEP-3)
9 | Public Web | OMCOZA | Tools / Calculators | GTT | Digital Channels | TBC | Tools / Calculators (GTT): confirm V2 completeness, TFSA template & ownerless calcs (ACT-052/053)
[14 empty] | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems |  |  |  |  | Design Systems
[14 empty] | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller |  |  |  |  | Brent Van Ziller
[14 empty] | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies | Status | Task | Effort | Priority | Risks/Dependencies
[14 empty] | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress |  |  |  |  | In Progress

## Stream Inputs
Stream | Owner | Deliverable | Activity | Duration | Start Date | End Date | Dependency | Risk | Confidence
Design Standards | Justin Evans | Discovery | Analytics
Design Standards | Justin Evans | Discovery | Research
Design Standards | Justin Evans | Discovery | Stakeholder Engagement
Design Standards | Justin Evans | Discovery | Consolidate
Design Standards | Justin Evans | Discovery | Understand
Design Standards | Justin Evans | Discovery | SEO
Design Standards | Justin Evans | Discovery | Copy
Design Standards | Justin Evans | Discovery | Ecosystem
Design Standards | Justin Evans | Discovery | Product
Design Standards | Justin Evans | Discovery | Compliance
Design Standards | Justin Evans | Discovery | Brand
Design Standards | Justin Evans | Discovery | OMDS
Design Standards | Justin Evans | Design | Desktop
Design Standards | Justin Evans | Design | Mobile
Design Standards | Justin Evans | Design | Copy Ready
Design Standards | Justin Evans | Design | SEO ready
Design Standards | Justin Evans | Design | Stakeholder Review
Design Standards | Justin Evans | Design | DS review
Design Standards | Justin Evans | Design | Tech Review
Design Standards | Justin Evans | Design | Testing
Design Standards | Justin Evans | Approval | Group marketing
Design Standards | Justin Evans | Approval | Internal
Design Standards | Justin Evans | Approval | External
Design Standards | Justin Evans | Approval | Clusters
Design Standards | Justin Evans | Handover | Design Ready
Design Standards | Justin Evans | Handover | DS review
Design Standards | Justin Evans | Handover | Final copy
Design Standards | Justin Evans | Handover | Sign-offs
Design Standards | Justin Evans | Handover | Rules
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | IA + Navigation container
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Journeys + Audience (generic)
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Templates (structural)
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | - Fit IA gap
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | - Support findability
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Landing page audience + sections
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Category
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Product
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Utility - Contact
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Utility - About
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Utility - Calculators
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | Content standards
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | OMDS enhancements
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | OMDS new
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Foundations | OMDS UI + Brand
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Journeys | Findability
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Journeys | Intent
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Journeys | Access to product info
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Journeys | Flow + page principles
Migration | Zee Msomi | Tech Uplift | Automated testing framework
Migration | Zee Msomi | Tech Uplift | DevOps pipelines to enforce delivery quality
Migration | Zee Msomi | Tech Uplift | AI-assisted Development
Migration | Zee Msomi | Operability | Observability, migrating Dynatrace
Migration | Zee Msomi | Operability | Grafana dashboard (OMAR)
Migration | Zee Msomi | Operability | Analytics - co-locating analytics tagging with content
Migration | Zee Msomi | Migration | Ensure all content is moved |  |  |  | Decommission depends on full content move (ASM-002)
Migration | Zee Msomi | Migration | Decon 'old' platform |  |  |  | Phased decommissioning as migrated (DEC-012)
Migration | Zee Msomi | Migration | Consume Designs for Navigation and Pages
Migration | Zee Msomi | Migration | Audit whats available in Figma
Migration | Zee Msomi | Migration | Templates - similar pages reviewed between sites
Migration | Zee Msomi | Migration | Whats outstanding in OMDS?
Migration | Zee Msomi | Migration | Stkaeholder reviews
Migration | Zee Msomi | Migration | V2 'as-is' migration review
Migration | Zee Msomi | Migration | - OMAR sites
Migration | Zee Msomi | Migration | - L&S, UT, etc
Migration | Zee Msomi | Migration | Information architecture WT & V2 nav components
Migration | Zee Msomi | Environment | Setup environment + staging
Migration | Zee Msomi | Contentstack | Complete development in Contentstack |  |  |  | Publishing & testing depend on this
Migration | Zee Msomi | Beta | Staging in Beta
Migration | Zee Msomi | Move to Prod | Production / testing / tooling
Publishing | Bee Bryce | Update Contentstack | Complete Dev work in Contentstack
Publishing | Bee Bryce | URL structure | Complete URL structure & obtain sign-off |  |  |  | ~95% of URLs change; sign-off required (ACT-017)
Publishing | Bee Bryce | New Templates | Create new templates in Beta | 2 hours per page |  |  |  | Capacity risk - 2 publishers only (RSK-008/011)
Publishing | Bee Bryce | Build As-Is pages | Rebuild As-Is pages in Beta | 30 min per page
Publishing | Bee Bryce | Navigation + Footer | Complete navigation & footer for As-Is pages
Publishing | Bee Bryce | Testing | Testing all pages in Beta
Feature Delivery | Wayne - Cross Channels | Find an Adviser | Build feature to include design system V2 & deploy to Beta
Feature Delivery | Wayne - Cross Channels | Calculators (in progress) | Complete build on Debt calculator, Personal Loans calculator, Budget calculator
Feature Delivery | Wayne - Cross Channels | Calculators (ready for Beta) | Testing Income Tax calculator, Retirement calculator, 2 pot savings calculator
Feature Delivery | Tebogo Segoje (L&S serv) | Public Web | Funeral & Death Claims
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Transaction tracking
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Lump sum injections
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Change personal details
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Manage contributions
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Switch Funds
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Withdrawals / Disinvestments
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | Change premium allocation
Feature Delivery | Tebogo Segoje (L&S serv) | Secure Web | 2-pot
Go-Live readiness | Luvuyo Mkumatela | Pen test | Pen testing (ZA + OMAR) |  |  |  | CISO engagement required (DEP-14)
Go-Live readiness | Luvuyo Mkumatela | QA | QAG
Go-Live readiness | Luvuyo Mkumatela | ServiceNow updates | SNOW updates |  |  |  | ServiceNow API updates before prod (DEP-15)
Go-Live readiness | Luvuyo Mkumatela | Approvals | Security Approvals
Go-Live readiness | Luvuyo Mkumatela | Comms | Call Centre Comms
OMAR | Luvuyo Mkumatela / Keshvi | Navigation | Navigation
OMAR | Luvuyo Mkumatela / Keshvi | Page Builds | Page development
SEO | Bernice Bryce / Luvuyo | SEO (Pre-prod, QA & Beta) | Tools |  |  |  |  | SEO not ready - blocking; >=2 months lead (RSK-013)
SEO | Bernice Bryce / Luvuyo | SEO (Pre-prod, QA & Beta) | Site tagging (current)
SEO | Bernice Bryce / Luvuyo | Analytics | Google Analytics (new site tagging)
SEO | Bernice Bryce / Luvuyo | Analytics | Customer experience tool (glassbox)
SEO | Bernice Bryce / Luvuyo | Analytics | OMAR analytics (country requirements)
SEO | Bernice Bryce / Luvuyo | Analytics | Tableau integration

## Roadmap
Workstream | Milestone | Owner | Start Date | End Date | Dependency | Status | Comments
SEO Engagement | detailed SEO action plan of what we are working on for the rest of the year | Luvuyo/ Nondalo | 2026-06-08 | 2026-06-12 | CMO officer approval |  | Kick off held meeting held 27 May
Go Live Readiness | Security Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | Engagment wth CISO Office |  | Requested options for Penetratrion Testing
OMAR Engagement | Re ALlignment with OMAR Teams | Keshvi / Luvuyo | 2026-06-08 | 2026-06-12 | Irene Availability and in country teams
Go Live Readiness | QAG Team Engagement | Luvuyo | 2026-06-09 | 2026-06-09 | QAG Team |  | Requested options for Penetratrion Testing
Scope Definition | Resolve migration vs transformation scope + options for stakeholders | Gareth Bew / Keshvi | Day 2 | Not confirmed | Sponsor / Steering | In Progress | Full scope ~2027 vs end-Nov (RSK-010)
Publishing | Confirm dedicated OMAR publishing capacity + tracker | Bernice Bryce | Not confirmed | Not confirmed | Programme capacity decision | Not started | RSK-008/011
Design Systems | OMDS operating model + component audit + DS V2 to Beta | Brent von Zitters | Not confirmed | Not confirmed | DS team capacity | Not started | RSK-014
Migration | URL audit + as-is definition + environment strategy | Natalie / Nithin / Zee | Not confirmed | Not confirmed | Scope decision | Not started | ACT-004/009/017
Go Live Readiness | Go-live readiness checklist (pen-test, ServiceNow, comms, decommission) | Luvuyo Mkumatela | Not confirmed | Not confirmed | Security/QAG engagement | Not started | RSK-016
Knowledge | Stand up centralised documentation / knowledge system | Gareth Bew | Not confirmed | Not confirmed | - | Not started | RSK-017

## Dependencies
ID | Stream | Dependency | Owner | Required By | Impact if Late | Mitigation | Escalation Path | Status
Dep-1 | Publishing | SA - only 2 resources split across BAU and Transformation work | Bernice Bryce | Before publishing phase | Migration publishing throughput insufficient | Dedicated OMAR publisher; ring-fence BAU (ACT-003) | Programme / Steering | Open
Dep-2 | Publishing | OMAR - no publishers | Bernice Bryce | Before OMAR publishing | OMAR pages cannot be published | Identify/secure OMAR publishing capacity | Programme / Steering | Open
Dep-3 | Publishing | Publishing can only start once all Dev work has been completed in Contentstack | Nithin Ramsaroop / Zee Msomi | Per area | Publishing blocked | Sequence Contentstack dev completion; track in Basic View | Programme | Open
Dep-4 | Publishing | All content & assets needs to be signed off | Natalie Patel | Per area | Publishing blocked / rework | Content packs + sign-off gate (ACT-019) | Programme | Open
Dep-5 | Publishing | Approved URL structure to be provided | Natalie Patel | Before build | Build blocked; redirects wrong | URL audit + sign-off (ACT-017) | Programme | Open
Dep-6 | Publishing | Completed Designs, Dev work & Content | Design / Execution | Before publishing | Publishing blocked | Enforce exit gates per stage (DEC-007) | Programme | Open
Dep-7 | Cross Channel | From end of PI2, cross channel team is dependant on the Web platform team for FE work | Wayne Moodley | End PI2 | FE delivery velocity drops | Web Platform capacity/prioritisation model (ACT-021) | Programme | Open
Dep-8 | Cross Channel | Easy plus sales journey - journey migration is depedant on the Funeral product page template and requires MFC sign-off | Wayne Moodley | Before EasiPlus enablement | EasiPlus journey blocked | Escalate MFC sign-off + Funeral product page template (ACT-023) | Cross Channels / Programme | Open
Dep-9 | Cross Channel | Contact Us - analysis & design needs to be planned for | Wayne Moodley | PI3 | Contact Us slips | Plan analysis/design in PI3 (ACT-045) | Cross Channels | Open
Dep-10 | L&S Servicing | There is a dependency on a component of the journey built by the Rewards team that currently requires updates, as it is causing inconsistencies between the app and web experiences. Alignment is needed with the Rewards team to determine the appropriate approach before the migration can proceed. This dependency may im | Tebogo Segoje | Before L&S servicing migration | App/web inconsistency; migration blocked | Align with Rewards team on approach | Programme | Open
Dep-11 | Web - Execution | Design system components ( Nav and Product Pages) | Zee Msomi / Brent von Zitters | Before page build | Page build blocked | Prioritise Nav & Product Page DS components (PRK-009) | Programme | Open
Dep-12 | Cross Channel | Notify e-commerce (Nthabi) of URL changes so Google Analytics tracking is updated | Wayne Moodley | Pre go-live | Broken exec sales/traffic reporting | Notify Nthabi; align tracking (ACT-046) | Programme | Open
Dep-13 | Go Live / Security | Security-team confirmation on pen-test / crowdsource testing before go-live | Luvuyo Mkumatela | Pre go-live | Go-live blocked / security exposure | CISO Office engagement (see Roadmap) | Programme / CISO | Open
Dep-14 | Go Live | ServiceNow API updates + QA/security/marketing approvals before production | Luvuyo Mkumatela | Pre go-live | Production deployment blocked | Complete SNOW updates; QAG engagement | Programme | Open
Dep-15 | SEO | SEO >=2 months lead before QA for tagging & validation | Bernice Bryce / Luvuyo | ≥ 2 months pre-QA | Go-live blocked by SEO | Engage SEO early; SEO action plan (Roadmap) | Programme | Open
Dep-16 | OMAR | OMAR team scope & partnership-management confirmation | Megan | Early | Regional scope unclear | Re-engage OMAR team (ACT-049) | Programme | Open
Dep-17
Dep-18
Dep-19
Dep-20

## Critical Path
Sequence | Activity | Owner | Predecessor | Start Date | End Date | Critical (Y/N) | Notes
1 | Confirm scope (migration vs transformation / tactical option) | Gareth Bew / Keshvi | - | Day 2 | Not confirmed | Y | Master gate (DEC-001)
2 | Define 'as-is' + page-treatment rules | Design / Programme | 1 | Not confirmed | Not confirmed | Y | ACT-004
3 | Design foundations (IA, navigation, templates, standards) | Design / OMDS | 1 | Not confirmed | Not confirmed | Y | DEC-006
4 | DS component audit + build (Nav, Product pages, DS V2) | Brent / Zee Msomi | 3 | Not confirmed | Not confirmed | Y | DEP-12, RSK-014
5 | URL audit + structure sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | ACT-017
6 | Content readiness + packs + sign-off | Natalie Patel | 2 | Not confirmed | Not confirmed | Y | DEP-5
7 | Complete development in Contentstack | Nithin / Zee Msomi | 4 | Not confirmed | Not confirmed | Y | DEP-4
8 | Build pages in Beta (new templates + as-is) | Bernice Bryce / Publishing | 5,6,7 | Not confirmed | Not confirmed | Y | Publishing gate
9 | SEO tagging (>=2 months before QA) | Bernice / Luvuyo | 5 | Not confirmed | Not confirmed | Y | DEP-16
10 | Testing all pages in Beta | Publishing / QA | 8 | Not confirmed | Not confirmed | Y | DEP-2 (testing)
11 | Pen-test + QAG + ServiceNow + approvals | Luvuyo Mkumatela | 10 | Not confirmed | Not confirmed | Y | RSK-016, DEP-14/15
12 | Go-live + phased decommission | Programme | 11 | Not confirmed | End November | Y | DEC-012 (hard deadline)

## RAID Log
Type | ID | Stream | Description | Owner | Impact | Probability | Mitigation | Due Date | Status
Risk | RSK-001 | Cross Channel | FE resources - dev resources will move out of Cross Channel team | Wayne Moodley | High | High | Post-PI2 FE transition plan; formalise Web Platform capacity & prioritisation (ACT-021) | End PI2 | Open
Risk | RSK-002 | Cross Channel | BA capacity (extended medical leave + new recruit) | Wayne Moodley / Cross Channels | Medium | High | Secure interim BA capacity; accelerate recruitment (ACT-022) | Not confirmed | Open
Risk | RSK-003 | OMAR | Resources that cuts across regions have left t thoe organisation (RTE) | Programme / Keshvi Singh | High | High | Resource review; confirm regional delivery capacity (ACT-014) | Not confirmed | Open
Risk | RSK-004 | OMAR - Nam | Secure Web - Migration at risk due to the fact that 2 resources split across deliveries | Luvuyo Mkumatela / Regional | High | High | Secure web mitigation plan; confirm owner (ACT-015) | Not confirmed | Open
Risk | RSK-005 | OMAR - Nam | Team has recently taken over migrating the of servicing transactions. with 2 resources having to manage the Secure Web , and Public Web Migration it is a big RIsk | Regional (Namibia) | High | High | Recovery plan for Namibia secure + servicing (ACT-015/016) | Not confirmed | Open
Risk | RSK-006 | OMAR Botswana | 1 out of 9 Sales journey completed thus far | Regional (Botswana) | High | High | Botswana recovery plan for remaining 8 of 9 transactions (ACT-016) | Not confirmed | Open
Risk | RSK-007 | OMAR Overall | Reduced development delivery across the OMAR Region | Programme / Execution | High | High | Confirm regional delivery capacity; scope options (ACT-014/028) | Not confirmed | Open
| RSK-008 | OMAR Publishing of Sites | Publishing SA and OMAR = Bernice | Bernice Bryce | High | High | Dedicated OMAR/SA publishing capacity + tracker (ACT-003/005) | Not confirmed | Open
Risk | RSK-009 | Programme | Migration vs transformation scope ambiguity changes scope, effort, budget, timeline & risk | Gareth Bew / Keshvi Singh | Very High | High | Formal scope decision + revised plan; tactical vs strategic options (ACT-001/028) | Day 2 | Open
Risk | RSK-010 | Programme | Full discussed scope implies ~end-2027 vs fixed end-Nov budget window | Gareth Bew | High | High | Gap analysis; agree tactical scope e.g. navigation-only (ACT-028, QST-016) | Day 2 | Open
Risk | RSK-011 | Publishing | 'As-is' definition unclear -> blocks estimates, testing scope, decommission | Programme / Design | High | High | Define & approve as-is (ACT-004) | Not confirmed | Open
Risk | RSK-012 | Execution | ~95% of URLs changing; redirect handling + GA tracking / e-commerce campaign impact | Execution / Natalie Patel | High | High | URL audit; redirect plan; notify e-commerce/Nthabi (ACT-017/046) | Not confirmed | Open
Risk | RSK-013 | SEO | SEO not ready + ownership not finalised; needs >=2 month lead before QA | SEO / Luvuyo / Bernice | High | High | SEO/analytics workshop; appoint owner; SEO gates (ACT-012) | Not confirmed | Open
Risk | RSK-014 | Design Systems | Most components not in Contentstack; DS V2 dependency blocks Beta | Brent von Zitters / Zee Msomi | High | High | Figma/DS component audit; DS V2 to Beta (ACT-008/047) | Not confirmed | Open
Risk | RSK-015 | Execution | Environment sequencing (Beta/Staging/Prod/tooling) undefined | Nithin Ramsaroop / Zee Msomi | Medium | High | Environment strategy & ownership (ACT-009) | Not confirmed | Open
Risk | RSK-016 | Go Live | Go-live readiness open: pen-test, ServiceNow, security, comms, decommission | Luvuyo Mkumatela | High | High | Go-live readiness checklist; security & QAG engagement (ACT-013) | Not confirmed | Open
Risk | RSK-017 | Programme | No centralised/shared knowledge system -> delays, lost history | Gareth Bew | High | Medium | Stand up centralised documentation system (ACT-054) | Not confirmed | Open
Risk | RSK-018 | Design Systems | OMDS treated as UI library not governance; component sprawl / design debt | Brent von Zitters | Medium | High | OMDS operating model + component lifecycle (ACT-006/007) | Not confirmed | Open
Issue | ISS-001 | Brand / CI | Full Brand/CI not approved (only interim brand: fonts/logo) | Brand / Group Marketing | High | - | Secure early CI / confirm interim route + exception handling | Not confirmed | Open
Issue | ISS-002 | Publishing | One person covers publishing across everything; small change = touch every page | Natalie Patel / Programme | High | - | Dedicated publishing capacity (ACT-003) | Not confirmed | Open
Issue | ISS-003 | Secure Web | Secure web incomplete (product views, dashboards); 'learn more' on old platform; no service-tree solution | Programme / Execution | High | - | Mitigation plan + service-team solution (ACT-015) | Not confirmed | Open
Issue | ISS-004 | Planning | No reliable total page count; manual Google-Sheet tracking | Natalie Patel | Medium | - | Updated inventory + better tracker (ACT-005) | Not confirmed | Open
Assumption | ASM-001 | Programme | End-November deadline fixed and achievable within escalated capacity | Programme / Sponsor | High | - | Confirm scope-capacity-date trade-off (ACT-028) | Not confirmed | Open
Assumption | ASM-002 | Execution | All content must move because old platform must be decommissioned | Programme / Execution | Medium | - | Confirm full vs selective migration scope | Not confirmed | Open
Assumption | ASM-003 | Publishing | 2h/new-template & 30min/as-is page hold at scale | Natalie Patel | Medium | - | Validate vs real throughput + hardcoded-content remediation | Not confirmed | Open
Assumption | ASM-004 | Scope | A tactical scope (e.g. navigation-only) can deliver value within the window | Programme | High | - | Validate via options + gap analysis (ACT-028) | Not confirmed | Open

## Governance
Forum | Purpose | Chair | Participants | Cadence | Inputs | Outputs | Escalation Route
Steering Committee | Programme oversight; scope/budget/risk decisions; shutdown & go-live approvals | Sponsor (TBC) | Exec sponsors, programme leads | TBC | Consolidated RAID, risk view, scope options | Decisions, approvals, escalations | Sponsor / Exec
Programme Delivery Sync | Track delivery, dependencies and blockers across streams | Gareth Bew | Stream leads | Weekly (TBC) | Basic View, Stream Inputs, Action Log | Updated tracker, actions | Steering Committee
OMDS / Design Authority | Component governance, standards, approvals, lifecycle & exceptions | Brent von Zitters | DS team, Design leads, Group Marketing | TBC | Component requests, designs | Approved components, standards, exceptions | Head of Design -> Programme
Design Handover / Exit-Gate Review | Confirm Definition of Done & handover design->build->publish | Design & Content leads | Design, DS, Web Dev, Publishing | Per area | Designs, content packs, sign-offs | Handover sign-off | Programme
SEO & Analytics Forum | Confirm SEO/analytics ownership, tooling, tagging standards | Luvuyo / Bernice | SEO, Analytics, Execution | TBC | SEO action plan, tagging requirements | Tagging standards, SEO sign-off | Programme / CMO
Go-Live Readiness Review | Go/no-go; security, ServiceNow, comms, decommission readiness | Keshvi / Luvuyo | Execution, Security, Ops, Comms | Per release | Readiness checklist | Go/no-go decision | Steering Committee

## Action Log
# | Area / Journey | Workstream | Priority | Issue / Decision / Action | Owner | Due Date | Status | Notes
1 | All / OMCOZA | Migration / Publishing | Critical | URL Audit - map all current URLs to new-world IA; redirects + switch-off | Natalie Patel / Execution | Not confirmed | Open | ~95% of URLs change; migration control not publishing admin (ACT-017)
2 | All | Programme | Critical | Resolve & document scope decision (migration vs transformation vs tactical hybrid) | Gareth Bew / Keshvi | Day 2 | Open | Master gate (DEC-001, RSK-009)
3 | All | Design / Programme | Critical | Define & approve the 'as-is' migration definition | Programme / Design | Not confirmed | Open | Blocks estimates/testing/decommission (ACT-004)
4 | OMAR / SA | Publishing | Critical | Confirm & secure dedicated publishing resource for OMAR; ring-fence BAU | Bernice Bryce / Programme | Not confirmed | Open | Only 2 publishers today (ACT-003)
5 | All | Publishing | High | Create complete page inventory + publishing tracker; capacity model vs 1,530 baseline | Natalie Patel | Not confirmed | In Progress | (ACT-005)
6 | Design Systems | OMDS | High | Formalise OMDS operating model, design authority, approval SLAs & exceptions | Brent von Zitters | Not confirmed | Open | (ACT-006)
7 | Design Systems | OMDS | High | Define component lifecycle + component impact register | Brent von Zitters | Not confirmed | Open | (ACT-007)
8 | Migration | Execution | High | Complete Figma & Design System component audit | Zee Msomi / Brent | Not confirmed | Open | (ACT-008)
9 | Migration | Execution | High | Define Beta/Staging/Production environment strategy & ownership | Nithin / Zee Msomi | Not confirmed | Open | (ACT-009)
10 | Migration | Execution | High | Define & implement automated testing framework + DevOps quality gates | Zee Msomi / Daniel | Not confirmed | Open | (ACT-010/050; Daniel capacity risk)
11 | Migration | Execution | Medium | Define observability (Dynatrace browser+server, Grafana, CMS analytics tagging) | Nithin Ramsaroop | Not confirmed | Open | (ACT-011/051)
12 | OMAR / SEO | SEO | High | Run SEO & analytics workshop - confirm ownership, tooling, tagging standards | Luvuyo / Bernice | Not confirmed | Open | SEO not ready; >=2mo lead (ACT-012)
13 | Go Live | Programme | High | Build go-live readiness checklist (pen-test, QAG, ServiceNow, security, comms, decommission) | Luvuyo Mkumatela | Not confirmed | Open | (ACT-013)
14 | OMAR | Programme | High | Run resource review; confirm regional delivery capacity | Keshvi / Programme | Not confirmed | Open | (ACT-014)
15 | OMAR - Nam | Regional | High | Mitigation plan for secure web migration & servicing transactions | Regional / Luvuyo | Not confirmed | Open | (ACT-015)
16 | OMAR - Botswana | Regional | High | Botswana recovery plan for remaining servicing transactions | Regional | Not confirmed | Open | 1 of 9 done (ACT-016)
17 | All | Programme | Critical | Gap analysis: committed scope vs realistic 5-month deliverables; produce options | Gareth Bew / Keshvi | Day 2 | Open | Full scope ~2027 (ACT-028, RSK-010)
18 | All | Content | High | Content audit per section (migrate/consolidate/delete/rewrite) + assign ownership | Natalie Patel | Not confirmed | Open | (ACT-044)
19 | Cross Channel | Cross Channels | High | Notify e-commerce (Nthabi) of URL changes for GA tracking | Wayne Moodley | Not confirmed | Open | (ACT-046, DEP-13)
20 | Migration | Execution | High | Tag Figma designs to DS components; map names to Contentstack & code | Execution / Design | Not confirmed | Open | (ACT-047)
21 | All | Programme | High | Create centralised documentation / knowledge system | Gareth Bew | Not confirmed | Open | Root-cause of delay (ACT-054, RSK-017)
22 | OMAR | Programme | High | Re-engage OMAR team to confirm scope + partnership management | Megan | Not confirmed | Open | (ACT-049)
23 | Personal / Bank | Programme | High | Clarify Faoli/OM Bank as separate brand + confirm bank-section page ownership | Gareth Bew | Not confirmed | Open | (DEC-013, QST-017)
24 | Tools / Calculators | Cross Channels | Medium | Review calculators V2 completeness; confirm TFSA template + ownerless calcs | Gareth / Wayne | Not confirmed | Open | (ACT-052/053, QST-012/018)
25 | Design Standards | Design | High | Define comprehensive Definition of Done for design artifacts (incl. SEO input) | Brent / Gareth | Not confirmed | Open | (ACT-038)
26 | Design Standards | Design | High | Outline approval process for design artifacts (marketing/product/brand sign-offs) | Brent / Gareth | Not confirmed | Open | (ACT-039)
27 | Design Delivery | Design | High | Finalise template structure & hand to build for parallel development | Gareth / Design | Not confirmed | Open | (ACT-041)
28 | All | Programme | High | Translate whiteboard outputs into detailed Excel plan (tasks, milestones, dates) | Gareth Bew | Not confirmed | In Progress | (ACT-026 - this workbook)
29 | All | Design | High | Sequence captured ideas; draft logical platform roadmap | Design team | Not confirmed | Open | (ACT-030)
30 | Go Live | Go Live | High | Confirm pen-test / crowdsource testing requirement with security (CISO) | Luvuyo Mkumatela | 2026-06-09 | Open | (DEP-14, Roadmap)
31 | Go Live | Go Live | High | Complete ServiceNow API updates + QA/security/marketing approvals | Luvuyo Mkumatela | Not confirmed | Open | (DEP-15)
32 | Migration | Execution | Medium | Define phased decommissioning process (turn off legacy as migrated) | Programme / Execution | Not confirmed | Open | (DEC-012)

## Key Decisions
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
DEC-001 | Scope | Migration vs transformation | Define & bound programme scope: content migration, web transformation, or bounded hybrid | Gareth Bew / Keshvi | Yes - Critical | Proposed / Open | Day 2 | Defining question; drives all downstream (RSK-009)
DEC-002 | Strategy | Success metrics | Adopt platform + customer success metrics (analytics, DS compliance, <3s load, NPS, organic traffic, etc.) | Gareth Bew | Confirmed | Confirmed | - | Basis for prioritisation
DEC-003 | Scope | MVP | MVP = new navigation for 4 simplified audiences + secure web IA | Gareth Bew / Keshvi | Confirmed | Confirmed | - | Detailed MVP deliverable still to define (QST)
DEC-004 | Delivery | Migration dependencies | Identify & communicate dependencies (OMA, rewards, site owners) + tasks per business area | Programme | Confirmed (intent) | Confirmed (intent) | - | Execution via ACT-002
DEC-005 | Delivery | Whiteboard -> plan | Run per-workstream whiteboard exercise; consolidate into programme plan + RAID/action/decision logs | Gareth Bew | Confirmed | Confirmed | - | Executed in session
DEC-006 | Design | Design foundations | Establish IA, navigation, templates and content/SEO/brand standards as migration foundation | Design / OMDS | Confirmed | Confirmed | - | Foundational
DEC-007 | Governance | Handover governance | Define governance, approval routing & entry/exit-gate handover criteria between teams | Design / Programme | Yes | Proposed | Not confirmed | SLAs/exceptions outstanding (ACT-006)
DEC-008 | Migration | Page treatment | Product pages -> new templates; other pages move as-is / restyle / retain UI | Design / Execution | Yes | Proposed | Not confirmed | Depends on as-is definition (QST-002)
DEC-009 | Technical | Automated testing | Implement automated testing + DevOps pipeline/quality-gate enforcement | Execution | Yes | Proposed | Not confirmed | Daniel capacity risk (RSK)
DEC-010 | Resourcing | Dedicated publisher | Ring-fence dedicated migration publisher, separate from BAU | Publishing / Programme | Yes | Proposed | Not confirmed | (ACT-003)
DEC-011 | SEO | SEO lead time | Engage SEO team >=2 months before QA for tagging & validation | SEO / Programme | Confirmed (intent) | Confirmed (intent) | - | Owner/tooling TBC (ACT-012)
DEC-012 | Migration | Phased decommissioning | Turn off legacy components progressively as migrated (not all at end) | Programme / Execution | Yes | Proposed | Not confirmed | Define process/sequencing (ACT-032)
DEC-013 | Brand | Faoli / OM Bank separate brand | Treat the bank as a separate entity/brand with own IA & governance | Programme | Yes | Proposed | Not confirmed | Confirm brand name + page ownership (QST-017)
DEC-014 | Governance | Design-phase skip | Allow some teams to skip design phase & implement directly (dependency-based) | Gareth / Brent | Yes | Proposed | Not confirmed | Needs criteria; design-drift risk (RSK-018)

## Trade off's
ID | Category | Item | Description | Owner | Decision Required | Status | Due Date | Notes
TO-1 | Scope | Tactical vs strategic | Navigation-only / phased quick deliverable vs full web transformation | Gareth Bew / Keshvi | Choose scope option for the timeline | Open | Day 2 | Full scope ~end-2027 vs end-Nov; 6-month deliverable needs reduced scope (QST-016, RSK-010)
TO-2 | Delivery | Speed vs rework | Migrate pages quickly without full template alignment vs wait for foundations | Programme | Accept rework risk? | Open | Not confirmed | GB: accept potential rework if migrated quickly (DEC-008)
TO-3 | Governance | Skip design vs full governance | Allow direct implementation for some teams vs full design lifecycle | Gareth / Brent | Permit design-phase skip + criteria? | Open | Not confirmed | Speed vs design drift (DEC-014, RSK-018)
TO-4 | Design | Standardisation vs flexibility | Rigid red zones vs modular green zones / 'snowflakes' | Brent / OMDS | Balance standard vs modular | Open | Not confirmed | (QST-014)
TO-5 | Quality | Quality vs capacity | Best-practice templates vs available resources | Programme | Hold quality despite capacity? | Open | Not confirmed | GB: template quality must not be cut for capacity
TO-6 | Scope | Full vs selective migration | Move all content (for decommission) vs consolidate/retire low-value pages | Programme / Execution | Confirm migration breadth | Open | Not confirmed | (ASM-002; page count 2,500 -> ~1,000)

## Lead Prep Artefacts
Preparation, Expected Outputs and Artefacts
Workstream | Lead / Facilitator | What each lead must bring | What the discussion must confirm | Artefact produced | Exit gate | Applies to | Status
Scope | Keshvi Singh | Confirm the business area in scope, journey or property name, current ownership, known in/out-of-scope items, assumptions, decision constraints, and BU approver where known. | Confirm the scope for each area or journey, including what is included, excluded, unresolved, or requiring escalation. | Scope Confirmation Line Item | Scope is confirmed, or marked TBC with a named owner and due date. | All OMCOZA area / journey rows | TBC
Design Standards | Justin Evans | Bring the relevant design standards, OMDS component rules, existing component options, known component gaps, exceptions, and any standards or content rules that must be applied. | Confirm the standards position for the area or journey: existing component, new component required, exception needed, or no design-system impact. | Design Standards and Component Readiness Log | Component and standards status captured with owner and decision path. | All OMCOZA area / journey rows | TBC
Design Delivery | Sebabatso Mtimkulu / Kameshnee Chetty | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design work required, design owner, review route, target handover date, and any blockers. | Design Delivery Tracker | Design status and handover date captured, or blocker assigned. | All OMCOZA area / journey rows | TBC
Content Readiness | Natalie Patel | Bring the content inventory, current content quality view, content owner, required content action, approval route, and any compliance needs. | Confirm the content action, content owner, approver, due date, and readiness risk. | Content Readiness Register | Content action and approver captured for the area or journey. | All OMCOZA area / journey rows | All OMCOZA area / journey rows
Design System | Brent von Zitters | Bring the current design status, required screens, pages or templates, SME review needs, dependencies on IA, content or components, and the target design handover date. | Confirm the design components ,pages required, review route, target handover date, and any blockers. | Updates to Design Systems | Design systerms updated handover date captured, or blocker assigned. | All OMCOZA area / journey rows
Feature Delivery | Wayne Moodley / Tebogo Segoje | Bring the feature scope, technical or feature needs, feature-team capacity, build dependencies, reusable component needs, delivery confidence, and date constraints. | Confirm whether feature-team involvement is required, the dependency, delivery commitment, and delivery risk. | Feature Delivery Dependency Log | Feature dependency and required date captured, or marked N/A. | All OMCOZA area / journey rows | TBC
Migration | Nithin Ramsaroop / Zethembiso Msomi / Luvuyo Mkumatela | Bring the proposed migration path, current platform position, technical onboarding status, environment dependencies, cross-team dependencies, and as-is versus restructure recommendation. | Confirm the migration pathway: restructure, migrate as-is, partial migration, full migration, no migration, retire, or decommission. | Migration Pathway Decision Sheet | Migration pathway captured with owner, prerequisite, and blocker. | All OMCOZA area / journey rows | TBC
Publishing / Release UAT | Bernice Bryce / BU SME / Execution | Bring the publishing route, CMS workflow, UAT owner, UAT scenarios, content approval status, release-window constraints, and publishing prerequisites. | Confirm the publishing and UAT path, required sign-offs, test ownership, and release hand-off. | Publishing and UAT Readiness Checklist | UAT owner, publishing route, and sign-off path captured. | All OMCOZA area / journey rows | TBC
Go-Live Readiness | Keshvi Singh / Execution | Bring go/no-go criteria, rollback needs, support and hypercare owner, BAU owner, monitoring or reporting owner, release communications, and escalation route. | Confirm release readiness and the operational handover position for the area or journey. | Go-Live and Operationalisation Checklist | Go-live prerequisites and BAU owner captured. | All OMCOZA area / journey rows | TBC