## Risks
Ref | Risk | Category | Probability | Impact | Score | Status | Owner | Mitigation discussed | Mitigation required | Escalation required | Due date | Workstream | Project | Task | Deliverable | Workshop day | Session | Trace ref
RSK-001 | Migration vs transformation scope ambiguity | BUSINESS | HIGH | HIGH | 9 | Escalated | Programme (GB) | — | Formal scope decision (ACT-001) | — | Day 2 | — | — | — | — | — | — | —
RSK-002 | Publishing capacity insufficient (~1,530 pages, 2 publishers) | RESOURCE | HIGH | HIGH | 9 | Escalated | Publishing/Programme | — | Dedicated OMAR capacity (ACT-003) | Escalated for governance review | Not confirmed | — | — | — | — | — | — | —
RSK-003 | 'As-is' definition unclear | PROCESS | HIGH | HIGH | 9 | Open | Programme/Design | — | Define as-is (ACT-004) | — | Not confirmed | — | — | — | — | — | — | —
RSK-004 | URL audit/redirect handling incomplete | TECHNICAL | MEDIUM | HIGH | 6 | Open | Execution | — | URL audit (ACT-017) | — | Not confirmed | — | — | — | — | — | — | —
RSK-005 | Regional resources cut | RESOURCE | HIGH | HIGH | 9 | Open | Programme/Regional | — | Resource review (ACT-014) | — | Not confirmed | — | — | — | — | — | — | —
RSK-006 | Daniel limited capacity for automation/testing | RESOURCE | MEDIUM | MEDIUM | 4 | Open | Execution | — | Automation plan (ACT-010) | — | Not confirmed | — | — | — | — | — | — | —
RSK-007 | OMDS treated as UI library not governance | GOVERNANCE | MEDIUM | HIGH | 6 | Open | OMDS | — | Operating model (ACT-006) | — | Not confirmed | — | — | — | — | — | — | —
RSK-008 | Most components don't exist in Contentstack | TECHNICAL | HIGH | HIGH | 9 | Open | Execution/OMDS | — | Component audit (ACT-008) | — | Not confirmed | — | — | — | — | — | — | —
RSK-009 | SEO & analytics ownership not finalised | GOVERNANCE | HIGH | HIGH | 9 | Open | SEO/Programme | — | SEO workshop (ACT-012) | — | Not confirmed | — | — | — | — | — | — | —
RSK-010 | Environment sequencing not defined | TECHNICAL | MEDIUM | HIGH | 6 | Open | Execution | — | Environment strategy (ACT-009) | — | Not confirmed | — | — | — | — | — | — | —
RSK-011 | Observability/analytics tagging added too late | TECHNICAL | MEDIUM | MEDIUM | 4 | Open | Execution | — | Embed in delivery (ACT-011) | — | Not confirmed | — | — | — | — | — | — | —
RSK-012 | Component sprawl / design debt | TECHNICAL | MEDIUM | MEDIUM | 4 | Open | OMDS | — | Lifecycle register (ACT-007) | — | Not confirmed | — | — | — | — | — | — | —
RSK-013 | Go-live readiness activities open | GOVERNANCE | HIGH | HIGH | 9 | Open | Programme | — | Readiness checklist (ACT-013) | — | Not confirmed | — | — | — | — | — | — | —
RSK-014 | Secure web migration at risk | DELIVERY | HIGH | HIGH | 9 | Open | Programme/Regional | — | Mitigation plan (ACT-015) | — | Not confirmed | — | — | — | — | — | — | —
RSK-015 | Servicing transactions at risk (BW 1/9) | DELIVERY | HIGH | HIGH | 9 | Open | Regional | — | Botswana recovery (ACT-016) | — | Not confirmed | — | — | — | — | — | — | —
RSK-016 | Unstandardised images/assets | PROCESS | MEDIUM | MEDIUM | 4 | Open | Content/OMDS | — | Asset standards (ACT-019) | — | Not confirmed | — | — | — | — | — | — | —
RSK-017 | Front-end resource exit after PI2 | RESOURCE | HIGH | HIGH | 9 | Open | CC/Web Platform | — | Transition plan (ACT-021) | — | End PI2 | — | — | — | — | — | — | —
RSK-018 | BA capacity constrained | RESOURCE | HIGH | MEDIUM | 6 | Open | Cross Channels | — | Interim BA (ACT-022) | — | Not confirmed | — | — | — | — | — | — | —
RSK-019 | Full scope ~2027 vs end-Nov window | TIMELINE | HIGH | HIGH | 9 | Open | Programme (GB) | — | Scope options (ACT-028) | — | Day 2 | — | — | — | — | — | — | —
RSK-020 | No centralised knowledge system | PEOPLE | HIGH | MEDIUM | 6 | Open | Programme (GB) | — | Documentation system (ACT-054) | — | Not confirmed | — | — | — | — | — | — | —
RSK-021 | ~95% URLs changing impacts e-commerce/GA | BUSINESS | HIGH | HIGH | 9 | Open | Execution/E-commerce | — | URL audit + notify Nthabi (ACT-046) | — | Pre go-live | — | — | — | — | — | — | —
RSK-022 | Security pen-test + ServiceNow not confirmed | SECURITY | MEDIUM | HIGH | 6 | Open | Programme/Security | — | Confirm testing (ACT-013) | — | Pre go-live | — | — | — | — | — | — | —
RSK-023 | Key-resource roll-offs — migration/feature team ~Sept 10; most knowledgeable QE August | RESOURCE | HIGH | HIGH | 9 | Open | Programme/CC (Tebogo) | — | Accelerate delivery; knowledge transfer; backfill (ACT-064) | — | Sept 10 / Aug | — | — | — | — | — | — | —
RSK-024 | Linear (current-capacity) delivery will not meet year-end; full scope extends well beyond | TIMELINE | HIGH | HIGH | 9 | Open | Programme (GB) | — | Four-squad parallel model + resource decision (DEC-016, ACT-064) | — | Year-end | — | — | — | — | — | — | —
RSK-025 | Post-sign-off red-zone template changes cascade across content + code on all affected pages | TECHNICAL | MEDIUM | HIGH | 6 | Open | Design/Execution | — | Red/green zones + change control (DEC-017/018) | — | Not confirmed | — | — | — | — | — | — | —
RSK-026 | Single points of failure — only Gareth & Natalie build templates; Bernice overloaded | RESOURCE | HIGH | HIGH | 9 | Open | Programme/Publishing | — | Additional capacity + training + onboarding (ACT-064/067) | — | Not confirmed | — | — | — | — | — | — | —
RSK-027 | Governance/template drift without controls (Contentstack ↔ Figma; new tenants) | GOVERNANCE | MEDIUM | MEDIUM | 4 | Open | Design/OMDS | — | Gatekeeper gate + Figma source-of-truth + onboarding (DEC-019, ACT-075) | — | Not confirmed | — | — | — | — | — | — | —
RSK-028 | Stakeholder sign-off delays extend template sign-off (esp. sequential Personal outreach) | BUSINESS | MEDIUM | HIGH | 6 | Open | Programme/Business | — | Structured engagement; group sign-off by page type (ACT-065, QST-025) | — | Not confirmed | — | — | — | — | — | — | —
RSK-029 | EasiPlus & dependent journeys blocked until Funeral/product pages complete | DELIVERY | MEDIUM | HIGH | 6 | Open | Cross Channels (Tebogo/Wayne) | — | Sequence product pages; escalate (DEP-018, ACT-074) | — | Not confirmed | — | — | — | — | — | — | —
RSK-030 | Secure-web portfolio-view requirements unclear before Sept roll-off → planning blocked | DELIVERY | HIGH | HIGH | 9 | Open | Secure Web/Migration (Tebogo) | — | Clarify portfolio-view scope (QST-024, DEP-020) | — | End Sept | — | — | — | — | — | — | —
RSK-031 | Not all year-end goals will be delivered → sponsor expectation-management required | BUSINESS | MEDIUM | MEDIUM | 4 | Open | Programme (GB) | — | Evidence-based scope communication; phased value (DEC-015) | — | Year-end | — | — | — | — | — | — | —
RSK-032 | Country teams without dedicated content/design resources (OMAR) cannot self-migrate | RESOURCE | HIGH | HIGH | 9 | Open | Programme/Regional | — | SA-first rollout + central support + squad extension (DEC-025) | — | Not confirmed | — | — | — | — | — | — | —

## Issues
Ref | Issue | Status | Current impact | Affected teams | Owner | Resolution required | Target resolution | Blocked workstream | Project | Task | Age (days) | Workshop day | Session | Trace ref
ISS-001 | Full Brand/CI not approved (interim only) | OPEN | Templates cannot scale confidently | Design, OMDS, Brand | Brand/Group Marketing | CI approval route | Not confirmed | — | — | — | 3 | — | — | —
ISS-002 | No reliable total page count; manual sheet tracking | OPEN | Capacity modelling unreliable | Publishing, Programme | Publishing | Inventory + tracker (ACT-005) | Not confirmed | — | — | — | 3 | — | — | —
ISS-003 | Secure web incomplete; no service-tree solution | OPEN | Secure journeys cannot fully go live | CC, Execution, Service | Programme | Mitigation (ACT-015) | Not confirmed | — | — | — | 3 | — | — | —
ISS-004 | Botswana servicing: 1 of 9 complete | OPEN | Regional go-live at risk | Regional (BW) | Regional | Recovery plan (ACT-016) | Not confirmed | — | — | — | 3 | — | — | —
ISS-005 | Go-live readiness activities open | OPEN | Cannot declare go-live readiness | Programme, Ops | Programme | Checklist (ACT-013) | Not confirmed | — | — | — | 3 | — | — | —
ISS-006 | BA on medical leave; recruitment ongoing | OPEN | CC requirements slowed | Cross Channels | Cross Channels | Interim BA (ACT-022) | Not confirmed | — | — | — | 3 | — | — | —
ISS-007 | Single person covers all publishing | OPEN | Throughput bottleneck now | Publishing | Publishing/Programme | Dedicated capacity (ACT-003) | Not confirmed | — | — | — | 3 | — | — | —
ISS-008 | No centralised knowledge system today | OPEN | Delays, repeated work | All | Programme (GB) | Knowledge system (ACT-054) | Not confirmed | — | — | — | 3 | — | — | —
ISS-009 | Current under-resourcing across all workstreams; teams beyond capacity | OPEN | Year-end delivery at risk; quality/morale pressure | All | Programme Leadership | Resource allocation decision (ACT-064) | Not confirmed | — | — | — | 3 | — | — | —
ISS-010 | Unclear business ownership for several journeys (compliments, complaints, unclaimed benefits, IR, corporate unclaimed benefits) | OPEN | Migration planning blocked for those journeys | Business teams | Programme (GB/Tebogo) | Identify owners + scope (ACT-073) | Not confirmed | — | — | — | 3 | — | — | —
ISS-011 | Portfolio-view dependencies/requirements unclear for Secure Web; aggravated by Sept roll-off | OPEN | Secure-web migration planning stalled | Secure Web/Migration | Technical teams (Tebogo) | Requirements clarification (QST-024, DEP-020) | Not confirmed | — | — | — | 3 | — | — | —

## Dependencies
Ref | Dependency | Status | Stream | Dependent workstream | Providing team | Receiving team | Required date | Delay risk | Escalation | Owner | Workstream | Project | Task | Deliverable | Workshop day | Session | Trace ref
DEP-001 | Contentstack dev + content/assets/URLs signed off before publishing | OPEN | Publishing | — | — | — | Not confirmed | Publishing & testing slip | Programme / Steering | Programme | — | — | — | — | — | — | —
DEP-002 | Testing cannot begin until all pages built in Beta | OPEN | Publishing | — | — | — | Not confirmed | Go-live slip | Programme | Programme | — | — | — | — | — | — | —
DEP-003 | DS V2 deployed to Beta (Find an Advisor + templates) | OPEN | Cross Channel | — | — | — | Not confirmed | Beta readiness blocked | Programme | Brent Van Ziller | — | — | — | — | — | — | —
DEP-004 | Figma/DS component audit before template scaling | OPEN | Design | — | — | — | Not confirmed | Build blocked / rework | Programme | Execution/Design | — | — | — | — | — | — | —
DEP-005 | URL audit before switch-off/redirect decisions | OPEN | Publishing | — | — | — | Not confirmed | Broken journeys, SEO loss | Programme | Natalie Patel | — | — | — | — | — | — | —
DEP-006 | Content packs + cluster/SME content before sign-off | OPEN | Publishing | — | — | — | Not confirmed | Publishing blocked | Programme | Natalie Patel | — | — | — | — | — | — | —
DEP-007 | Cross Channels depends on Web Platform for FE from PI2 | OPEN | Cross Channel | — | — | — | End PI2 | FE velocity drops | Programme | Wayne Moodley | — | — | — | — | — | — | —
DEP-008 | EasiPlus depends on Funeral template + MFC sign-off | OPEN | Cross Channel | — | — | — | Not confirmed | EasiPlus blocked | Programme | Wayne Moodley | — | — | — | — | — | — | —
DEP-009 | SEO ≥2 months lead before QA | OPEN | SEO | — | — | — | ≥2 months pre-QA | Go-live blocked by SEO | Programme | SEO | — | — | — | — | — | — | —
DEP-010 | Tax-free & flexi-invest pages link to migrated V2 journeys | OPEN | Cross Channel | — | — | — | Not confirmed | Journey continuity gaps | Programme | Cross Channels | — | — | — | — | — | — | —
DEP-011 | Service tree/dashboard solution for secure web | OPEN | Secure Web | — | — | — | Not confirmed | Secure web blocked | Programme | Service team | — | — | — | — | — | — | —
DEP-012 | Paid Ads URL requirements from Group Marketing | OPEN | SEO | — | — | — | Not confirmed | URL/analytics rework | Programme | Group Marketing | — | — | — | — | — | — | —
DEP-013 | Notify Nthabi of URL changes for GA tracking | OPEN | E-commerce | — | — | — | Pre go-live | Broken exec reporting | Programme | Wayne Moodley | — | — | — | — | — | — | —
DEP-014 | Final advisor flow into beta (Luvuyo) | OPEN | Cross Channel | — | — | — | Not confirmed | Find an Advisor slip | Programme | Wayne Moodley | — | — | — | — | — | — | —
DEP-015 | Security pen-test/crowdsource before go-live | OPEN | Go-Live | — | — | — | Pre go-live | Go-live blocked | Steering | Security team | — | — | — | — | — | — | —
DEP-016 | ServiceNow API updates + approvals before prod | OPEN | Go-Live | — | — | — | Pre go-live | Prod deployment blocked | Steering | Programme | — | — | — | — | — | — | —
DEP-017 | Personal IA + core templates + content guidelines complete before dev/build | OPEN | Design | — | — | — | End June | Build cannot proceed | Programme | Design (Seba/Justin) | — | — | — | — | — | — | —
DEP-018 | Product pages complete before EasiPlus & dependent sales journeys deploy | OPEN | Cross Channel | — | — | — | Not confirmed | EasiPlus blocked (reaffirms DEP-008) | Programme | Web (Gareth) | — | — | — | — | — | — | —
DEP-019 | IA sign-off per audience before each downstream stream proceeds (sequential) | OPEN | Design | — | — | — | Sequential per audience | Downstream streams blocked | Programme | Design / Business | — | — | — | — | — | — | —
DEP-020 | Secure-web portfolio-view technical requirements before Sept roll-off | OPEN | Secure Web | — | — | — | End Sept | Roll-off impact; planning blocked | Programme | Secure Web | — | — | — | — | — | — | —
DEP-021 | Template handover cadence (~every 2 weeks) feeds content creation & parallel builds | OPEN | Content | — | — | — | Ongoing | Content creation blocked | Programme | Design | — | — | — | — | — | — | —
DEP-022 | Desktop Figma output (source of truth) for automation & Contentstack mapping | OPEN | Execution | — | — | — | Not confirmed | Automation blocked | Programme | Design | — | — | — | — | — | — | —

## Constraints
Role / area | Named resource | Capacity concern | Confirmed vs suggested
Publishers | 2 publishers (1 migration + 1 BAU) | Only two publishers and no dedicated OMAR publisher; every change touches the full page inventory. | Confirmed
New-template build | — | ~2 hours per page for net-new template builds. | Estimate
As-is build | — | ~30 minutes per page — depends on the 'as-is' definition being agreed. | Estimate
BAU throughput | — | ~85 tickets cleared per 5-day cycle (reference throughput). | Reference
SEO lead time | SEO lead | ≥ 2 months of lead time required before QA / go-live windows. | Confirmed
Front-end engineering | Cross Channels squad | Most front-end developers roll off to Web Platform after PI2 (RSK-017) — finite build window. | Confirmed