## README_NOT_FOR_UPLOAD
Section | Detail
Purpose | Cleaned programme roadmap dataset extracted from all workstream input tabs in Workstream_Owner_Roadmap_InputSheet.xlsx.
Upload rule | Only sheets prefixed UPLOAD_ are intended for programme data upload. Sheets prefixed REFERENCE_ and Dashboard are control/reference material.
Authoritative source | The individual workstream tabs were used as the row-level source of truth because Cons_List contained fewer meaningful records than the workstream tabs.
Processed workstream tabs | Design Standards, Design Delivery, Content Readiness, Feature Delivery, Design Systems, Execution, Publishing, Go-Live Readiness, SEO Analytics, OMAR
Excluded non-upload tabs | Sheet1 and Piv contain cover/pivot information only. Cons_List was used for reconciliation only.
Date handling | Excel date serials were converted to YYYY-MM-DD. Effort cells displayed as 1900 dates were converted back to numeric day counts.
Taxonomy handling | Country values in the OMAR tab were normalised to Domain=OMAR and retained in Market/Area/Cluster fields.
Blank handling | Blank, zero, and obvious N/A source values were converted to TBC, All/TBC, or shared classifications where appropriate.
Quality handling | Invalid source formula values were not loaded as formulas; they are flagged in REFERENCE_Validation.
Traceability | Every upload row includes Source_Sheet and Source_Row for audit back to the original workbook.

## Dashboard
Programme Roadmap Clean Dataset
Only UPLOAD_ sheets are intended for upload. REFERENCE_ sheets are control material, not programme seed data.
Metric | Value | Workstream Summary
Programme records | 187 | Workstream | Programme_Records | Risk_Records | Constraint_Records | Dependency_Records | Needs_Validation
Risk records | 343 | Design Delivery | 35 | 72 | 71 | 68 | 35
Constraint records | 478 | Publishing | 27 | 27 | 67 | 24 | 24
Dependency records | 199 | Execution | 25 | 71 | 71 | 21 | 25
Records with dependencies | 148 | OMAR | 24 | 104 | 124 | 23 | 24
Records with risks | 149 | Feature Delivery | 22 | 26 | 37 | 5 | 12
Records with constraints | 163 | Design Standards | 20 | 9 | 11 | 25 | 4
Records requiring validation | 154 | Design Systems | 20 | 25 | 71 | 20 | 20
Workstream tabs processed | 10 | Go-Live Readiness | 8 | 5 | 22 | 8 | 8
Meaningful Cons_List records | 151 | Content Readiness | 4 | 0 | 0 | 4 | 0
|  | SEO / Analytics | 2 | 4 | 4 | 1 | 2
Priority Summary |  | Status Summary |  |  | Risk Severity Summary
Category | Count | Category | Count |  | Category | Count
High | 95 | Not Started | 91 |  | High | 202
Critical | 62 | In Progress | 75 |  | Critical | 124
Medium | 20 | TBC | 12 |  | Medium | 17
Low | 9 | Blocked | 4
TBC | 1 | Ready | 2
|  | N/A | 2
|  | Complete | 1
Constraint Type Summary |  | Dependency Type Summary |  |  | Channel Summary
Category | Count | Category | Count |  | Category | Count
Data Quality / Taxonomy Constraint | 150 | Upstream Delivery Dependency | 125 |  | Public Web | 161
Accountability Constraint | 94 | Approval Dependency | 41 |  | Secure Web | 22
Confidence / Planning Constraint | 79 | Collaboration / Input Dependency | 18 |  | TBC | 4
Schedule Constraint | 66 | Unspecified Upstream Dependency | 15
Effort / Capacity Constraint | 52
Sequencing Constraint | 22
Resource Constraint | 11
Technical Access / Data Constraint | 3
Tooling Constraint | 1

## UPLOAD_Master_Data
Programme_Record_ID | Workstream | Owner | Channel | Domain | Area_Journey | Cluster | Market | Clean_Task | Clean_Description | Start_Date | End_Date | Effort_Days | Effort_Days_Text | Confidence_Percent | Confidence_Band | Priority | Status | Upstream_Dependency | Upstream_Deliverable | Has_Risk | Has_Constraint | Has_Dependency | Comments | Scope_Items | Source_Sheet | Source_Row | Source_Channel | Source_Domain | Source_Area_Journey | Source_Cluster | Original_Task
PRG-0001 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Navigation |  | Design navigation structure based on the IA | Design navigation structure based on the IA for Public Web / OMCOZA / Entire Site / Navigation. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: Though we have an agreed structure, there is a dependency on brand alignment. Even though there is structure, we may not have stressed tested everything. Current status: In Progress. Source comment/context: This is about 90% complete, there is some changes based on testing and brand alignment (based on the approved interim brand). The DS team has paused this until we provide the amended nav structure. | 2026-06-04 | 2026-06-17 | 10 | 10 | 100 | High confidence | Critical | In Progress | Yes | Though we have an agreed structure, there is a dependency on brand alignment. Even though there is structure, we may not have stressed tested everything. | Yes | No | Yes | This is about 90% complete, there is some changes based on testing and brand alignment (based on the approved interim brand). The DS team has paused this until we provide the amended nav structure. |  | Design Standards | 4 | Public Web | OMCOZA | Entire site | Navigation | Design navigation structure based on the IA
PRG-0002 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Navigation |  | Complete footer navigation structure based on the IA | Complete footer navigation structure based on the IA for Public Web / OMCOZA / Entire Site / Navigation. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: Structure is agreed, we just need to finalise it with the actual AI and Nav items to display. We also need to remove the ribbon logo and update it as per the interim brand. Current status: In Progress. Source comment/context: This is about 70% complete, just need to align to approved interim Brand CI. | 2026-06-04 | 2026-06-17 | 10 | 10 | 100 | High confidence | Critical | In Progress | Yes | Structure is agreed, we just need to finalise it with the actual AI and Nav items to display. We also need to remove the ribbon logo and update it as per the interim brand. | No | No | Yes | This is about 70% complete, just need to align to approved interim Brand CI |  | Design Standards | 5 | Public Web | OMCOZA | Entire site | Navigation | Complete footer navigation structure based on the IA
PRG-0003 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Landing Page Template | Design Landing Page Template for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-18; end 2026-07-01; effort 10 days. Upstream dependency: This requires input and alignment from who will be providing feedback and approval of templates like this. Current status: In Progress. Source comment/context: This work has started. | 2026-06-18 | 2026-07-01 | 10 | 10 | 60 | Moderate confidence | Critical | In Progress | Yes | This requires input and alignment from who will be providing feedback and approval of templates like this. | Yes | No | Yes | This work has started |  | Design Standards | 6 | Public Web | OMCOZA | Entire site | Templates | Design Landing Page Template
PRG-0004 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Section Page Template | Design Section Page Template for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-18; end 2026-07-01; effort 10 days. Upstream dependency: This requires input and alignment from who will be providing feedback and approval of templates like this. Current status: In Progress. Source comment/context: This work has started. | 2026-06-18 | 2026-07-01 | 10 | 10 | 60 | Moderate confidence | High | In Progress | Yes | This requires input and alignment from who will be providing feedback and approval of templates like this. | Yes | No | Yes | This work has started |  | Design Standards | 7 | Public Web | OMCOZA | Entire site | Templates | Design Section Page Template
PRG-0005 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Finalise Category Page Template | Finalise Category Page Template for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: This needs to be further stress tested, but Retirement and Funeral is in a place where we are communicating this to DS. Current status: In Progress. Source comment/context: This is about 90% with the 2 categories designed. | 2026-06-04 | 2026-06-17 | 10 | 10 | 80 | High confidence | High | In Progress | Yes | This needs to be further stress tested, but Retirement and Funeral is in a place where we are communicating this to DS. | No | No | Yes | This is about 90% with the 2 categories designed. |  | Design Standards | 8 | Public Web | OMCOZA | Entire site | Templates | Finalise Category Page Template
PRG-0006 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Finalise Product Page Template | Finalise Product Page Template for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: This needs to be further stress tested, but Max Investments, Funeral Plan and FlexiSave is in a place where we are communicating this to DS. Current status: In Progress. Source comment/context: This is about 90% done with 3 product pages completed. | 2026-06-04 | 2026-06-17 | 10 | 10 | 80 | High confidence | High | In Progress | Yes | This needs to be further stress tested, but Max Investments, Funeral Plan and FlexiSave is in a place where we are communicating this to DS. | No | No | Yes | This is about 90% done with 3 product pages completed. |  | Design Standards | 9 | Public Web | OMCOZA | Entire site | Templates | Finalise Product Page Template
PRG-0007 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Template: Contact Us | Design Utility Template: Contact Us for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Current status: In Progress. Source comment/context: The work has started for both desktop and mobile. | 2026-06-04 | 2026-06-17 | 10 | 10 | 80 | High confidence | High | In Progress | No | We are simply consolidating the contact details into one page. | No | No | No | The work has started for both desktop and mobile. |  | Design Standards | 10 | Public Web | OMCOZA | Entire site | Templates | Design Utility Template: Contact Us
PRG-0008 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: All Calculators | Design Utility Template: All Calculators for Public Web / OMCOZA / Personal / Templates. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: There is a lot of calculators that require a lot of input across different product and business clusters. Current status: In Progress. Source comment/context: The work has started for both desktop and mobile. | 2026-06-04 | 2026-06-17 | 10 | 10 | 40 | Low confidence | High | In Progress | Yes | There is a lot of calculators that require a lot of input across different product and business clusters. | Yes | Yes | Yes | The work has started for both desktop and mobile. |  | Design Standards | 11 | Public Web | OMCOZA | Personal | Templates | Design Utility Template: All Calculators
PRG-0009 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: Calculators Page | Design Utility Template: Calculators Page for Public Web / OMCOZA / Personal / Templates. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech. Current status: In Progress. Source comment/context: This work has started. | 2026-06-04 | 2026-06-17 | 10 | 10 | 40 | Low confidence | High | In Progress | Yes | There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech. | Yes | Yes | Yes | This work has started. |  | Design Standards | 12 | Public Web | OMCOZA | Personal | Templates | Design Utility Template: Calculators Page
PRG-0010 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Tenant |  | Design Tenant Template | Design Tenant Template for Public Web / OMCOZA / Entire Site / Tenant. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards. Current status: In Progress. | 2026-06-04 | 2026-06-17 | 10 | 10 | 70 | Moderate confidence | High | In Progress | Yes | This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards. | No | Yes | Yes |  |  | Design Standards | 13 | Public Web | OMCOZA | Entire site | Tenant | Design Tenant Template
PRG-0011 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Templates: About Us | Design Utility Templates: About Us for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-18; end 2026-07-01; effort 10 days. Current status: Not Started. | 2026-06-18 | 2026-07-01 | 10 | 10 | 60 | Moderate confidence | Medium | Not Started | No | We are using existing content, we just need to consider how to consolidate the content. | No | No | No |  |  | Design Standards | 14 | Public Web | OMCOZA | Entire site | Templates | Design Utility Templates: About Us
PRG-0012 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Template: Careers | Design Utility Template: Careers for Public Web / OMCOZA / Entire Site / Templates. Planned delivery details: start 2026-06-18; end 2026-07-01; effort 10 days. Upstream dependency: This may require input from HC but if we are migrating the content as-is, then this could be a simple process. Current status: Not Started. | 2026-06-18 | 2026-07-01 | 10 | 10 | 40 | Low confidence | Medium | Not Started | Yes | This may require input from HC but if we are migrating the content as-is, then this could be a simple process. | No | Yes | Yes |  |  | Design Standards | 15 | Public Web | OMCOZA | Entire site | Templates | Design Utility Template: Careers
PRG-0013 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation structure based on the IA | Design navigation structure based on the IA for Secure Web / MyOM / Entire Site / Navigation. Planned delivery details: start 2026-07-02; end 2026-07-15; effort 10 days. Upstream dependency: Initial designs have been done, it requires further discussion of how the pieces need to fit. Current status: In Progress. Source comment/context: Initial designs has started. | 2026-07-02 | 2026-07-15 | 10 | 10 | 40 | Low confidence | High | In Progress | Yes | Initial designs have been done, it requires further discussion of how the pieces need to fit. | Yes | Yes | Yes | Initial designs has started. |  | Design Standards | 16 | Secure Web | MyOM | Entire site | Navigation | Design navigation structure based on the IA
PRG-0014 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation solution to allow access to other secure sites | Design navigation solution to allow access to other secure sites for Secure Web / MyOM / Entire Site / Navigation. Planned delivery details: start 2026-07-02; end 2026-07-15; effort 10 days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. | 2026-07-02 | 2026-07-15 | 10 | 10 | 70 | Moderate confidence | High | In Progress | Yes |  | Yes | Yes | Yes |  |  | Design Standards | 17 | Secure Web | MyOM | Entire site | Navigation | Design navigation solution to allow access to other secure sites
PRG-0015 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise generic copy standards | Finalise generic copy standards for TBC / Old Mutual Design Standards / Generic / Copy. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: Alignment with Group Marketing. Current status: Ready. Source comment/context: We are ready for sign off, it is aligned to brand and are requesting us to send to them for their records. | 2026-06-04 | 2026-06-17 | 10 | 10 | 80 | High confidence | Critical | Ready | Yes | Alignment with Group Marketing | No | Yes | Yes | We are ready for sign off, it is aligned to brand and are requesting us to send to them for their records. |  | Design Standards | 18 |  | Old Mutual Design Standards | Generic | Copy | Finalise generic copy standards
PRG-0016 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise SEO + AIEO standards | Finalise SEO + AIEO standards for TBC / Old Mutual Design Standards / Generic / Copy. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: Alignment with Group Marketing. Current status: Ready. Source comment/context: SEO is also in progress with their own standards, so our standards will be a living process and document. | 2026-06-04 | 2026-06-17 | 10 | 10 | 80 | High confidence | Critical | Ready | Yes | Alignment with Group Marketing | No | Yes | Yes | SEO is also in progress with their own standards, so our standards will be a living process and document |  | Design Standards | 19 |  | Old Mutual Design Standards | Generic | Copy | Finalise SEO + AIEO standards
PRG-0017 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | CI |  | Align DS to iterim Brand CI | Align DS to iterim Brand CI for TBC / Old Mutual Design Standards / Generic / CI. Planned delivery details: start 2026-06-04; end 2026-07-01; effort 20 days. Upstream dependency: Alignment with Group Marketing. Current status: In Progress. Source comment/context: The Interim Brand CI has been approved, luckily no major changes and just need align DS to brand. | 2026-06-04 | 2026-07-01 | 20 | 20 | 70 | Moderate confidence | High | In Progress | Yes | Alignment with Group Marketing | No | Yes | Yes | The Interim Brand CI has been approved, luckily no major changes and just need align DS to brand. |  | Design Standards | 20 |  | Old Mutual Design Standards | Generic | CI | Align DS to iterim Brand CI
PRG-0018 | Design Standards | Justin | Public Web | OMCOZA | OM Bank | Tenant |  | Design OM Bank Tenant site (structure) | Design OM Bank Tenant site (structure) for Public Web / OMCOZA / OM Bank / Tenant. Planned delivery details: start 2026-06-17; end 2026-07-02; effort 10 days. Upstream dependency: Alignment with OM Bank but also OMF. Current status: Not Started. Source comment/context: We need to have initial conversations around OM Bank and if OMF falls under their domain which means they will need to design and build out their screens and IA. | 2026-06-17 | 2026-07-02 | 10 | 10 | 20 | Very low confidence | Low | Not Started | Yes | Alignment with OM Bank but also OMF | No | Yes | Yes | We need to have initial conversations around OM Bank and if OMF falls under their domain which means they will need to design and build out their screens and IA. |  | Design Standards | 21 | Public Web | OMCOZA | OM Bank | Tenant | Design OM Bank Tenant site (structure)
PRG-0019 | Design Standards | Justin | Public Web | OMCOZA | Rewards | Tenant |  | Design Rewards Tenant Site | Design Rewards Tenant Site for Public Web / OMCOZA / Rewards / Tenant. Planned delivery details: start 2026-06-18; end 2026-07-02; effort 10 days. Upstream dependency: Rewards is in progress with a redeisgn / revamp. So we will be using their existing structure and content. Current status: In Progress. Source comment/context: For the initial migration - we are keeping to their existing structure and content while they go through their redesign. | 2026-06-18 | 2026-07-02 | 10 | 10 | 80 | High confidence | Low | In Progress | Yes | Rewards is in progress with a redeisgn / revamp. So we will be using their existing structure and content. | No | No | Yes | For the initial migration - we are keeping to their existing structure and content while they go through their redesign. |  | Design Standards | 22 | Public Web | OMCOZA | Rewards | Tenant | Design Rewards Tenant Site
PRG-0020 | Design Standards | Justin | Public Web | OMCOZA | Insure / iWyze | Tenant |  | Design iWyze Tenant Product Page Template | Design iWyze Tenant Product Page Template for Public Web / OMCOZA / Insure / iWyze / Tenant. Planned delivery details: start 2026-06-04; end 2026-06-17; effort 10 days. Upstream dependency: Alignment with OMF as well as the actual tenant. Current status: Not Started. | 2026-06-04 | 2026-06-17 | 10 | 10 | 30 | Very low confidence | High | Not Started | Yes | Alignment with OMF as well as the actual tenant. | Yes | Yes | Yes |  |  | Design Standards | 23 | Public Web | OMCOZA | Insure / iWyze | Tenant | Design iWyze Tenant Product Page Template
PRG-0021 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Personal / Retirement. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-06-04; end 2026-06-08; effort 3 days. Upstream dependency: We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined. Current status: In Progress. Source comment/context: Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams. | 2026-06-04 | 2026-06-08 | 3 | 3 | 100 | High confidence | Critical | In Progress | Yes | We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined. | Yes | Yes | Yes | Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams. | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 4 | Public Web | OMCOZA | Personal | Retirement | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0022 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Personal / Funeral. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-06-10; end 2026-06-15; effort 4 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-10 | 2026-06-15 | 4 | 4 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 5 | Public Web | OMCOZA | Personal | Funeral | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0023 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy for Public Web / OMCOZA / Personal / Investment > Flexi Save. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Product landing page with enhanced copy. Planned delivery details: start 2026-06-16; end 2026-06-16; effort 1 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-16 | 2026-06-16 | 1 | 1 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Product landing page with enhanced copy | Design Delivery | 6 | Public Web | OMCOZA | Personal | Investment > Flexi Save | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Product landing page with enhanced copy
PRG-0024 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) for Public Web / OMCOZA / Personal / Entire Site. Planned delivery details: start 2026-06-19; end 2026-06-23; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-19 | 2026-06-23 | 3 | 3 | 80 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 7 | Public Web | OMCOZA | Personal | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0025 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) for Public Web / OMCOZA / Business / Entire Site. Planned delivery details: start 2026-06-19; end 2026-06-23; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-19 | 2026-06-23 | 3 | 3 | 80 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 8 | Public Web | OMCOZA | Business | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0026 | Design Delivery | Sebabatso | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) for Public Web / OMCOZA / Corporate / Entire Site. Planned delivery details: start 2026-06-24; end 2026-06-26; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-24 | 2026-06-26 | 3 | 3 | 80 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 9 | Public Web | OMCOZA | Corporate | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0027 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) for Public Web / OMCOZA / Wealth / Entire Site. Planned delivery details: start 2026-06-29; end 2026-07-03; effort 5 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-06-29 | 2026-07-03 | 5 | 5 | 80 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 10 | Public Web | OMCOZA | Wealth | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0028 | Design Delivery | Sebabatso | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding for Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. Scope items: Kick-of recruitment process for additional capacity ¦ Vendor briefing ¦ CV review ¦ Interviews ¦ Candidate selection ¦ Onboarding. Planned delivery details: start 2026-06-08; end 2026-06-30; effort 17 days. Current status: Not Started. | 2026-06-08 | 2026-06-30 | 17 | 17 | 100 | High confidence | Critical | Not Started | No |  | Yes | Yes | No |  | Kick-of recruitment process for additional capacity ¦ Vendor briefing ¦ CV review ¦ Interviews ¦ Candidate selection ¦ Onboarding | Design Delivery | 11 | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE | Kick-of recruitment process for additional capacity Vendor briefing CV review Interviews Candidate selection Onboarding
PRG-0029 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Audience landing with enhanced copy for Public Web / OMCOZA / Personal / Personal Landing. Planned delivery details: start 2026-07-06; end 2026-07-08; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-08 | 3 | 3 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 12 | Public Web | OMCOZA | Personal | Personal Landing | Audience landing with enhanced copy
PRG-0030 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Personal / Invest. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-06; end 2026-07-15; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-15 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 13 | Public Web | OMCOZA | Personal | Invest | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0031 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Personal / OM Bank. Scope items: L3+ IA finalisation ¦ Section landing with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-16; end 2026-07-20; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-16 | 2026-07-20 | 3 | 3 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ Section landing with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 14 | Public Web | OMCOZA | Personal | OM BAnk | L3+ IA finalisation Section landing with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0032 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Personal / Insure. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-21; end 2026-08-03; effort 10 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-21 | 2026-08-03 | 10 | 10 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 15 | Public Web | OMCOZA | Personal | Insure | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0033 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy for Public Web / OMCOZA / Personal / About us. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy. Planned delivery details: start 2026-08-04; end 2026-08-07; effort 4 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-04 | 2026-08-07 | 4 | 4 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy | Design Delivery | 16 | Public Web | OMCOZA | Personal | About us | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (3+) with enhanced copy Product landing pages (3+) with enhanced copy
PRG-0034 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy for Public Web / OMCOZA / Personal / Careers. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy. Planned delivery details: start 2026-08-10; end 2026-08-13; effort 4 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-10 | 2026-08-13 | 4 | 4 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy | Design Delivery | 17 | Public Web | OMCOZA | Personal | Careers | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (3+) with enhanced copy Product landing pages (3+) with enhanced copy
PRG-0035 | Design Delivery | Sebabatso | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Mapping of new IA and Footer to sxisting site structure for Public Web / OMCOM / Entire Site / Entire Site. Planned delivery details: start 2026-08-14; end 2026-08-17; effort 2 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-14 | 2026-08-17 | 2 | 2 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 18 | Public Web | OMCOM | Entire site | Entire site | Mapping of new IA and Footer to sxisting site structure
PRG-0036 | Design Delivery | Sebabatso | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Mapping of new IA and Footer to sxisting site structure for Public Web / Bula Tsela / Entire Site / Entire Site. Planned delivery details: start 2026-08-18; end 2026-08-19; effort 2 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-18 | 2026-08-19 | 2 | 2 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 19 | Public Web | Bula Tsela | Entire site | Entire site | Mapping of new IA and Footer to sxisting site structure
PRG-0037 | Design Delivery | Sebabatso | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Mapping of new IA and Footer to sxisting site structure for Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. Planned delivery details: start 2026-08-20; end 2026-08-21; effort 2 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-20 | 2026-08-21 | 2 | 2 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 20 | Public Web | Learn Think Do (LTD) | Entire site | Entire site | Mapping of new IA and Footer to sxisting site structure
PRG-0038 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Audience landing with enhanced copy for Public Web / OMCOZA / Wealth / Wealth Landing. Planned delivery details: start 2026-07-06; end 2026-07-10; effort 5 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-10 | 5 | 5 | 70 | Moderate confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 21 | Public Web | OMCOZA | Wealth | Wealth Landing | Audience landing with enhanced copy
PRG-0039 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Wealth / Invest. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-13; end 2026-07-31; effort 15 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-13 | 2026-07-31 | 15 | 15 | 70 | Moderate confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 22 | Public Web | OMCOZA | Wealth | Invest | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0040 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Wealth / Plan. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-08-03; end 2026-08-21; effort 15 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-03 | 2026-08-21 | 15 | 15 | 70 | Moderate confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 23 | Public Web | OMCOZA | Wealth | Plan | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0041 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy for Public Web / OMCOZA / Wealth / About. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy. Planned delivery details: start 2026-08-24; end 2026-08-28; effort 5 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-24 | 2026-08-28 | 5 | 5 | 70 | Moderate confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy | Design Delivery | 24 | Public Web | OMCOZA | Wealth | About | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (3+) with enhanced copy Product landing pages (3+) with enhanced copy
PRG-0042 | Design Delivery | Sebabatso | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy for Public Web / OMCOZA / Wealth / Insights. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy. Planned delivery details: start 2026-08-31; end 2026-09-04; effort 5 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-31 | 2026-09-04 | 5 | 5 | 70 | Moderate confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (3+) with enhanced copy ¦ Product landing pages (3+) with enhanced copy | Design Delivery | 25 | Public Web | OMCOZA | Wealth | Insights | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (3+) with enhanced copy Product landing pages (3+) with enhanced copy
PRG-0043 | Design Delivery | Sebabatso | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Audience landing with enhanced copy for Public Web / OMCOZA / Corporate / Corporate Landing. Planned delivery details: start 2026-07-06; end 2026-07-09; effort 4 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-09 | 4 | 4 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 26 | Public Web | OMCOZA | Corporate | Corporate Landing | Audience landing with enhanced copy
PRG-0044 | Design Delivery | Sebabatso | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Corporate / Employees. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-06; end 2026-07-15; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-15 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 27 | Public Web | OMCOZA | Corporate | Employees | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0045 | Design Delivery | Sebabatso | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Corporate / Employers. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-16; end 2026-07-27; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-16 | 2026-07-27 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 28 | Public Web | OMCOZA | Corporate | Employers | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0046 | Design Delivery | Sebabatso | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Corporate / Services. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-28; end 2026-08-06; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-28 | 2026-08-06 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 29 | Public Web | OMCOZA | Corporate | Services | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0047 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Audience landing with enhanced copy for Public Web / OMCOZA / Business / Business Landing. Planned delivery details: start 2026-07-06; end 2026-07-09; effort 4 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-09 | 4 | 4 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 30 | Public Web | OMCOZA | Business | Business Landing | Audience landing with enhanced copy
PRG-0048 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Business / Insure. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-06; end 2026-07-15; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-06 | 2026-07-15 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 31 | Public Web | OMCOZA | Business | Insure | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0049 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Business / Invest. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-16; end 2026-07-27; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-16 | 2026-07-27 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 32 | Public Web | OMCOZA | Business | Invest | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0050 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Business / Protect. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-07-28; end 2026-08-06; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-07-28 | 2026-08-06 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 33 | Public Web | OMCOZA | Business | Protect | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0051 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Business / Guarantee. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-08-07; end 2026-08-18; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-07 | 2026-08-18 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 34 | Public Web | OMCOZA | Business | Guarantee | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0052 | Design Delivery | Sebabatso | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy for Public Web / OMCOZA / Business / Tools. Scope items: L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy. Planned delivery details: start 2026-08-19; end 2026-08-28; effort 8 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-19 | 2026-08-28 | 8 | 8 | 100 | High confidence | Critical | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | L3+ IA finalisation ¦ URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. ¦ Section landing with enhanced copy ¦ Category landing pages (5+) with enhanced copy ¦ Product landing pages (5+) with enhanced copy | Design Delivery | 35 | Public Web | OMCOZA | Business | Tools | L3+ IA finalisation URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture. Section landing with enhanced copy Category landing pages (5+) with enhanced copy Product landing pages (5+) with enhanced copy
PRG-0053 | Design Delivery | Sebabatso | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. for Public Web / OMCOZA / Personal / My OldMutual. Scope items: Public > Secure ¦ Secure > Public Transition. ¦ Access to other secure sites. ¦ Service tree definition (E.g. Product > Payment or Payment Hub > Product selection). ¦ IA + Navigation flow (Primary noun architecture). ¦ Potential Template impact (E.g. Dashboard). ¦ Customer validation. Planned delivery details: start 2026-07-06; end 2026-09-11; effort 50 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | 2026-07-06 | 2026-09-11 | 50 | 50 | 70 | Moderate confidence | Critical | TBC | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  | Public > Secure ¦ Secure > Public Transition. ¦ Access to other secure sites. ¦ Service tree definition (E.g. Product > Payment or Payment Hub > Product selection). ¦ IA + Navigation flow (Primary noun architecture). ¦ Potential Template impact (E.g. Dashboard). ¦ Customer validation. | Design Delivery | 36 | Public Web | OMCOZA | Personal | My OldMutual | Public > Secure ¦ Secure > Public Transition. Access to other secure sites. Service tree definition (E.g. Product > Payment or Payment Hub > Product selection). IA + Navigation flow (Primary noun architecture). Potential Template impact (E.g. Dashboard). Customer validation.
PRG-0054 | Design Delivery | Sebabatso | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Socilaisation of defined IA and Page templates for handover. for Public Web / OMAR: Kenya / Entire Site / Entire Site. Planned delivery details: start 2026-08-20; end 2026-08-24; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-20 | 2026-08-24 | 3 | 3 | 100 | High confidence | High | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 37 | Public Web | OMAR: Kenya | Entire Site | Entire Site | Socilaisation of defined IA and Page templates for handover.
PRG-0055 | Design Delivery | Sebabatso | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Socilaisation of defined IA and Page templates for handover. for Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. Planned delivery details: start 2026-08-20; end 2026-08-24; effort 3 days. Upstream dependency: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. Current status: In Progress. | 2026-08-20 | 2026-08-24 | 3 | 3 | 100 | High confidence | High | In Progress | Yes | We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Yes | Yes | Yes |  |  | Design Delivery | 38 | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site | Socilaisation of defined IA and Page templates for handover.
PRG-0056 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Retirement |  | Copy enhancement + link mapping dependent on design activities | Copy enhancement + link mapping dependent on design activities for Public Web / OMCOZA / Personal / Retirement. Planned delivery details: start 2026-06-04; end 2026-06-08; effort 3 days. Upstream dependency: Design readiness. Current status: In Progress. | 2026-06-04 | 2026-06-08 | 3 | 3 | 80 | High confidence | Critical | In Progress | Yes | Design readiness | No | No | Yes |  |  | Content Readiness | 4 | Public Web | OMCOZA | Personal | Retirement | Copy enhancement + link mapping dependent on design activities
PRG-0057 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Funeral |  | Copy enhancement + link mapping dependent on design activities | Copy enhancement + link mapping dependent on design activities for Public Web / OMCOZA / Personal / Funeral. Planned delivery details: start 2026-06-10; end 2026-06-15; effort 4 days. Upstream dependency: Design readiness. Current status: In Progress. | 2026-06-10 | 2026-06-15 | 4 | 4 | 80 | High confidence | Critical | In Progress | Yes | Design readiness | No | No | Yes |  |  | Content Readiness | 5 | Public Web | OMCOZA | Personal | Funeral | Copy enhancement + link mapping dependent on design activities
PRG-0058 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Invest Flexi Save |  | Copy enhancement + link mapping dependent on design activities | Copy enhancement + link mapping dependent on design activities for Public Web / OMCOZA / Personal / Invest Flexi Save. Planned delivery details: start 2026-06-16; end 2026-06-17; effort 2 days. Upstream dependency: Design readiness. Current status: In Progress. | 2026-06-16 | 2026-06-17 | 2 | 2 | 80 | High confidence | Critical | In Progress | Yes | Design readiness | No | No | Yes |  |  | Content Readiness | 6 | Public Web | OMCOZA | Personal | Invest Flexi Save | Copy enhancement + link mapping dependent on design activities
PRG-0059 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Personal landing page |  | Copy enhancement + link mapping dependent on design activities | Copy enhancement + link mapping dependent on design activities for Public Web / OMCOZA / Personal / Personal landing page. Planned delivery details: start 2026-07-06; end 2026-07-08; effort 3 days. Upstream dependency: Design readiness. Current status: In Progress. | 2026-07-06 | 2026-07-08 | 3 | 3 | 100 | High confidence | Critical | In Progress | Yes | Design readiness | No | No | Yes |  |  | Content Readiness | 7 | Public Web | OMCOZA | Personal | Personal landing page | Copy enhancement + link mapping dependent on design activities
PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Portfolio View for Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Part of the design work that is underway - not included in the number of journeys currently tracked. Current status: In Progress. Source comment/context: The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed. | TBC | TBC |  | TBC | 10 | Very low confidence | High | In Progress | Yes | Part of the design work that is underway - not included in the number of journeys currently tracked | Yes | Yes | Yes | The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed |  | Feature Delivery | 4 | Secure Web | N/A | Dashboard Views ( Porffolio Views) | All | Portfolio View
PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Standards on how to creates views on dashboard for TBC / TBC / Dashboard Views ( Porffolio Views) / All. Planned delivery details: start TBC; end TBC; effort TBC days. | TBC | TBC |  | TBC | 10 | Very low confidence | High | TBC | TBC |  | Yes | Yes | No |  |  | Feature Delivery | 5 |  |  | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard
PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Content Updates for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Content Updates to be confirmed. Current status: Blocked. Source comment/context:. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Blocked | Yes | Content Updates to be confirmed | Yes | Yes | Yes | . |  | Feature Delivery | 6 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Content Updates
PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Journeys Optimization for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Journey Optimisation to be confirmed. Current status: Blocked. Source comment/context:. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Blocked | Yes | Journey Optimisation to be confirmed | Yes | Yes | Yes | . |  | Feature Delivery | 7 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Journeys Optimization
PRG-0064 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Funeral and Death Claims | Funeral and Death Claims for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start 2026-06-01; end 2026-07-31; effort 45 days. Current status: In Progress. | 2026-06-01 | 2026-07-31 | 45 | 45 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 8 | Public Web | OMCOZA | Personal | L&S | Funeral and Death Claims
PRG-0065 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Transaction Tracking | Transaction Tracking for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-05-01; end 2026-06-30; effort 43 days. Current status: In Progress. | 2026-05-01 | 2026-06-30 | 43 | 43 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 9 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Transaction Tracking
PRG-0066 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Lump Sum Injections | Lump Sum Injections for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-03-01; end 2026-06-30; effort 87 days. Current status: In Progress. | 2026-03-01 | 2026-06-30 | 87 | 87 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 10 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Lump Sum Injections
PRG-0067 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Change Personal Details | Change Personal Details for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-05-01; end 2026-07-31; effort 66 days. Current status: In Progress. | 2026-05-01 | 2026-07-31 | 66 | 66 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 11 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Change Personal Details
PRG-0068 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Manage Contributions | Manage Contributions for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-05-01; end 2026-06-30; effort 43 days. Current status: In Progress. | 2026-05-01 | 2026-06-30 | 43 | 43 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 12 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Manage Contributions
PRG-0069 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Switch Funds | Switch Funds for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-05-01; end 2026-06-30; effort 43 days. Current status: In Progress. | 2026-05-01 | 2026-06-30 | 43 | 43 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 13 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Switch Funds
PRG-0070 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Withdrawals/Disinvestments | Withdrawals/Disinvestments for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-07-01; end 2026-12-01; effort 110 days. Current status: In Progress. | 2026-07-01 | 2026-12-01 | 110 | 110 | 40 | Low confidence | High | In Progress | No |  | Yes | Yes | No |  |  | Feature Delivery | 14 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Withdrawals/Disinvestments
PRG-0071 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Change Premium Allocation | Change Premium Allocation for Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Planned delivery details: start 2026-03-01; end 2026-06-30; effort 87 days. Current status: In Progress. | 2026-03-01 | 2026-06-30 | 87 | 87 | 80 | High confidence | High | In Progress | No |  | No | No | No |  |  | Feature Delivery | 15 | Secure Web | N/A | Servicing Transaction in Sec Web | All | Change Premium Allocation
PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Easy Plus Sales Jorurney on Public Web for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start TBC; end TBC. Upstream dependency: product page has to be updated before this journey can be migrated. Current status: Blocked. Source comment/context:. | TBC | TBC |  |  | 10 | Very low confidence | High | Blocked | Yes | product page has to be updated before this journey can be migrated | Yes | Yes | Yes | . |  | Feature Delivery | 16 | Public Web | OMCOZA | Personal | L&S | Easy Plus Sales Jorurney on Public Web
PRG-0073 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot | 2 Pot for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start 2026-03-01; end 2026-06-30; effort 87 days. Current status: In Progress. | 2026-03-01 | 2026-06-30 | 87 | 87 | 80 | High confidence | High | In Progress | TBC |  | No | No | No |  |  | Feature Delivery | 17 | Public Web | OMCOZA | Personal | L&S | 2 Pot
PRG-0074 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Find Advisor | Find Advisor for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start Beta Testing Ready; end Beta Testing Ready; effort Beta Testing Ready days. Upstream dependency: Design - Impact of of new templates on Find Advisor flow. Current status: In Progress. Source comment/context: TBC. | Beta Testing Ready | Beta Testing Ready |  | Beta Testing Ready | 90 | High confidence | High | In Progress | Yes | Design - Impact of of new templates on Find Advisor flow | No | Yes | Yes | TBC |  | Feature Delivery | 18 | Public Web | OMCOZA | Personal | L&S | Find Advisor
PRG-0075 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Debt Calculator | Debt Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start 2026-03-01; end 2026-06-30; effort 87 days. Current status: In Progress. | 2026-03-01 | 2026-06-30 | 87 | 87 | 80 | High confidence | High | In Progress | No | BA Capacity is constrained due current BA on medical Leave | Yes | Yes | No |  |  | Feature Delivery | 19 | Public Web | OMCOZA | Personal | L&S | Debt Calculator
PRG-0076 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Personal Calculator | Personal Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start 2026-03-01; end 2026-06-30; effort 87 days. | 2026-03-01 | 2026-06-30 | 87 | 87 | 80 | High confidence | High | TBC | No | End of Curent PI front end Development resources will move out of cross channel | Yes | Yes | No |  |  | Feature Delivery | 20 | Public Web | OMCOZA | Personal | L&S | Personal Calculator
PRG-0077 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Budget Calculator | Budget Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start 2026-03-02; end 2026-06-30; effort 87 days. | 2026-03-02 | 2026-06-30 | 87 | 87 |  | TBC | High | TBC | No |  | Yes | Yes | No |  |  | Feature Delivery | 21 | Public Web | OMCOZA | Personal | L&S | Budget Calculator
PRG-0078 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Income Tax Calculator | Income Tax Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start Beta Testing Ready; end Beta Testing Ready; effort Beta Testing Ready days. | Beta Testing Ready | Beta Testing Ready |  | Beta Testing Ready | 90 | High confidence | High | TBC | No |  | Yes | Yes | No |  |  | Feature Delivery | 22 | Public Web | OMCOZA | Personal | L&S | Income Tax Calculator
PRG-0079 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Retirement Calculator | Retirement Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start Beta Testing Ready; end Beta Testing Ready; effort Beta Testing Ready days. | Beta Testing Ready | Beta Testing Ready |  | Beta Testing Ready | 90 | High confidence | High | TBC | No |  | Yes | Yes | No |  |  | Feature Delivery | 23 | Public Web | OMCOZA | Personal | L&S | Retirement Calculator
PRG-0080 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot Calculator | 2 Pot Calculator for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start Beta Testing Ready; end Beta Testing Ready; effort Beta Testing Ready days. | Beta Testing Ready | Beta Testing Ready |  | Beta Testing Ready | 90 | High confidence | High | TBC | No |  | Yes | Yes | No |  |  | Feature Delivery | 24 | Public Web | OMCOZA | Personal | L&S | 2 Pot Calculator
PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Contact Us for Public Web / OMCOZA / Personal / L&S. Planned delivery details: start Analysis in Progress; end Analysis in Progress; effort Analysis in Progress days. | Analysis in Progress | Analysis in Progress |  | Analysis in Progress | 30 | Very low confidence | High | TBC | No |  | Yes | Yes | No |  |  | Feature Delivery | 25 | Public Web | OMCOZA | Personal | L&S | Contact Us
PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Design and Develop CI Updates onto OMDSv2 for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 10 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Blocked. | As soon as received |  | 10 | 10 | 50 | Low confidence | High | Blocked | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 4 | Public Web | All | All | All | Design and Develop CI Updates onto OMDSv2
PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Design and Develop Top Navigation Component Updates for Public Web / All / All / All. Planned delivery details: start 2026-05-01; effort 20 days. Upstream dependency: Foundational elements from Design Delivery. Current status: In Progress. Source comment/context: Started, but had to pause due to rework upstream. | 2026-05-01 |  | 20 | 20 | 50 | Low confidence | Critical | In Progress | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes | Started, but had to pause due to rework upstream. |  | Design Systems | 5 | Public Web | All | All | All | Design and Develop Top Navigation Component Updates
PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Design and Develop Top Navigation Component Updates for Secure Web / All / All / All. Planned delivery details: start As soon as received; effort 20 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 20 | 20 | 50 | Low confidence | Critical | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 6 | Secure Web | All | All | All | Design and Develop Top Navigation Component Updates
PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Design and Develop Footer Component Updates for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 5 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 5 | 5 | 50 | Low confidence | Critical | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 7 | Public Web | All | All | All | Design and Develop Footer Component Updates
PRG-0086 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Card Component Updates | Design and Develop Card Component Updates for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 10 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 10 | 10 | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | No | Yes | Yes |  |  | Design Systems | 8 | Public Web | All | All | All | Design and Develop Card Component Updates
PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Design and Develop Category Page Template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 8 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 8 | 8 | 50 | Low confidence | High | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 9 | Public Web | All | All | All | Design and Develop Category Page Template
PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Design and Develop Product Detail Page Template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 8 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 8 | 8 | 50 | Low confidence | High | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 10 | Public Web | All | All | All | Design and Develop Product Detail Page Template
PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Design and Develop Article Page Template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 3 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 3 | 3 | 50 | Low confidence | High | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 11 | Public Web | All | All | All | Design and Develop Article Page Template
PRG-0090 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Hero Banner Component Updates | Design and Develop Hero Banner Component Updates for Public Web / All / All / All. Planned delivery details: start As soon as received; effort 4 days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  | 4 | 4 | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | No | Yes | Yes |  |  | Design Systems | 12 | Public Web | All | All | All | Design and Develop Hero Banner Component Updates
PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Design and Develop Landing page template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 13 | Public Web | All | All | All | Design and Develop Landing page template
PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Design and Develop Section page template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 14 | Public Web | All | All | All | Design and Develop Section page template
PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Design and Develop Utility Template: Contact Us for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 15 | Public Web | All | All | All | Design and Develop Utility Template: Contact Us
PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Design and Develop Utility Template: All Calculators for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 16 | Public Web | All | All | All | Design and Develop Utility Template: All Calculators
PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Design and Develop Utility Template: Calculators Page for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 17 | Public Web | All | All | All | Design and Develop Utility Template: Calculators Page
PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Design and Develop Utility Templates: About Us for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 18 | Public Web | All | All | All | Design and Develop Utility Templates: About Us
PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Design and Develop Utility Template: Careers for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 19 | Public Web | All | All | All | Design and Develop Utility Template: Careers
PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Add copy standards to OMDS for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 20 | Public Web | All | All | All | Add copy standards to OMDS
PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Add copy standards to OMDS for Secure Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. Current status: Not Started. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | Not Started | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 21 | Secure Web | All | All | All | Add copy standards to OMDS
PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Design and Develop tenant template for Public Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | TBC | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 22 | Public Web | All | All | All | Design and Develop tenant template
PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Design and Develop tenant template for Secure Web / All / All / All. Planned delivery details: start As soon as received; effort Invalid source formula days. Upstream dependency: Foundational elements from Design Delivery. | As soon as received |  |  | Invalid source formula | 50 | Low confidence | Medium | TBC | Yes | Foundational elements from Design Delivery | Yes | Yes | Yes |  |  | Design Systems | 23 | Secure Web | All | All | All | Design and Develop tenant template
PRG-0102 | Execution | Luvuyo | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Implement OMCOM into production for Public Web / OMCOM / All / OM. Planned delivery details: start 2026-06-08; end 2026-06-12; effort 5 days. Upstream dependency: Stakeholder sign off. Current status: In Progress. Source comment/context: Awaiting stakeholder approval. | 2026-06-08 | 2026-06-12 | 5 | 5 | 70 | Moderate confidence | High | In Progress | Yes | Stakeholder sign off | Yes | Yes | Yes | Awaiting stakeholder approval |  | Execution | 4 | Public Web | OMCOM | All | OM | Implement OMCOM into production
PRG-0103 | Execution | Luvuyo | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Co-locating Content & Analytics Tagging | Dev: Co-locating Content & Analytics Tagging for Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. Planned delivery details: start 2026-06-15; end 2026-06-19; effort 5 days. Current status: Not Started. Source comment/context: Creating new content_types and updating existing content_types in ContentStack. | 2026-06-15 | 2026-06-19 | 5 | 5 | 90 | High confidence | Critical | Not Started | No |  | Yes | Yes | No | Creating new content_types and updating existing content_types in ContentStack |  | Execution | 5 | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire site |  | Dev: Co-locating Content & Analytics Tagging
PRG-0104 | Execution | Luvuyo | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Applying Analytics Tracking to V2 Components | Dev: Applying Analytics Tracking to V2 Components for Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. Planned delivery details: start 2026-06-23; end 2026-06-30; effort 6 days. Current status: Not Started. Source comment/context: Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable). | 2026-06-23 | 2026-06-30 | 6 | 6 | 70 | Moderate confidence | Critical | Not Started | No |  | Yes | Yes | No | Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable) |  | Execution | 6 | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire site |  | Dev: Applying Analytics Tracking to V2 Components
PRG-0105 | Execution | Luvuyo | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Dev: DevOps Quality Gate Pipeline for Public Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-15; end 2026-06-19; effort 5 days. Current status: Not Started. | 2026-06-15 | 2026-06-19 | 5 | 5 | 70 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 7 | Public Web | N/A | N/A |  | Dev: DevOps Quality Gate Pipeline
PRG-0106 | Execution | Luvuyo | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Dev: DevOps Quality Gate Pipeline for Secure Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-22; end 2026-06-29; effort 5 days. Current status: Not Started. | 2026-06-22 | 2026-06-29 | 5 | 5 | 70 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 8 | Secure Web | N/A | N/A |  | Dev: DevOps Quality Gate Pipeline
PRG-0107 | Execution | Luvuyo | Public Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | QE: Automated Testing Framework for Public Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-15; end 2026-06-19; effort 5 days. Current status: Not Started. | 2026-06-15 | 2026-06-19 | 5 | 5 | 70 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 9 | Public Web | N/A | N/A |  | QE: Automated Testing Framework
PRG-0108 | Execution | Luvuyo | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Dev/QE: DevOps - Integrate Automated Testing for Public Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-22; end 2026-06-29; effort 5 days. Current status: Not Started. | 2026-06-22 | 2026-06-29 | 5 | 5 | 60 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 10 | Public Web | N/A | N/A |  | Dev/QE: DevOps - Integrate Automated Testing
PRG-0109 | Execution | Luvuyo | Secure Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | QE: Automated Testing Framework for Secure Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-22; end 2026-06-29; effort 5 days. Current status: Not Started. | 2026-06-22 | 2026-06-29 | 5 | 5 | 70 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 11 | Secure Web | N/A | N/A |  | QE: Automated Testing Framework
PRG-0110 | Execution | Luvuyo | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Dev/QE: DevOps - Integrate Automated Testing for Secure Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-29; end 2026-07-03; effort 5 days. Current status: Not Started. | 2026-06-29 | 2026-07-03 | 5 | 5 | 60 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 12 | Secure Web | N/A | N/A |  | Dev/QE: DevOps - Integrate Automated Testing
PRG-0111 | Execution | Luvuyo | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Dev: Observability Dashboard Templates for Sites for Public Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-15; end 2026-06-22; effort 6 days. Current status: Not Started. | 2026-06-15 | 2026-06-22 | 6 | 6 | 70 | Moderate confidence | Critical | Not Started | No |  | Yes | Yes | No |  |  | Execution | 13 | Public Web | N/A | N/A |  | Dev: Observability Dashboard Templates for Sites
PRG-0112 | Execution | Luvuyo | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Dev: Observability Dashboard Templates for Sites for Secure Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-06-29; end 2026-07-01; effort 3 days. Upstream dependency: V2 DesignSystem update. Current status: Not Started. Source comment/context: Awaiting update to current V2 DesignSystem to allow for different background color. | 2026-06-29 | 2026-07-01 | 3 | 3 | 70 | Moderate confidence | Critical | Not Started | Yes | V2 DesignSystem update | Yes | Yes | Yes | Awaiting update to current V2 DesignSystem to allow for different background color |  | Execution | 14 | Secure Web | N/A | N/A |  | Dev: Observability Dashboard Templates for Sites
PRG-0113 | Execution | Luvuyo | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Dev: Styling Backwards Compatibility - V2 ModularPage for Public Web / All / All / Shared / All / TBC. Planned delivery details: start 2026-07-01; end 2026-07-02; effort 2 days. Upstream dependency: DesignSystem V2 Styling updates for background. Current status: Not Started. | 2026-07-01 | 2026-07-02 | 2 | 2 | 80 | High confidence | Critical | Not Started | Yes | DesignSystem V2 Styling updates for background | Yes | Yes | Yes |  |  | Execution | 18 | Public Web | All | N/A |  | Dev: Styling Backwards Compatibility - V2 ModularPage
PRG-0114 | Execution | Luvuyo | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Dev: Styling Backwards Compatibility - V2 ArticleModularPage for Public Web / All / All / Shared / All / TBC. Planned delivery details: start 2026-07-01; end 2026-07-02; effort 2 days. Upstream dependency: DesignSystem V2 Styling updates for background. Current status: Not Started. | 2026-07-01 | 2026-07-02 | 2 | 2 | 80 | High confidence | Critical | Not Started | Yes | DesignSystem V2 Styling updates for background | Yes | Yes | Yes |  |  | Execution | 19 | Public Web | All | N/A |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage
PRG-0115 | Execution | Luvuyo | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Dev: Export Analytics Data into Tableau for Public Web / All / All / Shared / All / TBC. Planned delivery details: start 2026-07-01; end 2026-07-06; effort ~5 days. Current status: Not Started. Source comment/context: Requires understanding of data sources, data destination, access credentials to involved systems. | 2026-07-01 | 2026-07-06 |  | ~5 | 40 | Low confidence | Critical | Not Started | No |  | Yes | Yes | Yes | Requires understanding of data sources, data destination, access credentials to involved systems |  | Execution | 20 | Public Web | All | N/A |  | Dev: Export Analytics Data into Tableau
PRG-0116 | Execution | Luvuyo | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Dev: Export Analytics Data into Tableau for Secure Web / Shared / Platform / All / Shared / All / TBC. Planned delivery details: start 2026-07-07; end 2026-07-10; effort 3 days. Current status: Not Started. Source comment/context: Requires understanding of data sources, data destination, access credentials to involved systems. | 2026-07-07 | 2026-07-10 | 3 | 3 | 40 | Low confidence | Critical | Not Started | No |  | Yes | Yes | Yes | Requires understanding of data sources, data destination, access credentials to involved systems |  | Execution | 21 | Secure Web | N/A | N/A |  | Dev: Export Analytics Data into Tableau
PRG-0117 | Execution | Luvuyo | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Dev: Configuring Web Transformation Page Template in ContentStack for Public Web / OMCOZA / Entire Site / All / TBC. Planned delivery details: start 2026-06-07; end 2026-07-09; effort 4 days. Upstream dependency: Web Transformation Page Template. Current status: Not Started. Source comment/context: Requires at least Web Transformation Page Template red-zones. | 2026-06-07 | 2026-07-09 | 4 | 4 | 80 | High confidence | Critical | Not Started | Yes | Web Transformation Page Template | Yes | Yes | Yes | Requires at least Web Transformation Page Template red-zones |  | Execution | 22 | Public Web | OMCOZA | Entire site |  | Dev: Configuring Web Transformation Page Template in ContentStack
PRG-0118 | Execution | Luvuyo | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Dev: Update Page Rendering Pipeline to support WT pages for Public Web / OMCOZA / Entire Site / All / TBC. Planned delivery details: start 2026-07-10; end 2026-07-16; effort 5 days. Upstream dependency: Web Transformation Page Template. Current status: Not Started. Source comment/context: Requires at least Web Transformation Page Template red-zones. | 2026-07-10 | 2026-07-16 | 5 | 5 | 80 | High confidence | Critical | Not Started | Yes | Web Transformation Page Template | Yes | Yes | Yes | Requires at least Web Transformation Page Template red-zones |  | Execution | 23 | Public Web | OMCOZA | Entire site |  | Dev: Update Page Rendering Pipeline to support WT pages
PRG-0119 | Execution | Luvuyo | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Dev: Navigation components updates public Web for Public Web / OMCOZA / All / Shared / All / TBC. Planned delivery details: start TBC; effort 8 days. Upstream dependency: New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component. Current status: Not Started. Source comment/context: Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component. | TBC |  | 8 | 8 | 40 | Low confidence | Critical | Not Started | Yes | New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component | Yes | Yes | Yes | Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component |  | Execution | 24 | Public Web | OMCOZA | N/A |  | Dev: Navigation components updates public Web
PRG-0120 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | QE : Automated Testing Framework (LS) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort 8 days. Current status: Not Started. | TBC |  | 8 | 8 | 60 | Moderate confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 25 | Public Web | OMCOZA | Personal |  | QE : Automated Testing Framework (LS)
PRG-0121 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Dev :Observability Dashboards for various sites (LS) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: effort 5 days. Current status: Not Started. |  |  | 5 | 5 | 50 | Low confidence | High | Not Started | No |  | Yes | Yes | No |  |  | Execution | 26 | Public Web | OMCOZA | Personal |  | Dev :Observability Dashboards for various sites (LS)
PRG-0122 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Dev : Modular Template (LS) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort 3 days. Upstream dependency: Design Page Template for Category & Product Detail pages. Current status: Not Started. Source comment/context: Awaiting Page Template drop. | TBC |  | 3 | 3 | 50 | Low confidence | Critical | Not Started | Yes | Design Page Template for Category & Product Detail pages | Yes | Yes | Yes | Awaiting Page Template drop |  | Execution | 28 | Public Web | OMCOZA | Personal |  | Dev : Modular Template (LS)
PRG-0123 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Dev : Modular Page Components (LS) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort ~5 days. Upstream dependency: New Transformation DesignSystem components. Current status: Not Started. Source comment/context: Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. | TBC |  |  | ~5 | 40 | Low confidence | Critical | Not Started | Yes | New Transformation DesignSystem components | Yes | Yes | Yes | Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. |  | Execution | 29 | Public Web | OMCOZA | Personal |  | Dev : Modular Page Components (LS)
PRG-0124 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Dev Applying analytics tracking to CMS (LS) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort ~5 days. Upstream dependency: New Transformation DesignSystem components. Current status: Not Started. Source comment/context: Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. | TBC |  |  | ~5 | 40 | Low confidence | Critical | Not Started | Yes | New Transformation DesignSystem components | Yes | Yes | Yes | Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. |  | Execution | 30 | Public Web | OMCOZA | Personal |  | Dev Applying analytics tracking to CMS (LS)
PRG-0125 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Dev: OMCOZA -Licence cutover for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort 5 days. Upstream dependency: Migrated OMCOZA site. Current status: Not Started. | TBC |  | 5 | 5 | 60 | Moderate confidence | Critical | Not Started | Yes | Migrated OMCOZA site | Yes | Yes | Yes |  |  | Execution | 31 | Public Web | OMCOZA | Personal |  | Dev: Omcoza -Licence cutover
PRG-0126 | Execution | Luvuyo | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Dev : Tableau Analytics for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start TBC; effort 8 days. Current status: Not Started. | TBC |  | 8 | 8 | 50 | Low confidence | Critical | Not Started | No |  | Yes | Yes | No |  |  | Execution | 32 | Public Web | OMCOZA | Personal |  | Dev : Tableau Analytics
PRG-0127 | Publishing | Bernice | Public Web | OMCOM | Entire Site | All / TBC |  | Take live in V2 new platform | Take live in V2 new platform for Public Web / OMCOM / Entire Site / All / TBC. Planned delivery details: start 2026-06-09; end 2026-06-11; effort 3 days. Current status: N/A. | 2026-06-09 | 2026-06-11 | 3 | 3 | 80 | High confidence | High | N/A | No |  | No | Yes | No |  |  | Publishing | 4 | Public Web | OMCOM | Entire site |  | Take live in V2 new platform
PRG-0128 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Testing in V2 new platform and log bugs | Testing in V2 new platform and log bugs for Public Web / OMAI (Alternatives) / Entire Site / All / TBC. Planned delivery details: start 2026-06-11; end 2026-06-26; effort 12 days. Current status: Not Started. Source comment/context: Need to work with Web developers for bug fixes. | 2026-06-11 | 2026-06-26 | 12 | 12 | 100 | High confidence | High | Not Started | No |  | Yes | Yes | Yes | Need to work with Web developers for bug fixes |  | Publishing | 5 | Public Web | OMAI (Alternatives) | Entire site |  | Testing in V2 new platform and log bugs
PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Take live in V2 new platform for Public Web / OMAI (Alternatives) / Entire Site / All / TBC. Planned delivery details: start TBC; effort Invalid source formula days. Current status: N/A. Source comment/context: Go live date will be determined in the next PI Planning. | TBC |  |  | Invalid source formula | 80 | High confidence | High | N/A | No |  | Yes | Yes | No | Go live date will be determined in the next PI Planning |  | Publishing | 6 | Public Web | OMAI (Alternatives) | Entire site |  | Take live in V2 new platform
PRG-0130 | Publishing | Bernice | Public Web | OMCOZA | Personal | Funeral |  | Record Funeral URL structure based on proposed sunset/consolidated pages. | Record Funeral URL structure based on proposed sunset/consolidated pages. for Public Web / OMCOZA / Personal / Funeral. Planned delivery details: start 2026-06-10; end 2026-06-18; effort 7 days. Current status: Not Started. Source comment/context: Work with Justin on the URLs for this section. | 2026-06-10 | 2026-06-18 | 7 | 7 | 90 | High confidence | High | Not Started | No |  | Yes | No | Yes | Work with Justin on the URLs for this section |  | Publishing | 7 | Public Web | OMCOZA | Personal | Funeral | Record Funeral URL structure based on proposed sunset/consolidated pages.
PRG-0131 | Publishing | Bernice | Public Web | OMCOZA | Personal | Retirement |  | Record Retirement URL structure based on consolidated pages as per new IA. | Record Retirement URL structure based on consolidated pages as per new IA. for Public Web / OMCOZA / Personal / Retirement. Planned delivery details: start 2026-06-10; end 2026-06-18; effort 7 days. Current status: Not Started. Source comment/context: Work with Justin on the URLs for this section. | 2026-06-10 | 2026-06-18 | 7 | 7 | 90 | High confidence | High | Not Started | No |  | Yes | No | Yes | Work with Justin on the URLs for this section |  | Publishing | 8 | Public Web | OMCOZA | Personal | Retirement | Record Retirement URL structure based on consolidated pages as per new IA.
PRG-0132 | Publishing | Bernice | Public Web | OMCOZA | Personal | Flexi Save |  | Record Flexi Save URL structure based on consolidated pages as per new IA. | Record Flexi Save URL structure based on consolidated pages as per new IA. for Public Web / OMCOZA / Personal / Flexi Save. Planned delivery details: start 2026-06-10; end 2026-06-18; effort 7 days. Current status: Not Started. Source comment/context: Work with Justin on the URLs for this section. | 2026-06-10 | 2026-06-18 | 7 | 7 | 90 | High confidence | High | Not Started | No |  | Yes | No | Yes | Work with Justin on the URLs for this section |  | Publishing | 9 | Public Web | OMCOZA | Personal | Flexi Save | Record Flexi Save URL structure based on consolidated pages as per new IA.
PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Record URL structure based on all as-is pages (keep/remove/consolidate) for Public Web / OMCOZA / as-is pages / All / TBC. Upstream dependency: Design/content. Current status: Not Started. |  |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 10 | Public Web | OMCOZA | As is pages |  | Record URL structure based on all as-is pages (keep/remove/consolidate)
PRG-0134 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Start moving as-is pages over to Beta | Start moving as-is pages over to Beta for Public Web / OMCOZA / as-is pages / All / TBC. Planned delivery details: start 2026-07-01; end 2026-12-01; effort 110 days. Upstream dependency: Design. Current status: In Progress. Source comment/context: Confirm pages and URLs for "as-is" pages before I can start moving. | 2026-07-01 | 2026-12-01 | 110 | 110 | 80 | High confidence | High | In Progress | Yes | Design | No | Yes | Yes | Confirm pages and URLs for "as-is" pages before I can start moving |  | Publishing | 11 | Public Web | OMCOZA | As is pages |  | Start moving as-is pages over to Beta
PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Record URL structure for all remaining Personal pages (keep/remove/consolidate) for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start 2026-07-30. Upstream dependency: Design/content. Current status: Not Started. | 2026-07-30 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 12 | Public Web | OMCOZA | Personal |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate)
PRG-0136 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Personal / All / TBC. Planned delivery details: start 2026-07-30; end 2026-12-01; effort 89 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-07-30 | 2026-12-01 | 89 | 89 | 70 | Moderate confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 13 | Public Web | OMCOZA | Personal |  | Start building new template pages
PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) for Public Web / OMCOZA / Corporate / All / TBC. Planned delivery details: start 2026-08-01. Upstream dependency: Design/content. Current status: Not Started. | 2026-08-01 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 14 | Public Web | OMCOZA | Corporate |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate)
PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Corporate / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-01; effort 87 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-01 | 87 | 87 | 40 | Low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 15 | Public Web | OMCOZA | Corporate |  | Start building new template pages
PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Wealth / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-02; effort 88 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-02 | 88 | 88 | 30 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 16 | Public Web | OMCOZA | Wealth |  | Start building new template pages
PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Record URL structure for all remaining Utility pages (keep/remove/consolidate) for Public Web / OMCOZA / Utility pages / All / TBC. Planned delivery details: start 2026-08-01. Upstream dependency: Design/content. Current status: Not Started. | 2026-08-01 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 17 | Public Web | OMCOZA | Utility pages |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate)
PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Utility pages / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-03; effort 89 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-03 | 89 | 89 | 30 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 18 | Public Web | OMCOZA | Utility pages |  | Start building new template pages
PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Record URL structure for all remaining About us pages (keep/remove/consolidate) for Public Web / OMCOZA / About Us / All / TBC. Planned delivery details: start 2026-08-01. Upstream dependency: Design/content. Current status: Not Started. | 2026-08-01 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 19 | Public Web | OMCOZA | About Us |  | Record URL structure for all remaining About us pages (keep/remove/consolidate)
PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / About Us / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-04; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-04 | 90 | 90 | 30 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 20 | Public Web | OMCOZA | About us |  | Start building new template pages
PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Record URL structure for all remaining Careers pages (keep/remove/consolidate) for Public Web / OMCOZA / Careers / All / TBC. Planned delivery details: start 2026-08-01. Upstream dependency: Design/content. Current status: Not Started. | 2026-08-01 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 21 | Public Web | OMCOZA | Careers |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate)
PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Careers / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-05; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-05 | 90 | 90 | 30 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 22 | Public Web | OMCOZA | Careers |  | Start building new template pages
PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Record URL structure for all remaining Business pages (keep/remove/consolidate) for Public Web / OMCOZA / Business / All / TBC. Planned delivery details: start 2026-08-01. Upstream dependency: Design/content. Current status: Not Started. | 2026-08-01 |  |  |  | 70 | Moderate confidence | High | Not Started | Yes | Design/content | Yes | Yes | Yes |  |  | Publishing | 23 | Public Web | OMCOZA | Business |  | Record URL structure for all remaining Business pages (keep/remove/consolidate)
PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Start building new template pages for Public Web / OMCOZA / Business / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-06 | 90 | 90 | 30 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 24 | Public Web | OMCOZA | Business |  | Start building new template pages
PRG-0148 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Add new Nav, Footer and update IA for Public Web / OMCOM / All / TBC / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-06 | 90 | 90 | 50 | Low confidence | Medium | Not Started | Yes | Design / Design Systems / Development | No | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 25 | Public Web | OMCOM |  |  | Add new Nav, Footer and update IA
PRG-0149 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Add new Nav, Footer and update IA for Public Web / OMAI (Alternatives) / All / TBC / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-06 | 90 | 90 | 50 | Low confidence | Medium | Not Started | Yes | Design / Design Systems / Development | No | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 26 | Public Web | OMAI (Alternatives) |  |  | Add new Nav, Footer and update IA
PRG-0150 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Add new Nav, Footer and update IA for Public Web / Bula Tsela / All / TBC / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-06 | 90 | 90 | 50 | Low confidence | Medium | Not Started | Yes | Design / Design Systems / Development | No | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 27 | Public Web | Bula Tsela |  |  | Add new Nav, Footer and update IA
PRG-0151 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Add new Nav, Footer and update IA for Public Web / LTD / All / TBC / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Work can only begin once all upstream teams have completed their work. | 2026-08-01 | 2026-12-06 | 90 | 90 | 50 | Low confidence | Medium | Not Started | Yes | Design / Design Systems / Development | No | Yes | Yes | Work can only begin once all upstream teams have completed their work |  | Publishing | 28 | Public Web | LTD |  |  | Add new Nav, Footer and update IA
PRG-0152 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC |  | Publishing requirements for OMAR, logged on OMAR tab | Publishing requirements for OMAR, logged on OMAR tab for Public Web / OMAR / All / TBC / All / TBC. Planned delivery details: start 2026-08-01; end 2026-12-06; effort 90 days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab. | 2026-08-01 | 2026-12-06 | 90 | 90 | 10 | Very low confidence | Medium | Not Started | Yes | Design / Design Systems / Development | No | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab. |  | Publishing | 29 | Public Web | OMAR |  |  | Publishing requirements for OMAR, logged on OMAR tab
PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Add all new redirects for the site for Public Web / OMCOZA / Entire Site / Entire Site. Planned delivery details: start TBC; end TBC; effort TBC days. Current status: Not Started. Source comment/context: Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live. | TBC | TBC |  | TBC |  | TBC | TBC | Not Started | TBC |  | No | Yes | No | Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live. |  | Publishing | 30 | Public Web | OMCOZA | Entire site | Entire site | Add all new redirects for the site
PRG-0154 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Penetration Testing Discussion and confirmation | Penetration Testing Discussion and confirmation for Public Web / All / All / All. Planned delivery details: start 2026-06-04; end 2026-06-04; effort 1 days. Current status: Complete. Source comment/context: Penetration Testing has to be done, at no cost to us, we just have to send URL' for testing - URL of sites must be sent Security Team. | 2026-06-04 | 2026-06-04 | 1 | 1 | 100 | High confidence | High | Complete | No |  | Yes | Yes | No | Penetration Testing has to be done, at no cost to us, we just have to send URL' for testing - URL of sites must be sent Security Team |  | Go-Live Readiness | 4 | Public Web | All | All | All | Penetration Testing Discussion and confirmation
PRG-0155 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Quality Assurance Approval | Quality Assurance Approval for Public Web / All / All / All. Planned delivery details: start 2026-11-01; end 2026-11-30; effort 21 days. Current status: Not Started. | 2026-11-01 | 2026-11-30 | 21 | 21 | 100 | High confidence | Low | Not Started | No |  | Yes | Yes | Yes |  |  | Go-Live Readiness | 5 | Public Web | All | All | All | Quality Assurance Approval
PRG-0156 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Security Approvals | Security Approvals for Public Web / All / All / All. Planned delivery details: start 2026-11-01; end 2026-11-30; effort 21 days. Upstream dependency: All deliveries must be in QA State. | 2026-11-01 | 2026-11-30 | 21 | 21 | 100 | High confidence | Low | TBC | Yes | All deliveries must be in QA State | Yes | Yes | Yes |  |  | Go-Live Readiness | 6 | Public Web | All | All | All | Security Approvals
PRG-0157 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Internal Communication ( Call Centre) - Marketing Team Driven | Internal Communication ( Call Centre) - Marketing Team Driven for Public Web / All / All / All. Planned delivery details: start 2026-09-01; end 2026-11-30; effort 65 days. Upstream dependency: All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T. Current status: Not Started. | 2026-09-01 | 2026-11-30 | 65 | 65 | 70 | Moderate confidence | Low | Not Started | Yes | All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T | No | Yes | Yes |  |  | Go-Live Readiness | 7 | Public Web | All | All | All | Internal Communication ( Call Centre) - Marketing Team Driven
PRG-0158 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Service Now Update | Service Now Update for Public Web / All / All / All. Planned delivery details: start 2026-09-01; end 2026-11-30; effort 65 days. Current status: Not Started. | 2026-09-01 | 2026-11-30 | 65 | 65 | 80 | High confidence | Low | Not Started | No |  | No | Yes | No |  |  | Go-Live Readiness | 8 | Public Web | All | All | All | Service Now Update
PRG-0159 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Executive Approval | Executive Approval for Public Web / All / All / All. Planned delivery details: start 2026-11-16; end 2026-11-30; effort 11 days. Upstream dependency: Approval to go ahead from all other Teams. Current status: Not Started. | 2026-11-16 | 2026-11-30 | 11 | 11 | 50 | Low confidence | Low | Not Started | Yes | Approval to go ahead from all other Teams | Yes | Yes | Yes |  |  | Go-Live Readiness | 9 | Public Web | All | All | All | Executive Approval
PRG-0160 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Change Management Go Ahead | Change Management Go Ahead for Public Web / All / All / All. Planned delivery details: start 2026-11-29; end 2026-11-30; effort 1 days. Upstream dependency: All work by teams must be completed. Current status: Not Started. | 2026-11-29 | 2026-11-30 | 1 | 1 | 50 | Low confidence | Low | Not Started | Yes | All work by teams must be completed | Yes | Yes | Yes |  |  | Go-Live Readiness | 10 | Public Web | All | All | All | Change Management Go Ahead
PRG-0161 | Go-Live Readiness | Luvuyo | Public Web | All | All | All |  | Customer Experience Tool | Customer Experience Tool for Public Web / All / All / All. Planned delivery details: start 2026-06-04; end 2026-09-30; effort 85 days. Upstream dependency: Tool Evaluating. Current status: Not Started. Source comment/context: Tool still in evaluation tool. | 2026-06-04 | 2026-09-30 | 85 | 85 | 10 | Very low confidence | Low | Not Started | Yes | Tool Evaluating | No | Yes | Yes | Tool still in evaluation tool |  | Go-Live Readiness | 11 | Public Web | All | All | All | Customer Experience Tool
PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Confirm Engagement Cycle with SEO Team for Public Web / All / All / All. Planned delivery details: start 2026-06-08; end 2026-06-15; effort 6 days. Current status: In Progress. Source comment/context: Final Approval will be provided by the CMO. | 2026-06-08 | 2026-06-15 | 6 | 6 | 100 | High confidence | High | In Progress | No |  | Yes | Yes | Yes | Final Approval will be provided by the CMO |  | SEO Analytics | 4 | Public Web | All | All | All | Confirm Engagement Cycle with SEO Team
PRG-0163 | SEO / Analytics | TBC | Public Web | All | All | All |  | SEO Requirements to Dev Team | SEO Requirements to Dev Team for Public Web / All / All / All. Planned delivery details: start 2026-06-08; end 2026-06-15; effort 6 days. | 2026-06-08 | 2026-06-15 | 6 | 6 | 100 | High confidence | High | TBC | No |  | Yes | Yes | No |  |  | SEO Analytics | 5 | Public Web | All | All | All | SEO Requirements to Dev Team
PRG-0164 | OMAR | Luvuyo | Public Web | OMAR | OMAR | OMAR | OMAR / TBC | Engagement required to communicate recalibration of project to various OMAR Stakeholder | Engagement required to communicate recalibration of project to various OMAR Stakeholder for Public Web / OMAR / OMAR / OMAR. Planned delivery details: start 2026-06-08; end 2026-06-30; effort 17 days. Current status: In Progress. Source comment/context: Engagement with OMAR teams are required in order to assist them with the recalibration of their plans, the plan must take into account Navigation and plan changes. | 2026-06-08 | 2026-06-30 | 17 | 17 | 70 | Moderate confidence | Critical | In Progress | No | Nothing , we need a clear communications plan for OMAR | Yes | Yes | No | Engagement with OMAR teams are required in order to assist them with the recalibration of their plans, the plan must take into account Navigation and plan changes |  | OMAR | 4 | Public Web | OMAR | OMAR | OMAR | Engagement required to communicate recalibration of project to various OMAR Stakeholder
PRG-0165 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 5 | Public Web | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform
PRG-0166 | OMAR | Luvuyo | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Ghana / Ghana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 6 | Public Web | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform
PRG-0167 | OMAR | Luvuyo | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Kenya / Kenya. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 7 | Public Web | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform
PRG-0168 | OMAR | Luvuyo | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Namibia / Namibia. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 8 | Public Web | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform
PRG-0169 | OMAR | Luvuyo | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Rwanda / Rwanda. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 9 | Public Web | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform
PRG-0170 | OMAR | Luvuyo | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Uganda / Uganda. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 10 | Public Web | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform
PRG-0171 | OMAR | Luvuyo | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Zimbabwe / Zimbabwe. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. Source comment/context: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes | Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work |  | OMAR | 11 | Public Web | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform
PRG-0172 | OMAR | Luvuyo | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Publishing of all pages in V2 New platform for Public Web / OMAR / Namibia / Namibia. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Design / Design Systems / Development. Current status: Not Started. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Design / Design Systems / Development | Yes | Yes | Yes |  |  | OMAR | 12 | Public Web | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform
PRG-0173 | OMAR | Luvuyo | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Travel Insurance Sales Migration for Public Web / OMAR / Ghana / Ghana. Planned delivery details: start 2026-07-18; end 2026-07-31; effort 10 days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. | 2026-07-18 | 2026-07-31 | 10 | 10 | 40 | Low confidence | High | In Progress | Yes |  | Yes | Yes | Yes |  |  | OMAR | 13 | Public Web | Ghana | Ghana | Ghana | Travel Insurance Sales Migration
PRG-0174 | OMAR | Luvuyo | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Mvest for Public Web / OMAR / Ghana / Ghana. Planned delivery details: start 2026-07-18; end 2026-07-31; effort 10 days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. | 2026-07-18 | 2026-07-31 | 10 | 10 | 40 | Low confidence | High | In Progress | Yes |  | Yes | Yes | Yes |  |  | OMAR | 14 | Public Web | Ghana | Ghana | Ghana | Mvest
PRG-0175 | OMAR | Luvuyo | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Personal Loan Application for Public Web / OMAR / Namibia / Namibia. Planned delivery details: start 2026-05-27; end 2026-07-31; effort 48 days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. | 2026-05-27 | 2026-07-31 | 48 | 48 | 50 | Low confidence | High | In Progress | Yes |  | Yes | Yes | Yes |  |  | OMAR | 15 | Public Web | Namibia | Namibia | Namibia | Personal Loan Application
PRG-0176 | OMAR | Luvuyo | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Personal Loan Repayment Calculator for Public Web / OMAR / Namibia / Namibia. Planned delivery details: start 2026-07-18; end 2026-07-31; effort 10 days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. | 2026-07-18 | 2026-07-31 | 10 | 10 | 50 | Low confidence | High | In Progress | Yes |  | Yes | Yes | Yes |  |  | OMAR | 16 | Public Web | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator
PRG-0177 | OMAR | Luvuyo | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Migration of Secure Web for Secure Web / OMAR / Namibia / Namibia. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency: Designs for their Secure Web. Current status: Not Started. Source comment/context: Resource constraints 2 people looking after 2 platforms. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes | Designs for their Secure Web | Yes | Yes | Yes | Resource constraints 2 people looking after 2 platforms |  | OMAR | 17 | Secure Web | Namibia | Namibia | Namibia | Migration of Secure Web
PRG-0178 | OMAR | Luvuyo | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Service Transactions for Secure Web / OMAR / Namibia / Namibia. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. | TBC | TBC |  | TBC |  | TBC | High | Not Started | Yes |  | Yes | Yes | Yes |  |  | OMAR | 18 | Secure Web | Namibia | Namibia | Namibia | Service Transactions
PRG-0179 | OMAR | Luvuyo | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Eswatini Funeral for Public Web / OMAR / eSwatini / eSwatini. Planned delivery details: start 2026-01-27; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. Source comment/context: testing in progress. | 2026-01-27 | TBC |  | TBC | 70 | Moderate confidence | High | In Progress | Yes |  | Yes | Yes | Yes | testing in progress |  | OMAR | 19 | Public Web | Ghana | Eswatini | Eswatini | Eswatini Funeral
PRG-0180 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Funeral Claims - Servicing Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | In Progress | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 20 | Public Web | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey
PRG-0181 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Motor claims - Service Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: In Progress. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | In Progress | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 21 | Public Web | Botswana | Botswana | Botswana | Motor claims - Service Journey
PRG-0182 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Home owners claims- Service Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 22 | Public Web | Botswana | Botswana | Botswana | Home owners claims- Service Journey
PRG-0183 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Home content claims Service Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 23 | Public Web | Botswana | Botswana | Botswana | Home content claims Service Journey
PRG-0184 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Credit Life for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 24 | Public Web | Botswana | Botswana | Botswana | Credit Life
PRG-0185 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Funeral Claims - Sales Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 25 | Public Web | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey
PRG-0186 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Motor claims - Sales Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 26 | Public Web | Botswana | Botswana | Botswana | Motor claims - Sales Journey
PRG-0187 | OMAR | Luvuyo | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Home owners claims- Sales Journey for Public Web / OMAR / Botswana / Botswana. Planned delivery details: start TBC; end TBC; effort TBC days. Upstream dependency is marked as required, but the dependency detail was not specified in the source worksheet. Current status: Not Started. Source comment/context: Resources shared between Botswana and Eswatini. | TBC | TBC |  | TBC | 10 | Very low confidence | High | Not Started | Yes |  | Yes | Yes | Yes | Resources shared between Botswana and Eswatini |  | OMAR | 27 | Public Web | Botswana | Botswana | Botswana | Home owners claims- Sales Journey

## UPLOAD_Risks
Risk_ID | Linked_Programme_Record_ID | Workstream | Owner | Channel | Domain | Area_Journey | Cluster | Market | Related_Deliverable | Risk_Type | Title | Detailed_Description | Risk_Severity | Priority | Status | Confidence_Percent | Required_Action | Source_Sheet | Source_Row | Source_Evidence
RSK-0001 | PRG-0001 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Navigation |  | Design navigation structure based on the IA | Blocker Risk | Design navigation structure based on the IA is at risk due to paused, blocked, or awaiting state | The source data indicates that Design navigation structure based on the IA is paused, blocked, or awaiting an upstream input. This creates delivery risk for Design Standards / Public Web / OMCOZA / Entire Site / Navigation. Evidence: This is about 90% complete, there is some changes based on testing and brand alignment (based on the approved interim brand). The DS team has paused this until we provide the amended nav structure. | High | Critical | In Progress | 100 | Escalate the blocker and agree a recovery action. | Design Standards | 4 | Design Standards row 4 ¦ task='Design navigation structure based on the IA' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='Though we have an agreed structure, there is a dependency on brand alignment. Even though there is structure, we may not have stressed tested everything.' ¦ comment='This is about 90% complete, there is some changes based on testing and brand alignment (based on the approved interim brand). The DS team has paused this until we provide the amended nav structure.'
RSK-0002 | PRG-0003 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Landing Page Template | Approval Risk | Design Landing Page Template has approval-gate risk | The source data shows that Design Landing Page Template depends on approval or sign-off. Late approval could delay downstream delivery for Design Standards / Public Web / OMCOZA / Entire Site / Templates. Evidence: This requires input and alignment from who will be providing feedback and approval of templates like this. | High | Critical | In Progress | 60 | Book approval session and define approval criteria. | Design Standards | 6 | Design Standards row 6 ¦ task='Design Landing Page Template' ¦ priority=Critical ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
RSK-0003 | PRG-0004 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Section Page Template | Approval Risk | Design Section Page Template has approval-gate risk | The source data shows that Design Section Page Template depends on approval or sign-off. Late approval could delay downstream delivery for Design Standards / Public Web / OMCOZA / Entire Site / Templates. Evidence: This requires input and alignment from who will be providing feedback and approval of templates like this. | Medium | High | In Progress | 60 | Book approval session and define approval criteria. | Design Standards | 7 | Design Standards row 7 ¦ task='Design Section Page Template' ¦ priority=High ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
RSK-0004 | PRG-0008 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: All Calculators | Confidence Risk | Design Utility Template: All Calculators has low-confidence delivery commitment | Design Utility Template: All Calculators is priority High with only 40% confidence. This creates commitment risk for Design Standards / Public Web / OMCOZA / Personal / Templates, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Design Standards | 11 | Design Standards row 11 ¦ task='Design Utility Template: All Calculators' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There is a lot of calculators that require a lot of input across different product and business clusters.' ¦ comment='The work has started for both desktop and mobile.'
RSK-0005 | PRG-0009 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: Calculators Page | Confidence Risk | Design Utility Template: Calculators Page has low-confidence delivery commitment | Design Utility Template: Calculators Page is priority High with only 40% confidence. This creates commitment risk for Design Standards / Public Web / OMCOZA / Personal / Templates, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Design Standards | 12 | Design Standards row 12 ¦ task='Design Utility Template: Calculators Page' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.' ¦ comment='This work has started.'
RSK-0006 | PRG-0013 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation structure based on the IA | Confidence Risk | Design navigation structure based on the IA has low-confidence delivery commitment | Design navigation structure based on the IA is priority High with only 40% confidence. This creates commitment risk for Design Standards / Secure Web / MyOM / Entire Site / Navigation, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Design Standards | 16 | Design Standards row 16 ¦ task='Design navigation structure based on the IA' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Initial designs have been done, it requires further discussion of how the pieces need to fit.' ¦ comment='Initial designs has started.'
RSK-0007 | PRG-0014 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation solution to allow access to other secure sites | Dependency Risk | Design navigation solution to allow access to other secure sites has an untracked dependency risk | The worksheet marks Design navigation solution to allow access to other secure sites as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for Design Standards / Secure Web / MyOM / Entire Site / Navigation. | High | High | In Progress | 70 | Name the upstream deliverable, owner, and target completion date. | Design Standards | 17 | Design Standards row 17 ¦ task='Design navigation solution to allow access to other secure sites' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes
RSK-0008 | PRG-0020 | Design Standards | Justin | Public Web | OMCOZA | Insure / iWyze | Tenant |  | Design iWyze Tenant Product Page Template | Schedule / Delivery Risk | Design iWyze Tenant Product Page Template may not start or complete on plan | Design iWyze Tenant Product Page Template is a High priority item with status 'Not Started'. This creates delivery risk for Design Standards / Public Web / OMCOZA / Insure / iWyze / Tenant, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Design Standards | 23 | Design Standards row 23 ¦ task='Design iWyze Tenant Product Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Alignment with OMF as well as the actual tenant.'
RSK-0009 | PRG-0020 | Design Standards | Justin | Public Web | OMCOZA | Insure / iWyze | Tenant |  | Design iWyze Tenant Product Page Template | Confidence Risk | Design iWyze Tenant Product Page Template has low-confidence delivery commitment | Design iWyze Tenant Product Page Template is priority High with only 30% confidence. This creates commitment risk for Design Standards / Public Web / OMCOZA / Insure / iWyze / Tenant, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Design Standards | 23 | Design Standards row 23 ¦ task='Design iWyze Tenant Product Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Alignment with OMF as well as the actual tenant.'
RSK-0010 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Retirement. Evidence: We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
RSK-0011 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Retirement. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
RSK-0012 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Funeral. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0013 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Funeral. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0014 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0015 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0016 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has approval-gate risk | The source data shows that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 80 | Book approval session and define approval criteria. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0017 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has accountability risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named owner before plan baseline. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0018 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has approval-gate risk | The source data shows that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 80 | Book approval session and define approval criteria. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0019 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has accountability risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named owner before plan baseline. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0020 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has approval-gate risk | The source data shows that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 80 | Book approval session and define approval criteria. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0021 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has accountability risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named owner before plan baseline. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0022 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has approval-gate risk | The source data shows that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 80 | Book approval session and define approval criteria. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0023 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has accountability risk | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named owner before plan baseline. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0024 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Schedule / Delivery Risk | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding may not start or complete on plan | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding is a Critical priority item with status 'Not Started'. This creates delivery risk for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 100 | Confirm start readiness, blockers, and escalation path. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
RSK-0025 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Resource Capacity Risk | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding. This creates capacity risk for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. Evidence:. | Critical | Critical | Not Started | 100 | Review allocation and confirm whether the current resource pool can support the committed scope. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
RSK-0026 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Accountability Risk | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding has accountability risk | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. | Critical | Critical | Not Started | 100 | Assign a named owner before plan baseline. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
RSK-0027 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Approval Risk | Audience landing with enhanced copy has approval-gate risk | The source data shows that Audience landing with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0028 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Accountability Risk | Audience landing with enhanced copy has accountability risk | Audience landing with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0029 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Invest. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0030 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Invest. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0031 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / OM Bank. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0032 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / OM Bank. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0033 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Insure. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0034 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Insure. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0035 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / About us. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0036 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / About us. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0037 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / Careers. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0038 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / Careers. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0039 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Risk | Mapping of new IA and Footer to sxisting site structure has approval-gate risk | The source data shows that Mapping of new IA and Footer to sxisting site structure depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0040 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Risk | Mapping of new IA and Footer to sxisting site structure has accountability risk | Mapping of new IA and Footer to sxisting site structure is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0041 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Risk | Mapping of new IA and Footer to sxisting site structure has approval-gate risk | The source data shows that Mapping of new IA and Footer to sxisting site structure depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0042 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Risk | Mapping of new IA and Footer to sxisting site structure has accountability risk | Mapping of new IA and Footer to sxisting site structure is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0043 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Risk | Mapping of new IA and Footer to sxisting site structure has approval-gate risk | The source data shows that Mapping of new IA and Footer to sxisting site structure depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0044 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Risk | Mapping of new IA and Footer to sxisting site structure has accountability risk | Mapping of new IA and Footer to sxisting site structure is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0045 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Approval Risk | Audience landing with enhanced copy has approval-gate risk | The source data shows that Audience landing with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 70 | Book approval session and define approval criteria. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0046 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Accountability Risk | Audience landing with enhanced copy has accountability risk | Audience landing with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0047 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / Invest. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 70 | Book approval session and define approval criteria. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0048 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / Invest. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0049 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / Plan. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 70 | Book approval session and define approval criteria. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0050 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / Plan. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0051 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / About. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 70 | Book approval session and define approval criteria. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0052 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / About. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0053 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Wealth / Insights. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 70 | Book approval session and define approval criteria. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0054 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Wealth / Insights. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0055 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Approval Risk | Audience landing with enhanced copy has approval-gate risk | The source data shows that Audience landing with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0056 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Accountability Risk | Audience landing with enhanced copy has accountability risk | Audience landing with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0057 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Corporate / Employees. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0058 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Corporate / Employees. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0059 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Corporate / Employers. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0060 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Corporate / Employers. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0061 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Corporate / Services. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0062 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Corporate / Services. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0063 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Approval Risk | Audience landing with enhanced copy has approval-gate risk | The source data shows that Audience landing with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Business Landing. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0064 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Accountability Risk | Audience landing with enhanced copy has accountability risk | Audience landing with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Business Landing. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0065 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Insure. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0066 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Insure. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0067 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Invest. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0068 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Invest. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0069 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Protect. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0070 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Protect. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0071 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Guarantee. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0072 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Guarantee. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0073 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has approval-gate risk | The source data shows that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Business / Tools. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0074 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has accountability risk | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Business / Tools. | Critical | Critical | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0075 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Schedule / Delivery Risk | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. may not start or complete on plan | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. is a Critical priority item with status 'TBC'. This creates delivery risk for Design Delivery / Public Web / OMCOZA / Personal / My OldMutual, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | TBC | 70 | Confirm start readiness, blockers, and escalation path. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0076 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Approval Risk | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. has approval-gate risk | The source data shows that Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | Critical | Critical | TBC | 70 | Book approval session and define approval criteria. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0077 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Accountability Risk | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. has accountability risk | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. is priority Critical but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. | Critical | Critical | TBC | 70 | Assign a named owner before plan baseline. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0078 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Approval Risk | Socilaisation of defined IA and Page templates for handover. has approval-gate risk | The source data shows that Socilaisation of defined IA and Page templates for handover. depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | High | High | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0079 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Accountability Risk | Socilaisation of defined IA and Page templates for handover. has accountability risk | Socilaisation of defined IA and Page templates for handover. is priority High but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. | High | High | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0080 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Approval Risk | Socilaisation of defined IA and Page templates for handover. has approval-gate risk | The source data shows that Socilaisation of defined IA and Page templates for handover. depends on approval or sign-off. Late approval could delay downstream delivery for Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined. | High | High | In Progress | 100 | Book approval session and define approval criteria. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0081 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Accountability Risk | Socilaisation of defined IA and Page templates for handover. has accountability risk | Socilaisation of defined IA and Page templates for handover. is priority High but has no named owner. This creates accountability risk for Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. | High | High | In Progress | 100 | Assign a named owner before plan baseline. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
RSK-0082 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Roadmap Planning Risk | Portfolio View has roadmap uncertainty due to TBC schedule or effort | Portfolio View is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All because the item cannot be sequenced or capacity-planned reliably. | High | High | In Progress | 10 | Resolve TBC dates and effort before baseline planning. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
RSK-0083 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Confidence Risk | Portfolio View has low-confidence delivery commitment | Portfolio View is priority High with only 10% confidence. This creates commitment risk for Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All, especially where dates are already present in the roadmap. | High | High | In Progress | 10 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
RSK-0084 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Schedule / Delivery Risk | Standards on how to creates views on dashboard may not start or complete on plan | Standards on how to creates views on dashboard is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 10 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
RSK-0085 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Roadmap Planning Risk | Standards on how to creates views on dashboard has roadmap uncertainty due to TBC schedule or effort | Standards on how to creates views on dashboard is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All because the item cannot be sequenced or capacity-planned reliably. | High | High | TBC | 10 | Resolve TBC dates and effort before baseline planning. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
RSK-0086 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Confidence Risk | Standards on how to creates views on dashboard has low-confidence delivery commitment | Standards on how to creates views on dashboard is priority High with only 10% confidence. This creates commitment risk for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All, especially where dates are already present in the roadmap. | High | High | TBC | 10 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
RSK-0087 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Schedule / Delivery Risk | Content Updates may not start or complete on plan | Content Updates is a High priority item with status 'Blocked'. This creates delivery risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Blocked | 10 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
RSK-0088 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Roadmap Planning Risk | Content Updates has roadmap uncertainty due to TBC schedule or effort | Content Updates is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All because the item cannot be sequenced or capacity-planned reliably. | High | High | Blocked | 10 | Resolve TBC dates and effort before baseline planning. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
RSK-0089 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Confidence Risk | Content Updates has low-confidence delivery commitment | Content Updates is priority High with only 10% confidence. This creates commitment risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All, especially where dates are already present in the roadmap. | High | High | Blocked | 10 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
RSK-0090 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Blocker Risk | Content Updates is at risk due to paused, blocked, or awaiting state | The source data indicates that Content Updates is paused, blocked, or awaiting an upstream input. This creates delivery risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Evidence:. | High | High | Blocked | 10 | Escalate the blocker and agree a recovery action. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
RSK-0091 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Schedule / Delivery Risk | Journeys Optimization may not start or complete on plan | Journeys Optimization is a High priority item with status 'Blocked'. This creates delivery risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Blocked | 10 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
RSK-0092 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Roadmap Planning Risk | Journeys Optimization has roadmap uncertainty due to TBC schedule or effort | Journeys Optimization is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All because the item cannot be sequenced or capacity-planned reliably. | High | High | Blocked | 10 | Resolve TBC dates and effort before baseline planning. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
RSK-0093 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Confidence Risk | Journeys Optimization has low-confidence delivery commitment | Journeys Optimization is priority High with only 10% confidence. This creates commitment risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All, especially where dates are already present in the roadmap. | High | High | Blocked | 10 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
RSK-0094 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Blocker Risk | Journeys Optimization is at risk due to paused, blocked, or awaiting state | The source data indicates that Journeys Optimization is paused, blocked, or awaiting an upstream input. This creates delivery risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. Evidence:. | High | High | Blocked | 10 | Escalate the blocker and agree a recovery action. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
RSK-0095 | PRG-0070 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Withdrawals/Disinvestments | Confidence Risk | Withdrawals/Disinvestments has low-confidence delivery commitment | Withdrawals/Disinvestments is priority High with only 40% confidence. This creates commitment risk for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 14 | Feature Delivery row 14 ¦ task='Withdrawals/Disinvestments' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=No
RSK-0096 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Schedule / Delivery Risk | Easy Plus Sales Jorurney on Public Web may not start or complete on plan | Easy Plus Sales Jorurney on Public Web is a High priority item with status 'Blocked'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Blocked | 10 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
RSK-0097 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Roadmap Planning Risk | Easy Plus Sales Jorurney on Public Web has roadmap uncertainty due to TBC schedule or effort | Easy Plus Sales Jorurney on Public Web is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S because the item cannot be sequenced or capacity-planned reliably. | High | High | Blocked | 10 | Resolve TBC dates and effort before baseline planning. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
RSK-0098 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Confidence Risk | Easy Plus Sales Jorurney on Public Web has low-confidence delivery commitment | Easy Plus Sales Jorurney on Public Web is priority High with only 10% confidence. This creates commitment risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially where dates are already present in the roadmap. | High | High | Blocked | 10 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
RSK-0099 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Blocker Risk | Easy Plus Sales Jorurney on Public Web is at risk due to paused, blocked, or awaiting state | The source data indicates that Easy Plus Sales Jorurney on Public Web is paused, blocked, or awaiting an upstream input. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S. Evidence:. | High | High | Blocked | 10 | Escalate the blocker and agree a recovery action. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
RSK-0100 | PRG-0075 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Debt Calculator | Resource Capacity Risk | Debt Calculator is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Debt Calculator. This creates capacity risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S. Evidence: BA Capacity is constrained due current BA on medical Leave. | Medium | High | In Progress | 80 | Review allocation and confirm whether the current resource pool can support the committed scope. | Feature Delivery | 19 | Feature Delivery row 19 ¦ task='Debt Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=No ¦ dependency='BA Capacity is constrained due current BA on medical Leave'
RSK-0101 | PRG-0076 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Personal Calculator | Schedule / Delivery Risk | Personal Calculator may not start or complete on plan | Personal Calculator is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 80 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 20 | Feature Delivery row 20 ¦ task='Personal Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=80% ¦ upstream=No ¦ dependency='End of Curent PI front end Development resources will move out of cross channel'
RSK-0102 | PRG-0077 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Budget Calculator | Schedule / Delivery Risk | Budget Calculator may not start or complete on plan | Budget Calculator is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC |  | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 21 | Feature Delivery row 21 ¦ task='Budget Calculator' ¦ priority=High ¦ status=TBC ¦ upstream=No
RSK-0103 | PRG-0078 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Income Tax Calculator | Schedule / Delivery Risk | Income Tax Calculator may not start or complete on plan | Income Tax Calculator is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 90 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 22 | Feature Delivery row 22 ¦ task='Income Tax Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
RSK-0104 | PRG-0079 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Retirement Calculator | Schedule / Delivery Risk | Retirement Calculator may not start or complete on plan | Retirement Calculator is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 90 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 23 | Feature Delivery row 23 ¦ task='Retirement Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
RSK-0105 | PRG-0080 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot Calculator | Schedule / Delivery Risk | 2 Pot Calculator may not start or complete on plan | 2 Pot Calculator is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 90 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 24 | Feature Delivery row 24 ¦ task='2 Pot Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
RSK-0106 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Schedule / Delivery Risk | Contact Us may not start or complete on plan | Contact Us is a High priority item with status 'TBC'. This creates delivery risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 30 | Confirm start readiness, blockers, and escalation path. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
RSK-0107 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Confidence Risk | Contact Us has low-confidence delivery commitment | Contact Us is priority High with only 30% confidence. This creates commitment risk for Feature Delivery / Public Web / OMCOZA / Personal / L&S, especially where dates are already present in the roadmap. | High | High | TBC | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
RSK-0108 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Schedule / Delivery Risk | Design and Develop CI Updates onto OMDSv2 may not start or complete on plan | Design and Develop CI Updates onto OMDSv2 is a High priority item with status 'Blocked'. This creates delivery risk for Design Systems / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Blocked | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0109 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Confidence Risk | Design and Develop CI Updates onto OMDSv2 has low-confidence delivery commitment | Design and Develop CI Updates onto OMDSv2 is priority High with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | High | High | Blocked | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0110 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Blocker Risk | Design and Develop CI Updates onto OMDSv2 is at risk due to paused, blocked, or awaiting state | The source data indicates that Design and Develop CI Updates onto OMDSv2 is paused, blocked, or awaiting an upstream input. This creates delivery risk for Design Systems / Public Web / All / All / All. Evidence: Foundational elements from Design Delivery. | High | High | Blocked | 50 | Escalate the blocker and agree a recovery action. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0111 | PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Confidence Risk | Design and Develop Top Navigation Component Updates has low-confidence delivery commitment | Design and Develop Top Navigation Component Updates is priority Critical with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | Critical | Critical | In Progress | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 5 | Design Systems row 5 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery' ¦ comment='Started, but had to pause due to rework upstream.'
RSK-0112 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Schedule / Delivery Risk | Design and Develop Top Navigation Component Updates may not start or complete on plan | Design and Develop Top Navigation Component Updates is a Critical priority item with status 'Not Started'. This creates delivery risk for Design Systems / Secure Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0113 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Confidence Risk | Design and Develop Top Navigation Component Updates has low-confidence delivery commitment | Design and Develop Top Navigation Component Updates is priority Critical with only 50% confidence. This creates commitment risk for Design Systems / Secure Web / All / All / All, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0114 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Schedule / Delivery Risk | Design and Develop Footer Component Updates may not start or complete on plan | Design and Develop Footer Component Updates is a Critical priority item with status 'Not Started'. This creates delivery risk for Design Systems / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0115 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Confidence Risk | Design and Develop Footer Component Updates has low-confidence delivery commitment | Design and Develop Footer Component Updates is priority Critical with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0116 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Schedule / Delivery Risk | Design and Develop Category Page Template may not start or complete on plan | Design and Develop Category Page Template is a High priority item with status 'Not Started'. This creates delivery risk for Design Systems / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0117 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Confidence Risk | Design and Develop Category Page Template has low-confidence delivery commitment | Design and Develop Category Page Template is priority High with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | High | High | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0118 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Schedule / Delivery Risk | Design and Develop Product Detail Page Template may not start or complete on plan | Design and Develop Product Detail Page Template is a High priority item with status 'Not Started'. This creates delivery risk for Design Systems / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0119 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Confidence Risk | Design and Develop Product Detail Page Template has low-confidence delivery commitment | Design and Develop Product Detail Page Template is priority High with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | High | High | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0120 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Schedule / Delivery Risk | Design and Develop Article Page Template may not start or complete on plan | Design and Develop Article Page Template is a High priority item with status 'Not Started'. This creates delivery risk for Design Systems / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0121 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Confidence Risk | Design and Develop Article Page Template has low-confidence delivery commitment | Design and Develop Article Page Template is priority High with only 50% confidence. This creates commitment risk for Design Systems / Public Web / All / All / All, especially where dates are already present in the roadmap. | High | High | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0122 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Data Quality Risk | Design and Develop Landing page template has source data calculation risk | The source effort value for Design and Develop Landing page template contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0123 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Data Quality Risk | Design and Develop Section page template has source data calculation risk | The source effort value for Design and Develop Section page template contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0124 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Data Quality Risk | Design and Develop Utility Template: Contact Us has source data calculation risk | The source effort value for Design and Develop Utility Template: Contact Us contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0125 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Data Quality Risk | Design and Develop Utility Template: All Calculators has source data calculation risk | The source effort value for Design and Develop Utility Template: All Calculators contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0126 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Data Quality Risk | Design and Develop Utility Template: Calculators Page has source data calculation risk | The source effort value for Design and Develop Utility Template: Calculators Page contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0127 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Data Quality Risk | Design and Develop Utility Templates: About Us has source data calculation risk | The source effort value for Design and Develop Utility Templates: About Us contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0128 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Data Quality Risk | Design and Develop Utility Template: Careers has source data calculation risk | The source effort value for Design and Develop Utility Template: Careers contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0129 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Data Quality Risk | Add copy standards to OMDS has source data calculation risk | The source effort value for Add copy standards to OMDS contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0130 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Data Quality Risk | Add copy standards to OMDS has source data calculation risk | The source effort value for Add copy standards to OMDS contained an invalid formula or value error. This creates data quality risk for Design Systems / Secure Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | Not Started | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0131 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Data Quality Risk | Design and Develop tenant template has source data calculation risk | The source effort value for Design and Develop tenant template contained an invalid formula or value error. This creates data quality risk for Design Systems / Public Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | TBC | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0132 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Data Quality Risk | Design and Develop tenant template has source data calculation risk | The source effort value for Design and Develop tenant template contained an invalid formula or value error. This creates data quality risk for Design Systems / Secure Web / All / All / All and may corrupt planning outputs if loaded unchanged. | Medium | Medium | TBC | 50 | Correct the effort value in the source workbook and reload. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
RSK-0133 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Blocker Risk | Implement OMCOM into production is at risk due to paused, blocked, or awaiting state | The source data indicates that Implement OMCOM into production is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Public Web / OMCOM / All / OM. Evidence: Awaiting stakeholder approval. | High | High | In Progress | 70 | Escalate the blocker and agree a recovery action. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
RSK-0134 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Approval Risk | Implement OMCOM into production has approval-gate risk | The source data shows that Implement OMCOM into production depends on approval or sign-off. Late approval could delay downstream delivery for Execution / Public Web / OMCOM / All / OM. Evidence: Stakeholder sign off. | High | High | In Progress | 70 | Book approval session and define approval criteria. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
RSK-0135 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Accountability Risk | Implement OMCOM into production has accountability risk | Implement OMCOM into production is priority High but has no named owner. This creates accountability risk for Execution / Public Web / OMCOM / All / OM. | High | High | In Progress | 70 | Assign a named owner before plan baseline. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
RSK-0136 | PRG-0103 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Co-locating Content & Analytics Tagging | Schedule / Delivery Risk | Dev: Co-locating Content & Analytics Tagging may not start or complete on plan | Dev: Co-locating Content & Analytics Tagging is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 90 | Confirm start readiness, blockers, and escalation path. | Execution | 5 | Execution row 5 ¦ task='Dev: Co-locating Content & Analytics Tagging' ¦ priority=Critical ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Creating new content_types and updating existing content_types in ContentStack'
RSK-0137 | PRG-0103 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Co-locating Content & Analytics Tagging | Accountability Risk | Dev: Co-locating Content & Analytics Tagging has accountability risk | Dev: Co-locating Content & Analytics Tagging is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 90 | Assign a named owner before plan baseline. | Execution | 5 | Execution row 5 ¦ task='Dev: Co-locating Content & Analytics Tagging' ¦ priority=Critical ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Creating new content_types and updating existing content_types in ContentStack'
RSK-0138 | PRG-0104 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Applying Analytics Tracking to V2 Components | Schedule / Delivery Risk | Dev: Applying Analytics Tracking to V2 Components may not start or complete on plan | Dev: Applying Analytics Tracking to V2 Components is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 6 | Execution row 6 ¦ task='Dev: Applying Analytics Tracking to V2 Components' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No ¦ comment='Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable)'
RSK-0139 | PRG-0104 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Applying Analytics Tracking to V2 Components | Accountability Risk | Dev: Applying Analytics Tracking to V2 Components has accountability risk | Dev: Applying Analytics Tracking to V2 Components is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 6 | Execution row 6 ¦ task='Dev: Applying Analytics Tracking to V2 Components' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No ¦ comment='Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable)'
RSK-0140 | PRG-0105 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Schedule / Delivery Risk | Dev: DevOps Quality Gate Pipeline may not start or complete on plan | Dev: DevOps Quality Gate Pipeline is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 7 | Execution row 7 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0141 | PRG-0105 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Accountability Risk | Dev: DevOps Quality Gate Pipeline has accountability risk | Dev: DevOps Quality Gate Pipeline is priority High but has no named owner. This creates accountability risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 7 | Execution row 7 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0142 | PRG-0106 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Schedule / Delivery Risk | Dev: DevOps Quality Gate Pipeline may not start or complete on plan | Dev: DevOps Quality Gate Pipeline is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 8 | Execution row 8 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0143 | PRG-0106 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Accountability Risk | Dev: DevOps Quality Gate Pipeline has accountability risk | Dev: DevOps Quality Gate Pipeline is priority High but has no named owner. This creates accountability risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 8 | Execution row 8 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0144 | PRG-0107 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Schedule / Delivery Risk | QE: Automated Testing Framework may not start or complete on plan | QE: Automated Testing Framework is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 9 | Execution row 9 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0145 | PRG-0107 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Accountability Risk | QE: Automated Testing Framework has accountability risk | QE: Automated Testing Framework is priority High but has no named owner. This creates accountability risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 9 | Execution row 9 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0146 | PRG-0108 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Schedule / Delivery Risk | Dev/QE: DevOps - Integrate Automated Testing may not start or complete on plan | Dev/QE: DevOps - Integrate Automated Testing is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 60 | Confirm start readiness, blockers, and escalation path. | Execution | 10 | Execution row 10 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0147 | PRG-0108 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Accountability Risk | Dev/QE: DevOps - Integrate Automated Testing has accountability risk | Dev/QE: DevOps - Integrate Automated Testing is priority High but has no named owner. This creates accountability risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Assign a named owner before plan baseline. | Execution | 10 | Execution row 10 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0148 | PRG-0109 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Schedule / Delivery Risk | QE: Automated Testing Framework may not start or complete on plan | QE: Automated Testing Framework is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 11 | Execution row 11 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0149 | PRG-0109 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Accountability Risk | QE: Automated Testing Framework has accountability risk | QE: Automated Testing Framework is priority High but has no named owner. This creates accountability risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 11 | Execution row 11 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0150 | PRG-0110 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Schedule / Delivery Risk | Dev/QE: DevOps - Integrate Automated Testing may not start or complete on plan | Dev/QE: DevOps - Integrate Automated Testing is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 60 | Confirm start readiness, blockers, and escalation path. | Execution | 12 | Execution row 12 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0151 | PRG-0110 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Accountability Risk | Dev/QE: DevOps - Integrate Automated Testing has accountability risk | Dev/QE: DevOps - Integrate Automated Testing is priority High but has no named owner. This creates accountability risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Assign a named owner before plan baseline. | Execution | 12 | Execution row 12 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0152 | PRG-0111 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Schedule / Delivery Risk | Dev: Observability Dashboard Templates for Sites may not start or complete on plan | Dev: Observability Dashboard Templates for Sites is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 13 | Execution row 13 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0153 | PRG-0111 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Accountability Risk | Dev: Observability Dashboard Templates for Sites has accountability risk | Dev: Observability Dashboard Templates for Sites is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 13 | Execution row 13 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
RSK-0154 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Schedule / Delivery Risk | Dev: Observability Dashboard Templates for Sites may not start or complete on plan | Dev: Observability Dashboard Templates for Sites is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
RSK-0155 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Blocker Risk | Dev: Observability Dashboard Templates for Sites is at risk due to paused, blocked, or awaiting state | The source data indicates that Dev: Observability Dashboard Templates for Sites is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. Evidence: Awaiting update to current V2 DesignSystem to allow for different background color. | Critical | Critical | Not Started | 70 | Escalate the blocker and agree a recovery action. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
RSK-0156 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Accountability Risk | Dev: Observability Dashboard Templates for Sites has accountability risk | Dev: Observability Dashboard Templates for Sites is priority Critical but has no named owner. This creates accountability risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named owner before plan baseline. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
RSK-0157 | PRG-0113 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Schedule / Delivery Risk | Dev: Styling Backwards Compatibility - V2 ModularPage may not start or complete on plan | Dev: Styling Backwards Compatibility - V2 ModularPage is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / All / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 80 | Confirm start readiness, blockers, and escalation path. | Execution | 18 | Execution row 18 ¦ task='Dev: Styling Backwards Compatibility - V2 ModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
RSK-0158 | PRG-0113 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Accountability Risk | Dev: Styling Backwards Compatibility - V2 ModularPage has accountability risk | Dev: Styling Backwards Compatibility - V2 ModularPage is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named owner before plan baseline. | Execution | 18 | Execution row 18 ¦ task='Dev: Styling Backwards Compatibility - V2 ModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
RSK-0159 | PRG-0114 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Schedule / Delivery Risk | Dev: Styling Backwards Compatibility - V2 ArticleModularPage may not start or complete on plan | Dev: Styling Backwards Compatibility - V2 ArticleModularPage is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / All / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 80 | Confirm start readiness, blockers, and escalation path. | Execution | 19 | Execution row 19 ¦ task='Dev: Styling Backwards Compatibility - V2 ArticleModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
RSK-0160 | PRG-0114 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Accountability Risk | Dev: Styling Backwards Compatibility - V2 ArticleModularPage has accountability risk | Dev: Styling Backwards Compatibility - V2 ArticleModularPage is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named owner before plan baseline. | Execution | 19 | Execution row 19 ¦ task='Dev: Styling Backwards Compatibility - V2 ArticleModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
RSK-0161 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Schedule / Delivery Risk | Dev: Export Analytics Data into Tableau may not start or complete on plan | Dev: Export Analytics Data into Tableau is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / All / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0162 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Confidence Risk | Dev: Export Analytics Data into Tableau has low-confidence delivery commitment | Dev: Export Analytics Data into Tableau is priority Critical with only 40% confidence. This creates commitment risk for Execution / Public Web / All / All / Shared / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0163 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Accountability Risk | Dev: Export Analytics Data into Tableau has accountability risk | Dev: Export Analytics Data into Tableau is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named owner before plan baseline. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0164 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Schedule / Delivery Risk | Dev: Export Analytics Data into Tableau may not start or complete on plan | Dev: Export Analytics Data into Tableau is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0165 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Confidence Risk | Dev: Export Analytics Data into Tableau has low-confidence delivery commitment | Dev: Export Analytics Data into Tableau is priority Critical with only 40% confidence. This creates commitment risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0166 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Accountability Risk | Dev: Export Analytics Data into Tableau has accountability risk | Dev: Export Analytics Data into Tableau is priority Critical but has no named owner. This creates accountability risk for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named owner before plan baseline. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
RSK-0167 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Schedule / Delivery Risk | Dev: Configuring Web Transformation Page Template in ContentStack may not start or complete on plan | Dev: Configuring Web Transformation Page Template in ContentStack is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Entire Site / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 80 | Confirm start readiness, blockers, and escalation path. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
RSK-0168 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Accountability Risk | Dev: Configuring Web Transformation Page Template in ContentStack has accountability risk | Dev: Configuring Web Transformation Page Template in ContentStack is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named owner before plan baseline. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
RSK-0169 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Schedule / Delivery Risk | Dev: Update Page Rendering Pipeline to support WT pages may not start or complete on plan | Dev: Update Page Rendering Pipeline to support WT pages is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Entire Site / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 80 | Confirm start readiness, blockers, and escalation path. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
RSK-0170 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Accountability Risk | Dev: Update Page Rendering Pipeline to support WT pages has accountability risk | Dev: Update Page Rendering Pipeline to support WT pages is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named owner before plan baseline. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
RSK-0171 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Schedule / Delivery Risk | Dev: Navigation components updates public Web may not start or complete on plan | Dev: Navigation components updates public Web is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / All / Shared / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
RSK-0172 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Roadmap Planning Risk | Dev: Navigation components updates public Web has roadmap uncertainty due to TBC schedule or effort | Dev: Navigation components updates public Web is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / All / Shared / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 40 | Resolve TBC dates and effort before baseline planning. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
RSK-0173 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Confidence Risk | Dev: Navigation components updates public Web has low-confidence delivery commitment | Dev: Navigation components updates public Web is priority Critical with only 40% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / All / Shared / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
RSK-0174 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Blocker Risk | Dev: Navigation components updates public Web is at risk due to paused, blocked, or awaiting state | The source data indicates that Dev: Navigation components updates public Web is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Public Web / OMCOZA / All / Shared / All / TBC. Evidence: Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component. | Critical | Critical | Not Started | 40 | Escalate the blocker and agree a recovery action. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
RSK-0175 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Accountability Risk | Dev: Navigation components updates public Web has accountability risk | Dev: Navigation components updates public Web is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named owner before plan baseline. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
RSK-0176 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Schedule / Delivery Risk | QE : Automated Testing Framework (LS) may not start or complete on plan | QE : Automated Testing Framework (LS) is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 60 | Confirm start readiness, blockers, and escalation path. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0177 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Roadmap Planning Risk | QE : Automated Testing Framework (LS) has roadmap uncertainty due to TBC schedule or effort | QE : Automated Testing Framework (LS) is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 60 | Resolve TBC dates and effort before baseline planning. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0178 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Accountability Risk | QE : Automated Testing Framework (LS) has accountability risk | QE : Automated Testing Framework (LS) is priority High but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 60 | Assign a named owner before plan baseline. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
RSK-0179 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Schedule / Delivery Risk | Dev :Observability Dashboards for various sites (LS) may not start or complete on plan | Dev :Observability Dashboards for various sites (LS) is a High priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0180 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Confidence Risk | Dev :Observability Dashboards for various sites (LS) has low-confidence delivery commitment | Dev :Observability Dashboards for various sites (LS) is priority High with only 50% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0181 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Accountability Risk | Dev :Observability Dashboards for various sites (LS) has accountability risk | Dev :Observability Dashboards for various sites (LS) is priority High but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 50 | Assign a named owner before plan baseline. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0182 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Schedule / Delivery Risk | Dev : Modular Template (LS) may not start or complete on plan | Dev : Modular Template (LS) is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
RSK-0183 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Roadmap Planning Risk | Dev : Modular Template (LS) has roadmap uncertainty due to TBC schedule or effort | Dev : Modular Template (LS) is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 50 | Resolve TBC dates and effort before baseline planning. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
RSK-0184 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Confidence Risk | Dev : Modular Template (LS) has low-confidence delivery commitment | Dev : Modular Template (LS) is priority Critical with only 50% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
RSK-0185 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Blocker Risk | Dev : Modular Template (LS) is at risk due to paused, blocked, or awaiting state | The source data indicates that Dev : Modular Template (LS) is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC. Evidence: Awaiting Page Template drop. | Critical | Critical | Not Started | 50 | Escalate the blocker and agree a recovery action. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
RSK-0186 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Accountability Risk | Dev : Modular Template (LS) has accountability risk | Dev : Modular Template (LS) is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Assign a named owner before plan baseline. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
RSK-0187 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Schedule / Delivery Risk | Dev : Modular Page Components (LS) may not start or complete on plan | Dev : Modular Page Components (LS) is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0188 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Roadmap Planning Risk | Dev : Modular Page Components (LS) has roadmap uncertainty due to TBC schedule or effort | Dev : Modular Page Components (LS) is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 40 | Resolve TBC dates and effort before baseline planning. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0189 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Confidence Risk | Dev : Modular Page Components (LS) has low-confidence delivery commitment | Dev : Modular Page Components (LS) is priority Critical with only 40% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0190 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Blocker Risk | Dev : Modular Page Components (LS) is at risk due to paused, blocked, or awaiting state | The source data indicates that Dev : Modular Page Components (LS) is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC. Evidence: Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. | Critical | Critical | Not Started | 40 | Escalate the blocker and agree a recovery action. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0191 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Accountability Risk | Dev : Modular Page Components (LS) has accountability risk | Dev : Modular Page Components (LS) is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named owner before plan baseline. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0192 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Schedule / Delivery Risk | Dev Applying analytics tracking to CMS (LS) may not start or complete on plan | Dev Applying analytics tracking to CMS (LS) is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0193 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Roadmap Planning Risk | Dev Applying analytics tracking to CMS (LS) has roadmap uncertainty due to TBC schedule or effort | Dev Applying analytics tracking to CMS (LS) is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 40 | Resolve TBC dates and effort before baseline planning. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0194 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Confidence Risk | Dev Applying analytics tracking to CMS (LS) has low-confidence delivery commitment | Dev Applying analytics tracking to CMS (LS) is priority Critical with only 40% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0195 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Blocker Risk | Dev Applying analytics tracking to CMS (LS) is at risk due to paused, blocked, or awaiting state | The source data indicates that Dev Applying analytics tracking to CMS (LS) is paused, blocked, or awaiting an upstream input. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC. Evidence: Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown. | Critical | Critical | Not Started | 40 | Escalate the blocker and agree a recovery action. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0196 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Accountability Risk | Dev Applying analytics tracking to CMS (LS) has accountability risk | Dev Applying analytics tracking to CMS (LS) is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named owner before plan baseline. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
RSK-0197 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Schedule / Delivery Risk | Dev: OMCOZA -Licence cutover may not start or complete on plan | Dev: OMCOZA -Licence cutover is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 60 | Confirm start readiness, blockers, and escalation path. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
RSK-0198 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Roadmap Planning Risk | Dev: OMCOZA -Licence cutover has roadmap uncertainty due to TBC schedule or effort | Dev: OMCOZA -Licence cutover is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 60 | Resolve TBC dates and effort before baseline planning. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
RSK-0199 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Accountability Risk | Dev: OMCOZA -Licence cutover has accountability risk | Dev: OMCOZA -Licence cutover is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 60 | Assign a named owner before plan baseline. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
RSK-0200 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Schedule / Delivery Risk | Dev : Tableau Analytics may not start or complete on plan | Dev : Tableau Analytics is a Critical priority item with status 'Not Started'. This creates delivery risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | Critical | Critical | Not Started | 50 | Confirm start readiness, blockers, and escalation path. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0201 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Roadmap Planning Risk | Dev : Tableau Analytics has roadmap uncertainty due to TBC schedule or effort | Dev : Tableau Analytics is priority Critical but has TBC or incomplete schedule/effort information. This creates roadmap risk for Execution / Public Web / OMCOZA / Personal / All / TBC because the item cannot be sequenced or capacity-planned reliably. | Critical | Critical | Not Started | 50 | Resolve TBC dates and effort before baseline planning. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0202 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Confidence Risk | Dev : Tableau Analytics has low-confidence delivery commitment | Dev : Tableau Analytics is priority Critical with only 50% confidence. This creates commitment risk for Execution / Public Web / OMCOZA / Personal / All / TBC, especially where dates are already present in the roadmap. | Critical | Critical | Not Started | 50 | Pressure-test assumptions and update date, scope, or resource plan. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0203 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Accountability Risk | Dev : Tableau Analytics has accountability risk | Dev : Tableau Analytics is priority Critical but has no named owner. This creates accountability risk for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Assign a named owner before plan baseline. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
RSK-0204 | PRG-0128 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Testing in V2 new platform and log bugs | Schedule / Delivery Risk | Testing in V2 new platform and log bugs may not start or complete on plan | Testing in V2 new platform and log bugs is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 100 | Confirm start readiness, blockers, and escalation path. | Publishing | 5 | Publishing row 5 ¦ task='Testing in V2 new platform and log bugs' ¦ priority=High ¦ status=Not Started ¦ confidence=100% ¦ upstream=No ¦ comment='Need to work with Web developers for bug fixes'
RSK-0205 | PRG-0128 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Testing in V2 new platform and log bugs | Testing / Quality Risk | Testing in V2 new platform and log bugs has testing or defect-resolution risk | The source notes indicate testing or bug fixing is still required for Testing in V2 new platform and log bugs. This creates readiness risk for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. Evidence: Need to work with Web developers for bug fixes. | High | High | Not Started | 100 | Track defects, confirm owners, and define exit criteria. | Publishing | 5 | Publishing row 5 ¦ task='Testing in V2 new platform and log bugs' ¦ priority=High ¦ status=Not Started ¦ confidence=100% ¦ upstream=No ¦ comment='Need to work with Web developers for bug fixes'
RSK-0206 | PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Roadmap Planning Risk | Take live in V2 new platform has roadmap uncertainty due to TBC schedule or effort | Take live in V2 new platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC because the item cannot be sequenced or capacity-planned reliably. | High | High | N/A | 80 | Resolve TBC dates and effort before baseline planning. | Publishing | 6 | Publishing row 6 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No ¦ comment='Go live date will be determined in the next PI Planning'
RSK-0207 | PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Data Quality Risk | Take live in V2 new platform has source data calculation risk | The source effort value for Take live in V2 new platform contained an invalid formula or value error. This creates data quality risk for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC and may corrupt planning outputs if loaded unchanged. | High | High | N/A | 80 | Correct the effort value in the source workbook and reload. | Publishing | 6 | Publishing row 6 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No ¦ comment='Go live date will be determined in the next PI Planning'
RSK-0208 | PRG-0130 | Publishing | Bernice | Public Web | OMCOZA | Personal | Funeral |  | Record Funeral URL structure based on proposed sunset/consolidated pages. | Schedule / Delivery Risk | Record Funeral URL structure based on proposed sunset/consolidated pages. may not start or complete on plan | Record Funeral URL structure based on proposed sunset/consolidated pages. is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Personal / Funeral, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 90 | Confirm start readiness, blockers, and escalation path. | Publishing | 7 | Publishing row 7 ¦ task='Record Funeral URL structure based on proposed sunset/consolidated pages.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
RSK-0209 | PRG-0131 | Publishing | Bernice | Public Web | OMCOZA | Personal | Retirement |  | Record Retirement URL structure based on consolidated pages as per new IA. | Schedule / Delivery Risk | Record Retirement URL structure based on consolidated pages as per new IA. may not start or complete on plan | Record Retirement URL structure based on consolidated pages as per new IA. is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Personal / Retirement, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 90 | Confirm start readiness, blockers, and escalation path. | Publishing | 8 | Publishing row 8 ¦ task='Record Retirement URL structure based on consolidated pages as per new IA.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
RSK-0210 | PRG-0132 | Publishing | Bernice | Public Web | OMCOZA | Personal | Flexi Save |  | Record Flexi Save URL structure based on consolidated pages as per new IA. | Schedule / Delivery Risk | Record Flexi Save URL structure based on consolidated pages as per new IA. may not start or complete on plan | Record Flexi Save URL structure based on consolidated pages as per new IA. is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Personal / Flexi Save, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 90 | Confirm start readiness, blockers, and escalation path. | Publishing | 9 | Publishing row 9 ¦ task='Record Flexi Save URL structure based on consolidated pages as per new IA.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
RSK-0211 | PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure based on all as-is pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure based on all as-is pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / as-is pages / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 10 | Publishing row 10 ¦ task='Record URL structure based on all as-is pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0212 | PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining Personal pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining Personal pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 12 | Publishing row 12 ¦ task='Record URL structure for all remaining Personal pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0213 | PRG-0136 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Personal / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 13 | Publishing row 13 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0214 | PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Corporate / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 14 | Publishing row 14 ¦ task='Record URL structure for all remaining Corporate pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0215 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Corporate / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 40 | Confirm start readiness, blockers, and escalation path. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0216 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 40% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / Corporate / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 40 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0217 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Wealth / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0218 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 30% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / Wealth / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0219 | PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining Utility pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining Utility pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Utility pages / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 17 | Publishing row 17 ¦ task='Record URL structure for all remaining Utility pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0220 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Utility pages / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0221 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 30% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / Utility pages / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0222 | PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining About us pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining About us pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / About Us / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 19 | Publishing row 19 ¦ task='Record URL structure for all remaining About us pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0223 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / About Us / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0224 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 30% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / About Us / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0225 | PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining Careers pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining Careers pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Careers / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 21 | Publishing row 21 ¦ task='Record URL structure for all remaining Careers pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0226 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Careers / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0227 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 30% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / Careers / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0228 | PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Schedule / Delivery Risk | Record URL structure for all remaining Business pages (keep/remove/consolidate) may not start or complete on plan | Record URL structure for all remaining Business pages (keep/remove/consolidate) is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Business / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 70 | Confirm start readiness, blockers, and escalation path. | Publishing | 23 | Publishing row 23 ¦ task='Record URL structure for all remaining Business pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
RSK-0229 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Schedule / Delivery Risk | Start building new template pages may not start or complete on plan | Start building new template pages is a High priority item with status 'Not Started'. This creates delivery risk for Publishing / Public Web / OMCOZA / Business / All / TBC, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 30 | Confirm start readiness, blockers, and escalation path. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0230 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Confidence Risk | Start building new template pages has low-confidence delivery commitment | Start building new template pages is priority High with only 30% confidence. This creates commitment risk for Publishing / Public Web / OMCOZA / Business / All / TBC, especially where dates are already present in the roadmap. | High | High | Not Started | 30 | Pressure-test assumptions and update date, scope, or resource plan. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
RSK-0231 | PRG-0154 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Penetration Testing Discussion and confirmation | Accountability Risk | Penetration Testing Discussion and confirmation has accountability risk | Penetration Testing Discussion and confirmation is priority High but has no named owner. This creates accountability risk for Go-Live Readiness / Public Web / All / All / All. | High | High | Complete | 100 | Assign a named owner before plan baseline. | Go-Live Readiness | 4 | Go-Live Readiness row 4 ¦ task='Penetration Testing Discussion and confirmation' ¦ priority=High ¦ status=Complete ¦ confidence=100% ¦ upstream=No ¦ comment='Penetration Testing has to be done, at no cost to us, we just have to send URL' for testing - URL of sites must be sent Security Team'
RSK-0232 | PRG-0155 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Quality Assurance Approval | Approval Risk | Quality Assurance Approval has approval-gate risk | The source data shows that Quality Assurance Approval depends on approval or sign-off. Late approval could delay downstream delivery for Go-Live Readiness / Public Web / All / All / All. Evidence:. | Medium | Low | Not Started | 100 | Book approval session and define approval criteria. | Go-Live Readiness | 5 | Go-Live Readiness row 5 ¦ task='Quality Assurance Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
RSK-0233 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Approval Risk | Security Approvals has approval-gate risk | The source data shows that Security Approvals depends on approval or sign-off. Late approval could delay downstream delivery for Go-Live Readiness / Public Web / All / All / All. Evidence: All deliveries must be in QA State. | Medium | Low | TBC | 100 | Book approval session and define approval criteria. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
RSK-0234 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Approval Risk | Executive Approval has approval-gate risk | The source data shows that Executive Approval depends on approval or sign-off. Late approval could delay downstream delivery for Go-Live Readiness / Public Web / All / All / All. Evidence: Approval to go ahead from all other Teams. | Medium | Low | Not Started | 50 | Book approval session and define approval criteria. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
RSK-0235 | PRG-0160 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Change Management Go Ahead | Approval Risk | Change Management Go Ahead has approval-gate risk | The source data shows that Change Management Go Ahead depends on approval or sign-off. Late approval could delay downstream delivery for Go-Live Readiness / Public Web / All / All / All. Evidence: All work by teams must be completed. | Medium | Low | Not Started | 50 | Book approval session and define approval criteria. | Go-Live Readiness | 10 | Go-Live Readiness row 10 ¦ task='Change Management Go Ahead' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='All work by teams must be completed'
RSK-0236 | PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Approval Risk | Confirm Engagement Cycle with SEO Team has approval-gate risk | The source data shows that Confirm Engagement Cycle with SEO Team depends on approval or sign-off. Late approval could delay downstream delivery for SEO / Analytics / Public Web / All / All / All. Evidence: Final Approval will be provided by the CMO. | High | High | In Progress | 100 | Book approval session and define approval criteria. | SEO Analytics | 4 | SEO Analytics row 4 ¦ task='Confirm Engagement Cycle with SEO Team' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=No ¦ comment='Final Approval will be provided by the CMO'
RSK-0237 | PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Accountability Risk | Confirm Engagement Cycle with SEO Team has accountability risk | Confirm Engagement Cycle with SEO Team is priority High but has no named owner. This creates accountability risk for SEO / Analytics / Public Web / All / All / All. | High | High | In Progress | 100 | Assign a named owner before plan baseline. | SEO Analytics | 4 | SEO Analytics row 4 ¦ task='Confirm Engagement Cycle with SEO Team' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=No ¦ comment='Final Approval will be provided by the CMO'
RSK-0238 | PRG-0163 | SEO / Analytics | TBC | Public Web | All | All | All |  | SEO Requirements to Dev Team | Schedule / Delivery Risk | SEO Requirements to Dev Team may not start or complete on plan | SEO Requirements to Dev Team is a High priority item with status 'TBC'. This creates delivery risk for SEO / Analytics / Public Web / All / All / All, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | TBC | 100 | Confirm start readiness, blockers, and escalation path. | SEO Analytics | 5 | SEO Analytics row 5 ¦ task='SEO Requirements to Dev Team' ¦ priority=High ¦ status=TBC ¦ confidence=100% ¦ upstream=No
RSK-0239 | PRG-0163 | SEO / Analytics | TBC | Public Web | All | All | All |  | SEO Requirements to Dev Team | Accountability Risk | SEO Requirements to Dev Team has accountability risk | SEO Requirements to Dev Team is priority High but has no named owner. This creates accountability risk for SEO / Analytics / Public Web / All / All / All. | High | High | TBC | 100 | Assign a named owner before plan baseline. | SEO Analytics | 5 | SEO Analytics row 5 ¦ task='SEO Requirements to Dev Team' ¦ priority=High ¦ status=TBC ¦ confidence=100% ¦ upstream=No
RSK-0240 | PRG-0164 | OMAR | TBC | Public Web | OMAR | OMAR | OMAR | OMAR / TBC | Engagement required to communicate recalibration of project to various OMAR Stakeholder | Accountability Risk | Engagement required to communicate recalibration of project to various OMAR Stakeholder has accountability risk | Engagement required to communicate recalibration of project to various OMAR Stakeholder is priority Critical but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / OMAR / OMAR. | Critical | Critical | In Progress | 70 | Assign a named owner before plan baseline. | OMAR | 4 | OMAR row 4 ¦ task='Engagement required to communicate recalibration of project to various OMAR Stakeholder' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=No ¦ dependency='Nothing , we need a clear communications plan for OMAR' ¦ comment='Engagement with OMAR teams are required in order to assist them with the recalibration of their plans, the plan must take into account Navigation and plan changes'
RSK-0241 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0242 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0243 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0244 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0245 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Ghana / Ghana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0246 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Ghana / Ghana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0247 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Ghana / Ghana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0248 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0249 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Kenya / Kenya, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0250 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Kenya / Kenya because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0251 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Kenya / Kenya, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0252 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0253 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0254 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Namibia / Namibia because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0255 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0256 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0257 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Rwanda / Rwanda, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0258 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Rwanda / Rwanda because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0259 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Rwanda / Rwanda, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0260 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0261 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Uganda / Uganda, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0262 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Uganda / Uganda because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0263 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Uganda / Uganda, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0264 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0265 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0266 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0267 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0268 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
RSK-0269 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Schedule / Delivery Risk | Publishing of all pages in V2 New platform may not start or complete on plan | Publishing of all pages in V2 New platform is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
RSK-0270 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Roadmap Planning Risk | Publishing of all pages in V2 New platform has roadmap uncertainty due to TBC schedule or effort | Publishing of all pages in V2 New platform is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Namibia / Namibia because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
RSK-0271 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Confidence Risk | Publishing of all pages in V2 New platform has low-confidence delivery commitment | Publishing of all pages in V2 New platform is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
RSK-0272 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Accountability Risk | Publishing of all pages in V2 New platform has accountability risk | Publishing of all pages in V2 New platform is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
RSK-0273 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Confidence Risk | Travel Insurance Sales Migration has low-confidence delivery commitment | Travel Insurance Sales Migration is priority High with only 40% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Ghana / Ghana, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0274 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Dependency Risk | Travel Insurance Sales Migration has an untracked dependency risk | The worksheet marks Travel Insurance Sales Migration as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Name the upstream deliverable, owner, and target completion date. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0275 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Accountability Risk | Travel Insurance Sales Migration has accountability risk | Travel Insurance Sales Migration is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Assign a named owner before plan baseline. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0276 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Confidence Risk | Mvest has low-confidence delivery commitment | Mvest is priority High with only 40% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Ghana / Ghana, especially where dates are already present in the roadmap. | High | High | In Progress | 40 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0277 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Dependency Risk | Mvest has an untracked dependency risk | The worksheet marks Mvest as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Name the upstream deliverable, owner, and target completion date. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0278 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Accountability Risk | Mvest has accountability risk | Mvest is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Assign a named owner before plan baseline. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
RSK-0279 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Confidence Risk | Personal Loan Application has low-confidence delivery commitment | Personal Loan Application is priority High with only 50% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially where dates are already present in the roadmap. | High | High | In Progress | 50 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0280 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Dependency Risk | Personal Loan Application has an untracked dependency risk | The worksheet marks Personal Loan Application as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Name the upstream deliverable, owner, and target completion date. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0281 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Accountability Risk | Personal Loan Application has accountability risk | Personal Loan Application is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Assign a named owner before plan baseline. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0282 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Confidence Risk | Personal Loan Repayment Calculator has low-confidence delivery commitment | Personal Loan Repayment Calculator is priority High with only 50% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Namibia / Namibia, especially where dates are already present in the roadmap. | High | High | In Progress | 50 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0283 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Dependency Risk | Personal Loan Repayment Calculator has an untracked dependency risk | The worksheet marks Personal Loan Repayment Calculator as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Name the upstream deliverable, owner, and target completion date. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0284 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Accountability Risk | Personal Loan Repayment Calculator has accountability risk | Personal Loan Repayment Calculator is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Assign a named owner before plan baseline. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
RSK-0285 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Schedule / Delivery Risk | Migration of Secure Web may not start or complete on plan | Migration of Secure Web is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Secure Web / OMAR / Namibia / Namibia, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
RSK-0286 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Roadmap Planning Risk | Migration of Secure Web has roadmap uncertainty due to TBC schedule or effort | Migration of Secure Web is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Secure Web / OMAR / Namibia / Namibia because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
RSK-0287 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Confidence Risk | Migration of Secure Web has low-confidence delivery commitment | Migration of Secure Web is priority High with only 10% confidence. This creates commitment risk for OMAR / Secure Web / OMAR / Namibia / Namibia, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
RSK-0288 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Resource Capacity Risk | Migration of Secure Web is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Migration of Secure Web. This creates capacity risk for OMAR / Secure Web / OMAR / Namibia / Namibia. Evidence: Resource constraints 2 people looking after 2 platforms. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
RSK-0289 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Accountability Risk | Migration of Secure Web has accountability risk | Migration of Secure Web is priority High but has no named owner. This creates accountability risk for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
RSK-0290 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Schedule / Delivery Risk | Service Transactions may not start or complete on plan | Service Transactions is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Secure Web / OMAR / Namibia / Namibia, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started |  | Confirm start readiness, blockers, and escalation path. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
RSK-0291 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Roadmap Planning Risk | Service Transactions has roadmap uncertainty due to TBC schedule or effort | Service Transactions is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Secure Web / OMAR / Namibia / Namibia because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started |  | Resolve TBC dates and effort before baseline planning. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
RSK-0292 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Dependency Risk | Service Transactions has an untracked dependency risk | The worksheet marks Service Transactions as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Name the upstream deliverable, owner, and target completion date. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
RSK-0293 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Accountability Risk | Service Transactions has accountability risk | Service Transactions is priority High but has no named owner. This creates accountability risk for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Assign a named owner before plan baseline. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
RSK-0294 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Roadmap Planning Risk | Eswatini Funeral has roadmap uncertainty due to TBC schedule or effort | Eswatini Funeral is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / eSwatini / eSwatini because the item cannot be sequenced or capacity-planned reliably. | High | High | In Progress | 70 | Resolve TBC dates and effort before baseline planning. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
RSK-0295 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Dependency Risk | Eswatini Funeral has an untracked dependency risk | The worksheet marks Eswatini Funeral as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Name the upstream deliverable, owner, and target completion date. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
RSK-0296 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Testing / Quality Risk | Eswatini Funeral has testing or defect-resolution risk | The source notes indicate testing or bug fixing is still required for Eswatini Funeral. This creates readiness risk for OMAR / Public Web / OMAR / eSwatini / eSwatini. Evidence: testing in progress. | High | High | In Progress | 70 | Track defects, confirm owners, and define exit criteria. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
RSK-0297 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Accountability Risk | Eswatini Funeral has accountability risk | Eswatini Funeral is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Assign a named owner before plan baseline. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
RSK-0298 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Roadmap Planning Risk | Funeral Claims - Servicing Journey has roadmap uncertainty due to TBC schedule or effort | Funeral Claims - Servicing Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | In Progress | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0299 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Confidence Risk | Funeral Claims - Servicing Journey has low-confidence delivery commitment | Funeral Claims - Servicing Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | In Progress | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0300 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Dependency Risk | Funeral Claims - Servicing Journey has an untracked dependency risk | The worksheet marks Funeral Claims - Servicing Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0301 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Resource Capacity Risk | Funeral Claims - Servicing Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Funeral Claims - Servicing Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | In Progress | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0302 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Accountability Risk | Funeral Claims - Servicing Journey has accountability risk | Funeral Claims - Servicing Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Assign a named owner before plan baseline. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0303 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Roadmap Planning Risk | Motor claims - Service Journey has roadmap uncertainty due to TBC schedule or effort | Motor claims - Service Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | In Progress | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0304 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Confidence Risk | Motor claims - Service Journey has low-confidence delivery commitment | Motor claims - Service Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | In Progress | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0305 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Dependency Risk | Motor claims - Service Journey has an untracked dependency risk | The worksheet marks Motor claims - Service Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0306 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Resource Capacity Risk | Motor claims - Service Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Motor claims - Service Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | In Progress | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0307 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Accountability Risk | Motor claims - Service Journey has accountability risk | Motor claims - Service Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Assign a named owner before plan baseline. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0308 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Schedule / Delivery Risk | Home owners claims- Service Journey may not start or complete on plan | Home owners claims- Service Journey is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0309 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Roadmap Planning Risk | Home owners claims- Service Journey has roadmap uncertainty due to TBC schedule or effort | Home owners claims- Service Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0310 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Confidence Risk | Home owners claims- Service Journey has low-confidence delivery commitment | Home owners claims- Service Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0311 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Dependency Risk | Home owners claims- Service Journey has an untracked dependency risk | The worksheet marks Home owners claims- Service Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0312 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Resource Capacity Risk | Home owners claims- Service Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Home owners claims- Service Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0313 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Accountability Risk | Home owners claims- Service Journey has accountability risk | Home owners claims- Service Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0314 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Schedule / Delivery Risk | Home content claims Service Journey may not start or complete on plan | Home content claims Service Journey is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0315 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Roadmap Planning Risk | Home content claims Service Journey has roadmap uncertainty due to TBC schedule or effort | Home content claims Service Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0316 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Confidence Risk | Home content claims Service Journey has low-confidence delivery commitment | Home content claims Service Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0317 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Dependency Risk | Home content claims Service Journey has an untracked dependency risk | The worksheet marks Home content claims Service Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0318 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Resource Capacity Risk | Home content claims Service Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Home content claims Service Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0319 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Accountability Risk | Home content claims Service Journey has accountability risk | Home content claims Service Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0320 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Schedule / Delivery Risk | Credit Life may not start or complete on plan | Credit Life is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0321 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Roadmap Planning Risk | Credit Life has roadmap uncertainty due to TBC schedule or effort | Credit Life is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0322 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Confidence Risk | Credit Life has low-confidence delivery commitment | Credit Life is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0323 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Dependency Risk | Credit Life has an untracked dependency risk | The worksheet marks Credit Life as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0324 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Resource Capacity Risk | Credit Life is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Credit Life. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0325 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Accountability Risk | Credit Life has accountability risk | Credit Life is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0326 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Schedule / Delivery Risk | Funeral Claims - Sales Journey may not start or complete on plan | Funeral Claims - Sales Journey is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0327 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Roadmap Planning Risk | Funeral Claims - Sales Journey has roadmap uncertainty due to TBC schedule or effort | Funeral Claims - Sales Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0328 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Confidence Risk | Funeral Claims - Sales Journey has low-confidence delivery commitment | Funeral Claims - Sales Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0329 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Dependency Risk | Funeral Claims - Sales Journey has an untracked dependency risk | The worksheet marks Funeral Claims - Sales Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0330 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Resource Capacity Risk | Funeral Claims - Sales Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Funeral Claims - Sales Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0331 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Accountability Risk | Funeral Claims - Sales Journey has accountability risk | Funeral Claims - Sales Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0332 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Schedule / Delivery Risk | Motor claims - Sales Journey may not start or complete on plan | Motor claims - Sales Journey is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0333 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Roadmap Planning Risk | Motor claims - Sales Journey has roadmap uncertainty due to TBC schedule or effort | Motor claims - Sales Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0334 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Confidence Risk | Motor claims - Sales Journey has low-confidence delivery commitment | Motor claims - Sales Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0335 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Dependency Risk | Motor claims - Sales Journey has an untracked dependency risk | The worksheet marks Motor claims - Sales Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0336 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Resource Capacity Risk | Motor claims - Sales Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Motor claims - Sales Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0337 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Accountability Risk | Motor claims - Sales Journey has accountability risk | Motor claims - Sales Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0338 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Schedule / Delivery Risk | Home owners claims- Sales Journey may not start or complete on plan | Home owners claims- Sales Journey is a High priority item with status 'Not Started'. This creates delivery risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially if dependencies, approvals, or schedule gaps remain unresolved. | High | High | Not Started | 10 | Confirm start readiness, blockers, and escalation path. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0339 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Roadmap Planning Risk | Home owners claims- Sales Journey has roadmap uncertainty due to TBC schedule or effort | Home owners claims- Sales Journey is priority High but has TBC or incomplete schedule/effort information. This creates roadmap risk for OMAR / Public Web / OMAR / Botswana / Botswana because the item cannot be sequenced or capacity-planned reliably. | High | High | Not Started | 10 | Resolve TBC dates and effort before baseline planning. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0340 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Confidence Risk | Home owners claims- Sales Journey has low-confidence delivery commitment | Home owners claims- Sales Journey is priority High with only 10% confidence. This creates commitment risk for OMAR / Public Web / OMAR / Botswana / Botswana, especially where dates are already present in the roadmap. | High | High | Not Started | 10 | Pressure-test assumptions and update date, scope, or resource plan. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0341 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Dependency Risk | Home owners claims- Sales Journey has an untracked dependency risk | The worksheet marks Home owners claims- Sales Journey as dependent on upstream work but does not identify the upstream deliverable. This creates untracked dependency risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Name the upstream deliverable, owner, and target completion date. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0342 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Resource Capacity Risk | Home owners claims- Sales Journey is at risk from resource capacity constraints | The source notes indicate shared or constrained resources for Home owners claims- Sales Journey. This creates capacity risk for OMAR / Public Web / OMAR / Botswana / Botswana. Evidence: Resources shared between Botswana and Eswatini. | High | High | Not Started | 10 | Review allocation and confirm whether the current resource pool can support the committed scope. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
RSK-0343 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Accountability Risk | Home owners claims- Sales Journey has accountability risk | Home owners claims- Sales Journey is priority High but has no named owner. This creates accountability risk for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named owner before plan baseline. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'

## UPLOAD_Constraints
Constraint_ID | Linked_Programme_Record_ID | Workstream | Owner | Channel | Domain | Area_Journey | Cluster | Market | Related_Deliverable | Constraint_Type | Title | Detailed_Description | Constraint_Severity | Priority | Status | Confidence_Percent | Required_Action | Source_Sheet | Source_Row | Source_Evidence
CON-0001 | PRG-0008 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: All Calculators | Confidence / Planning Constraint | Design Utility Template: All Calculators has low delivery confidence | The confidence level for Design Utility Template: All Calculators is 40%, which is low for roadmap commitment. This constrains predictability for Design Standards / Public Web / OMCOZA / Personal / Templates. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 11 | Design Standards row 11 ¦ task='Design Utility Template: All Calculators' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There is a lot of calculators that require a lot of input across different product and business clusters.' ¦ comment='The work has started for both desktop and mobile.'
CON-0002 | PRG-0009 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: Calculators Page | Confidence / Planning Constraint | Design Utility Template: Calculators Page has low delivery confidence | The confidence level for Design Utility Template: Calculators Page is 40%, which is low for roadmap commitment. This constrains predictability for Design Standards / Public Web / OMCOZA / Personal / Templates. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 12 | Design Standards row 12 ¦ task='Design Utility Template: Calculators Page' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.' ¦ comment='This work has started.'
CON-0003 | PRG-0010 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Tenant |  | Design Tenant Template | Technical Access / Data Constraint | Design Tenant Template is constrained by unresolved data/source access detail | The source notes indicate that Design Tenant Template requires clarity on data sources, destination, or access credentials. This constrains implementation for Design Standards / Public Web / OMCOZA / Entire Site / Tenant. | Medium | High | In Progress | 70 | Confirm source systems, destination, credentials, and responsible technical owner. | Design Standards | 13 | Design Standards row 13 ¦ task='Design Tenant Template' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards.'
CON-0004 | PRG-0012 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Template: Careers | Confidence / Planning Constraint | Design Utility Template: Careers has low delivery confidence | The confidence level for Design Utility Template: Careers is 40%, which is low for roadmap commitment. This constrains predictability for Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Medium | Medium | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 15 | Design Standards row 15 ¦ task='Design Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='This may require input from HC but if we are migrating the content as-is, then this could be a simple process.'
CON-0005 | PRG-0013 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation structure based on the IA | Confidence / Planning Constraint | Design navigation structure based on the IA has low delivery confidence | The confidence level for Design navigation structure based on the IA is 40%, which is low for roadmap commitment. This constrains predictability for Design Standards / Secure Web / MyOM / Entire Site / Navigation. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 16 | Design Standards row 16 ¦ task='Design navigation structure based on the IA' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Initial designs have been done, it requires further discussion of how the pieces need to fit.' ¦ comment='Initial designs has started.'
CON-0006 | PRG-0014 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation solution to allow access to other secure sites | Data Quality / Taxonomy Constraint | Design navigation solution to allow access to other secure sites has taxonomy or data-quality gaps | The item has data-quality flags: Upstream dependency marked yes but detail missing. This constrains clean ingestion and reporting for Design Standards / Secure Web / MyOM / Entire Site / Navigation. | High | High | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Standards | 17 | Design Standards row 17 ¦ task='Design navigation solution to allow access to other secure sites' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes
CON-0007 | PRG-0015 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise generic copy standards | Data Quality / Taxonomy Constraint | Finalise generic copy standards has taxonomy or data-quality gaps | The item has data-quality flags: Channel missing. This constrains clean ingestion and reporting for Design Standards / TBC / Old Mutual Design Standards / Generic / Copy. | Critical | Critical | Ready | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Standards | 18 | Design Standards row 18 ¦ task='Finalise generic copy standards' ¦ priority=Critical ¦ status=Ready ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='We are ready for sign off, it is aligned to brand and are requesting us to send to them for their records.'
CON-0008 | PRG-0016 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise SEO + AIEO standards | Data Quality / Taxonomy Constraint | Finalise SEO + AIEO standards has taxonomy or data-quality gaps | The item has data-quality flags: Channel missing. This constrains clean ingestion and reporting for Design Standards / TBC / Old Mutual Design Standards / Generic / Copy. | Critical | Critical | Ready | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Standards | 19 | Design Standards row 19 ¦ task='Finalise SEO + AIEO standards' ¦ priority=Critical ¦ status=Ready ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='SEO is also in progress with their own standards, so our standards will be a living process and document'
CON-0009 | PRG-0017 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | CI |  | Align DS to iterim Brand CI | Data Quality / Taxonomy Constraint | Align DS to iterim Brand CI has taxonomy or data-quality gaps | The item has data-quality flags: Channel missing. This constrains clean ingestion and reporting for Design Standards / TBC / Old Mutual Design Standards / Generic / CI. | High | High | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Standards | 20 | Design Standards row 20 ¦ task='Align DS to iterim Brand CI' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='The Interim Brand CI has been approved, luckily no major changes and just need align DS to brand.'
CON-0010 | PRG-0018 | Design Standards | Justin | Public Web | OMCOZA | OM Bank | Tenant |  | Design OM Bank Tenant site (structure) | Confidence / Planning Constraint | Design OM Bank Tenant site (structure) has low delivery confidence | The confidence level for Design OM Bank Tenant site (structure) is 20%, which is low for roadmap commitment. This constrains predictability for Design Standards / Public Web / OMCOZA / OM Bank / Tenant. | Medium | Low | Not Started | 20 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 21 | Design Standards row 21 ¦ task='Design OM Bank Tenant site (structure)' ¦ priority=Low ¦ status=Not Started ¦ confidence=20% ¦ upstream=Yes ¦ dependency='Alignment with OM Bank but also OMF' ¦ comment='We need to have initial conversations around OM Bank and if OMF falls under their domain which means they will need to design and build out their screens and IA.'
CON-0011 | PRG-0020 | Design Standards | Justin | Public Web | OMCOZA | Insure / iWyze | Tenant |  | Design iWyze Tenant Product Page Template | Confidence / Planning Constraint | Design iWyze Tenant Product Page Template has low delivery confidence | The confidence level for Design iWyze Tenant Product Page Template is 30%, which is low for roadmap commitment. This constrains predictability for Design Standards / Public Web / OMCOZA / Insure / iWyze / Tenant. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Standards | 23 | Design Standards row 23 ¦ task='Design iWyze Tenant Product Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Alignment with OMF as well as the actual tenant.'
CON-0012 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Retirement. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
CON-0013 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Retirement. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
CON-0014 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Funeral. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0015 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Funeral. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0016 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0017 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0018 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has no named owner | No owner is recorded for the Design Delivery item 'Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named accountable owner or workstream lead. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0019 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Data Quality / Taxonomy Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Entire Site. | Critical | Critical | In Progress | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0020 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has no named owner | No owner is recorded for the Design Delivery item 'Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named accountable owner or workstream lead. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0021 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Data Quality / Taxonomy Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Entire Site. | Critical | Critical | In Progress | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0022 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has no named owner | No owner is recorded for the Design Delivery item 'Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named accountable owner or workstream lead. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0023 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Data Quality / Taxonomy Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. | Critical | Critical | In Progress | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0024 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Accountability Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has no named owner | No owner is recorded for the Design Delivery item 'Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. | Critical | Critical | In Progress | 80 | Assign a named accountable owner or workstream lead. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0025 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Data Quality / Taxonomy Constraint | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. | Critical | Critical | In Progress | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0026 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Accountability Constraint | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding has no named owner | No owner is recorded for the Design Delivery item 'Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding'. This constrains accountability for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. | Critical | Critical | Not Started | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
CON-0027 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Data Quality / Taxonomy Constraint | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. | Critical | Critical | Not Started | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
CON-0028 | PRG-0028 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE |  | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Resource Constraint | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding is constrained by shared or limited resources | The source notes indicate resource pressure for Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding: . This constrains delivery capacity for Design Delivery / Public Web / RESOURCE RECRUITMENT / ALL SITES IN SCOPE / ALL SITES IN SCOPE. | Critical | Critical | Not Started | 100 | Confirm resource allocation, competing commitments, and whether additional support is required. | Design Delivery | 11 | Design Delivery row 11 ¦ task='Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding' ¦ priority=Critical ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
CON-0029 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Accountability Constraint | Audience landing with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'Audience landing with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0030 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Data Quality / Taxonomy Constraint | Audience landing with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0031 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Invest. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0032 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Invest. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0033 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / OM Bank. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0034 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / OM Bank. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0035 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Insure. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0036 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Insure. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0037 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / About us. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0038 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / About us. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0039 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / Careers. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0040 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / Careers. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0041 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Constraint | Mapping of new IA and Footer to sxisting site structure has no named owner | No owner is recorded for the Design Delivery item 'Mapping of new IA and Footer to sxisting site structure'. This constrains accountability for Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0042 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Data Quality / Taxonomy Constraint | Mapping of new IA and Footer to sxisting site structure has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0043 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Constraint | Mapping of new IA and Footer to sxisting site structure has no named owner | No owner is recorded for the Design Delivery item 'Mapping of new IA and Footer to sxisting site structure'. This constrains accountability for Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0044 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Data Quality / Taxonomy Constraint | Mapping of new IA and Footer to sxisting site structure has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0045 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Accountability Constraint | Mapping of new IA and Footer to sxisting site structure has no named owner | No owner is recorded for the Design Delivery item 'Mapping of new IA and Footer to sxisting site structure'. This constrains accountability for Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0046 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Data Quality / Taxonomy Constraint | Mapping of new IA and Footer to sxisting site structure has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0047 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Accountability Constraint | Audience landing with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'Audience landing with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0048 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Data Quality / Taxonomy Constraint | Audience landing with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0049 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / Invest. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0050 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / Invest. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0051 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / Plan. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0052 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / Plan. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0053 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / About. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0054 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / About. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0055 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Wealth / Insights. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0056 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Wealth / Insights. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0057 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Accountability Constraint | Audience landing with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'Audience landing with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0058 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Data Quality / Taxonomy Constraint | Audience landing with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0059 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Corporate / Employees. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0060 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Corporate / Employees. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0061 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Corporate / Employers. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0062 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Corporate / Employers. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0063 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Corporate / Services. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0064 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Corporate / Services. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0065 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Accountability Constraint | Audience landing with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'Audience landing with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Business Landing. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0066 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Data Quality / Taxonomy Constraint | Audience landing with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Business Landing. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0067 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Insure. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0068 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Insure. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0069 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Invest. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0070 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Invest. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0071 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Protect. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0072 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Protect. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0073 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Guarantee. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0074 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Guarantee. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0075 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Accountability Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has no named owner | No owner is recorded for the Design Delivery item 'L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Business / Tools. | Critical | Critical | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0076 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Data Quality / Taxonomy Constraint | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Business / Tools. | Critical | Critical | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0077 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Accountability Constraint | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. has no named owner | No owner is recorded for the Design Delivery item 'Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.'. This constrains accountability for Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. | Critical | Critical | TBC | 70 | Assign a named accountable owner or workstream lead. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0078 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Data Quality / Taxonomy Constraint | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Status missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. | Critical | Critical | TBC | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0079 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Accountability Constraint | Socilaisation of defined IA and Page templates for handover. has no named owner | No owner is recorded for the Design Delivery item 'Socilaisation of defined IA and Page templates for handover.'. This constrains accountability for Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. | High | High | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0080 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Data Quality / Taxonomy Constraint | Socilaisation of defined IA and Page templates for handover. has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. | High | High | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0081 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Accountability Constraint | Socilaisation of defined IA and Page templates for handover. has no named owner | No owner is recorded for the Design Delivery item 'Socilaisation of defined IA and Page templates for handover.'. This constrains accountability for Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. | High | High | In Progress | 100 | Assign a named accountable owner or workstream lead. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0082 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Data Quality / Taxonomy Constraint | Socilaisation of defined IA and Page templates for handover. has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. | High | High | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
CON-0083 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Schedule Constraint | Portfolio View has incomplete schedule detail | The planned schedule for Portfolio View is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All. | High | High | In Progress | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
CON-0084 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Effort / Capacity Constraint | Portfolio View has incomplete or non-standard effort estimate | The effort value for Portfolio View is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All. | High | High | In Progress | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
CON-0085 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Confidence / Planning Constraint | Portfolio View has low delivery confidence | The confidence level for Portfolio View is 10%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All. | High | High | In Progress | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
CON-0086 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Schedule Constraint | Standards on how to creates views on dashboard has incomplete schedule detail | The planned schedule for Standards on how to creates views on dashboard is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All. | High | High | TBC | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
CON-0087 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Effort / Capacity Constraint | Standards on how to creates views on dashboard has incomplete or non-standard effort estimate | The effort value for Standards on how to creates views on dashboard is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All. | High | High | TBC | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
CON-0088 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Confidence / Planning Constraint | Standards on how to creates views on dashboard has low delivery confidence | The confidence level for Standards on how to creates views on dashboard is 10%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All. | High | High | TBC | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
CON-0089 | PRG-0061 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All |  | Standards on how to creates views on dashboard | Data Quality / Taxonomy Constraint | Standards on how to creates views on dashboard has taxonomy or data-quality gaps | The item has data-quality flags: Channel missing; Domain missing; Start date tbc; End date tbc; Effort tbc; Status missing. This constrains clean ingestion and reporting for Feature Delivery / TBC / TBC / Dashboard Views ( Porffolio Views) / All. | High | High | TBC | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 5 | Feature Delivery row 5 ¦ task='Standards on how to creates views on dashboard' ¦ priority=High ¦ status=TBC ¦ confidence=10% ¦ upstream=TBC
CON-0090 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Schedule Constraint | Content Updates has incomplete schedule detail | The planned schedule for Content Updates is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
CON-0091 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Effort / Capacity Constraint | Content Updates has incomplete or non-standard effort estimate | The effort value for Content Updates is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
CON-0092 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Confidence / Planning Constraint | Content Updates has low delivery confidence | The confidence level for Content Updates is 10%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
CON-0093 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Schedule Constraint | Journeys Optimization has incomplete schedule detail | The planned schedule for Journeys Optimization is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
CON-0094 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Effort / Capacity Constraint | Journeys Optimization has incomplete or non-standard effort estimate | The effort value for Journeys Optimization is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
CON-0095 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Confidence / Planning Constraint | Journeys Optimization has low delivery confidence | The confidence level for Journeys Optimization is 10%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | Blocked | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
CON-0096 | PRG-0070 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Withdrawals/Disinvestments | Confidence / Planning Constraint | Withdrawals/Disinvestments has low delivery confidence | The confidence level for Withdrawals/Disinvestments is 40%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 14 | Feature Delivery row 14 ¦ task='Withdrawals/Disinvestments' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=No
CON-0097 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Schedule Constraint | Easy Plus Sales Jorurney on Public Web has incomplete schedule detail | The planned schedule for Easy Plus Sales Jorurney on Public Web is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | Blocked | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
CON-0098 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Effort / Capacity Constraint | Easy Plus Sales Jorurney on Public Web has incomplete or non-standard effort estimate | The effort value for Easy Plus Sales Jorurney on Public Web is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | Blocked | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
CON-0099 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Confidence / Planning Constraint | Easy Plus Sales Jorurney on Public Web has low delivery confidence | The confidence level for Easy Plus Sales Jorurney on Public Web is 10%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | Blocked | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
CON-0100 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Data Quality / Taxonomy Constraint | Easy Plus Sales Jorurney on Public Web has taxonomy or data-quality gaps | The item has data-quality flags: Start date tbc; End date tbc; Effort missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | Blocked | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
CON-0101 | PRG-0074 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Find Advisor | Schedule Constraint | Find Advisor has incomplete schedule detail | The planned schedule for Find Advisor is not fully confirmed. Start date status: Text / check; end date status: Text / check. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | Medium | High | In Progress | 90 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 18 | Feature Delivery row 18 ¦ task='Find Advisor' ¦ priority=High ¦ status=In Progress ¦ confidence=90% ¦ upstream=Yes ¦ dependency='Design - Impact of of new templates on Find Advisor flow' ¦ comment='TBC'
CON-0102 | PRG-0074 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Find Advisor | Effort / Capacity Constraint | Find Advisor has incomplete or non-standard effort estimate | The effort value for Find Advisor is recorded as 'Beta Testing Ready', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | Medium | High | In Progress | 90 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 18 | Feature Delivery row 18 ¦ task='Find Advisor' ¦ priority=High ¦ status=In Progress ¦ confidence=90% ¦ upstream=Yes ¦ dependency='Design - Impact of of new templates on Find Advisor flow' ¦ comment='TBC'
CON-0103 | PRG-0075 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Debt Calculator | Resource Constraint | Debt Calculator is constrained by shared or limited resources | The source notes indicate resource pressure for Debt Calculator: BA Capacity is constrained due current BA on medical Leave. This constrains delivery capacity for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | Medium | High | In Progress | 80 | Confirm resource allocation, competing commitments, and whether additional support is required. | Feature Delivery | 19 | Feature Delivery row 19 ¦ task='Debt Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=No ¦ dependency='BA Capacity is constrained due current BA on medical Leave'
CON-0104 | PRG-0076 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Personal Calculator | Data Quality / Taxonomy Constraint | Personal Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 20 | Feature Delivery row 20 ¦ task='Personal Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=80% ¦ upstream=No ¦ dependency='End of Curent PI front end Development resources will move out of cross channel'
CON-0105 | PRG-0077 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Budget Calculator | Confidence / Planning Constraint | Budget Calculator has no confidence rating | No confidence level is recorded for Budget Calculator. This constrains delivery certainty and prioritisation for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC |  | Capture confidence level and rationale. | Feature Delivery | 21 | Feature Delivery row 21 ¦ task='Budget Calculator' ¦ priority=High ¦ status=TBC ¦ upstream=No
CON-0106 | PRG-0077 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Budget Calculator | Data Quality / Taxonomy Constraint | Budget Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC |  | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 21 | Feature Delivery row 21 ¦ task='Budget Calculator' ¦ priority=High ¦ status=TBC ¦ upstream=No
CON-0107 | PRG-0078 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Income Tax Calculator | Schedule Constraint | Income Tax Calculator has incomplete schedule detail | The planned schedule for Income Tax Calculator is not fully confirmed. Start date status: Text / check; end date status: Text / check. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 22 | Feature Delivery row 22 ¦ task='Income Tax Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0108 | PRG-0078 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Income Tax Calculator | Effort / Capacity Constraint | Income Tax Calculator has incomplete or non-standard effort estimate | The effort value for Income Tax Calculator is recorded as 'Beta Testing Ready', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 22 | Feature Delivery row 22 ¦ task='Income Tax Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0109 | PRG-0078 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Income Tax Calculator | Data Quality / Taxonomy Constraint | Income Tax Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date text / check; Effort text / estimate; Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 22 | Feature Delivery row 22 ¦ task='Income Tax Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0110 | PRG-0079 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Retirement Calculator | Schedule Constraint | Retirement Calculator has incomplete schedule detail | The planned schedule for Retirement Calculator is not fully confirmed. Start date status: Text / check; end date status: Text / check. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 23 | Feature Delivery row 23 ¦ task='Retirement Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0111 | PRG-0079 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Retirement Calculator | Effort / Capacity Constraint | Retirement Calculator has incomplete or non-standard effort estimate | The effort value for Retirement Calculator is recorded as 'Beta Testing Ready', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 23 | Feature Delivery row 23 ¦ task='Retirement Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0112 | PRG-0079 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Retirement Calculator | Data Quality / Taxonomy Constraint | Retirement Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date text / check; Effort text / estimate; Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 23 | Feature Delivery row 23 ¦ task='Retirement Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0113 | PRG-0080 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot Calculator | Schedule Constraint | 2 Pot Calculator has incomplete schedule detail | The planned schedule for 2 Pot Calculator is not fully confirmed. Start date status: Text / check; end date status: Text / check. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 24 | Feature Delivery row 24 ¦ task='2 Pot Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0114 | PRG-0080 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot Calculator | Effort / Capacity Constraint | 2 Pot Calculator has incomplete or non-standard effort estimate | The effort value for 2 Pot Calculator is recorded as 'Beta Testing Ready', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 24 | Feature Delivery row 24 ¦ task='2 Pot Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0115 | PRG-0080 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | 2 Pot Calculator | Data Quality / Taxonomy Constraint | 2 Pot Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date text / check; Effort text / estimate; Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 90 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 24 | Feature Delivery row 24 ¦ task='2 Pot Calculator' ¦ priority=High ¦ status=TBC ¦ confidence=90% ¦ upstream=No
CON-0116 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Schedule Constraint | Contact Us has incomplete schedule detail | The planned schedule for Contact Us is not fully confirmed. Start date status: Text / check; end date status: Text / check. This constrains roadmap sequencing for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 30 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
CON-0117 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Effort / Capacity Constraint | Contact Us has incomplete or non-standard effort estimate | The effort value for Contact Us is recorded as 'Analysis in Progress', not a clean numeric day value. This constrains capacity planning for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 30 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
CON-0118 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Confidence / Planning Constraint | Contact Us has low delivery confidence | The confidence level for Contact Us is 30%, which is low for roadmap commitment. This constrains predictability for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
CON-0119 | PRG-0081 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Contact Us | Data Quality / Taxonomy Constraint | Contact Us has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date text / check; Effort text / estimate; Status missing. This constrains clean ingestion and reporting for Feature Delivery / Public Web / OMCOZA / Personal / L&S. | High | High | TBC | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Feature Delivery | 25 | Feature Delivery row 25 ¦ task='Contact Us' ¦ priority=High ¦ status=TBC ¦ confidence=30% ¦ upstream=No
CON-0120 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Schedule Constraint | Design and Develop CI Updates onto OMDSv2 has incomplete schedule detail | The planned schedule for Design and Develop CI Updates onto OMDSv2 is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | High | High | Blocked | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0121 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Confidence / Planning Constraint | Design and Develop CI Updates onto OMDSv2 has low delivery confidence | The confidence level for Design and Develop CI Updates onto OMDSv2 is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | High | High | Blocked | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0122 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Data Quality / Taxonomy Constraint | Design and Develop CI Updates onto OMDSv2 has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | High | High | Blocked | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0123 | PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Schedule Constraint | Design and Develop Top Navigation Component Updates has incomplete schedule detail | The planned schedule for Design and Develop Top Navigation Component Updates is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Critical | Critical | In Progress | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 5 | Design Systems row 5 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery' ¦ comment='Started, but had to pause due to rework upstream.'
CON-0124 | PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Confidence / Planning Constraint | Design and Develop Top Navigation Component Updates has low delivery confidence | The confidence level for Design and Develop Top Navigation Component Updates is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Critical | Critical | In Progress | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 5 | Design Systems row 5 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery' ¦ comment='Started, but had to pause due to rework upstream.'
CON-0125 | PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Data Quality / Taxonomy Constraint | Design and Develop Top Navigation Component Updates has taxonomy or data-quality gaps | The item has data-quality flags: End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Critical | Critical | In Progress | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 5 | Design Systems row 5 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery' ¦ comment='Started, but had to pause due to rework upstream.'
CON-0126 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Schedule Constraint | Design and Develop Top Navigation Component Updates has incomplete schedule detail | The planned schedule for Design and Develop Top Navigation Component Updates is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Secure Web / All / All / All. | Critical | Critical | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0127 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Confidence / Planning Constraint | Design and Develop Top Navigation Component Updates has low delivery confidence | The confidence level for Design and Develop Top Navigation Component Updates is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Secure Web / All / All / All. | Critical | Critical | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0128 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Data Quality / Taxonomy Constraint | Design and Develop Top Navigation Component Updates has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Secure Web / All / All / All. | Critical | Critical | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0129 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Schedule Constraint | Design and Develop Footer Component Updates has incomplete schedule detail | The planned schedule for Design and Develop Footer Component Updates is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Critical | Critical | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0130 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Confidence / Planning Constraint | Design and Develop Footer Component Updates has low delivery confidence | The confidence level for Design and Develop Footer Component Updates is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Critical | Critical | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0131 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Data Quality / Taxonomy Constraint | Design and Develop Footer Component Updates has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Critical | Critical | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0132 | PRG-0086 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Card Component Updates | Schedule Constraint | Design and Develop Card Component Updates has incomplete schedule detail | The planned schedule for Design and Develop Card Component Updates is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 8 | Design Systems row 8 ¦ task='Design and Develop Card Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0133 | PRG-0086 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Card Component Updates | Confidence / Planning Constraint | Design and Develop Card Component Updates has low delivery confidence | The confidence level for Design and Develop Card Component Updates is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 8 | Design Systems row 8 ¦ task='Design and Develop Card Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0134 | PRG-0086 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Card Component Updates | Data Quality / Taxonomy Constraint | Design and Develop Card Component Updates has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 8 | Design Systems row 8 ¦ task='Design and Develop Card Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0135 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Schedule Constraint | Design and Develop Category Page Template has incomplete schedule detail | The planned schedule for Design and Develop Category Page Template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0136 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Confidence / Planning Constraint | Design and Develop Category Page Template has low delivery confidence | The confidence level for Design and Develop Category Page Template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0137 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Data Quality / Taxonomy Constraint | Design and Develop Category Page Template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0138 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Schedule Constraint | Design and Develop Product Detail Page Template has incomplete schedule detail | The planned schedule for Design and Develop Product Detail Page Template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0139 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Confidence / Planning Constraint | Design and Develop Product Detail Page Template has low delivery confidence | The confidence level for Design and Develop Product Detail Page Template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0140 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Data Quality / Taxonomy Constraint | Design and Develop Product Detail Page Template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0141 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Schedule Constraint | Design and Develop Article Page Template has incomplete schedule detail | The planned schedule for Design and Develop Article Page Template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0142 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Confidence / Planning Constraint | Design and Develop Article Page Template has low delivery confidence | The confidence level for Design and Develop Article Page Template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0143 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Data Quality / Taxonomy Constraint | Design and Develop Article Page Template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | High | High | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0144 | PRG-0090 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Hero Banner Component Updates | Schedule Constraint | Design and Develop Hero Banner Component Updates has incomplete schedule detail | The planned schedule for Design and Develop Hero Banner Component Updates is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 12 | Design Systems row 12 ¦ task='Design and Develop Hero Banner Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0145 | PRG-0090 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Hero Banner Component Updates | Confidence / Planning Constraint | Design and Develop Hero Banner Component Updates has low delivery confidence | The confidence level for Design and Develop Hero Banner Component Updates is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 12 | Design Systems row 12 ¦ task='Design and Develop Hero Banner Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0146 | PRG-0090 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Hero Banner Component Updates | Data Quality / Taxonomy Constraint | Design and Develop Hero Banner Component Updates has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 12 | Design Systems row 12 ¦ task='Design and Develop Hero Banner Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0147 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Schedule Constraint | Design and Develop Landing page template has incomplete schedule detail | The planned schedule for Design and Develop Landing page template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0148 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Effort / Capacity Constraint | Design and Develop Landing page template has incomplete or non-standard effort estimate | The effort value for Design and Develop Landing page template is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0149 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Confidence / Planning Constraint | Design and Develop Landing page template has low delivery confidence | The confidence level for Design and Develop Landing page template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0150 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Data Quality / Taxonomy Constraint | Design and Develop Landing page template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0151 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Schedule Constraint | Design and Develop Section page template has incomplete schedule detail | The planned schedule for Design and Develop Section page template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0152 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Effort / Capacity Constraint | Design and Develop Section page template has incomplete or non-standard effort estimate | The effort value for Design and Develop Section page template is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0153 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Confidence / Planning Constraint | Design and Develop Section page template has low delivery confidence | The confidence level for Design and Develop Section page template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0154 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Data Quality / Taxonomy Constraint | Design and Develop Section page template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0155 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Schedule Constraint | Design and Develop Utility Template: Contact Us has incomplete schedule detail | The planned schedule for Design and Develop Utility Template: Contact Us is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0156 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Effort / Capacity Constraint | Design and Develop Utility Template: Contact Us has incomplete or non-standard effort estimate | The effort value for Design and Develop Utility Template: Contact Us is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0157 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Confidence / Planning Constraint | Design and Develop Utility Template: Contact Us has low delivery confidence | The confidence level for Design and Develop Utility Template: Contact Us is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0158 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Data Quality / Taxonomy Constraint | Design and Develop Utility Template: Contact Us has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0159 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Schedule Constraint | Design and Develop Utility Template: All Calculators has incomplete schedule detail | The planned schedule for Design and Develop Utility Template: All Calculators is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0160 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Effort / Capacity Constraint | Design and Develop Utility Template: All Calculators has incomplete or non-standard effort estimate | The effort value for Design and Develop Utility Template: All Calculators is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0161 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Confidence / Planning Constraint | Design and Develop Utility Template: All Calculators has low delivery confidence | The confidence level for Design and Develop Utility Template: All Calculators is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0162 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Data Quality / Taxonomy Constraint | Design and Develop Utility Template: All Calculators has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0163 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Schedule Constraint | Design and Develop Utility Template: Calculators Page has incomplete schedule detail | The planned schedule for Design and Develop Utility Template: Calculators Page is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0164 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Effort / Capacity Constraint | Design and Develop Utility Template: Calculators Page has incomplete or non-standard effort estimate | The effort value for Design and Develop Utility Template: Calculators Page is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0165 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Confidence / Planning Constraint | Design and Develop Utility Template: Calculators Page has low delivery confidence | The confidence level for Design and Develop Utility Template: Calculators Page is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0166 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Data Quality / Taxonomy Constraint | Design and Develop Utility Template: Calculators Page has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0167 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Schedule Constraint | Design and Develop Utility Templates: About Us has incomplete schedule detail | The planned schedule for Design and Develop Utility Templates: About Us is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0168 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Effort / Capacity Constraint | Design and Develop Utility Templates: About Us has incomplete or non-standard effort estimate | The effort value for Design and Develop Utility Templates: About Us is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0169 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Confidence / Planning Constraint | Design and Develop Utility Templates: About Us has low delivery confidence | The confidence level for Design and Develop Utility Templates: About Us is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0170 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Data Quality / Taxonomy Constraint | Design and Develop Utility Templates: About Us has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0171 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Schedule Constraint | Design and Develop Utility Template: Careers has incomplete schedule detail | The planned schedule for Design and Develop Utility Template: Careers is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0172 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Effort / Capacity Constraint | Design and Develop Utility Template: Careers has incomplete or non-standard effort estimate | The effort value for Design and Develop Utility Template: Careers is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0173 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Confidence / Planning Constraint | Design and Develop Utility Template: Careers has low delivery confidence | The confidence level for Design and Develop Utility Template: Careers is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0174 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Data Quality / Taxonomy Constraint | Design and Develop Utility Template: Careers has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0175 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Schedule Constraint | Add copy standards to OMDS has incomplete schedule detail | The planned schedule for Add copy standards to OMDS is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0176 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Effort / Capacity Constraint | Add copy standards to OMDS has incomplete or non-standard effort estimate | The effort value for Add copy standards to OMDS is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0177 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Confidence / Planning Constraint | Add copy standards to OMDS has low delivery confidence | The confidence level for Add copy standards to OMDS is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0178 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Data Quality / Taxonomy Constraint | Add copy standards to OMDS has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0179 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Schedule Constraint | Add copy standards to OMDS has incomplete schedule detail | The planned schedule for Add copy standards to OMDS is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Secure Web / All / All / All. | Medium | Medium | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0180 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Effort / Capacity Constraint | Add copy standards to OMDS has incomplete or non-standard effort estimate | The effort value for Add copy standards to OMDS is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Secure Web / All / All / All. | Medium | Medium | Not Started | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0181 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Confidence / Planning Constraint | Add copy standards to OMDS has low delivery confidence | The confidence level for Add copy standards to OMDS is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Secure Web / All / All / All. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0182 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Data Quality / Taxonomy Constraint | Add copy standards to OMDS has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Design Systems / Secure Web / All / All / All. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0183 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Schedule Constraint | Design and Develop tenant template has incomplete schedule detail | The planned schedule for Design and Develop tenant template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Public Web / All / All / All. | Medium | Medium | TBC | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0184 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Effort / Capacity Constraint | Design and Develop tenant template has incomplete or non-standard effort estimate | The effort value for Design and Develop tenant template is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Public Web / All / All / All. | Medium | Medium | TBC | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0185 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Confidence / Planning Constraint | Design and Develop tenant template has low delivery confidence | The confidence level for Design and Develop tenant template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Public Web / All / All / All. | Medium | Medium | TBC | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0186 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Data Quality / Taxonomy Constraint | Design and Develop tenant template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula; Status missing. This constrains clean ingestion and reporting for Design Systems / Public Web / All / All / All. | Medium | Medium | TBC | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0187 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Schedule Constraint | Design and Develop tenant template has incomplete schedule detail | The planned schedule for Design and Develop tenant template is not fully confirmed. Start date status: Text / check; end date status: Missing. This constrains roadmap sequencing for Design Systems / Secure Web / All / All / All. | Medium | Medium | TBC | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0188 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Effort / Capacity Constraint | Design and Develop tenant template has incomplete or non-standard effort estimate | The effort value for Design and Develop tenant template is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Design Systems / Secure Web / All / All / All. | Medium | Medium | TBC | 50 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0189 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Confidence / Planning Constraint | Design and Develop tenant template has low delivery confidence | The confidence level for Design and Develop tenant template is 50%, which is low for roadmap commitment. This constrains predictability for Design Systems / Secure Web / All / All / All. | Medium | Medium | TBC | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0190 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Data Quality / Taxonomy Constraint | Design and Develop tenant template has taxonomy or data-quality gaps | The item has data-quality flags: Start date text / check; End date missing; Effort invalid source formula; Status missing. This constrains clean ingestion and reporting for Design Systems / Secure Web / All / All / All. | Medium | Medium | TBC | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
CON-0191 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Accountability Constraint | Implement OMCOM into production has no named owner | No owner is recorded for the Execution item 'Implement OMCOM into production'. This constrains accountability for Execution / Public Web / OMCOM / All / OM. | High | High | In Progress | 70 | Assign a named accountable owner or workstream lead. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
CON-0192 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Data Quality / Taxonomy Constraint | Implement OMCOM into production has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOM / All / OM. | High | High | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
CON-0193 | PRG-0103 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Co-locating Content & Analytics Tagging | Accountability Constraint | Dev: Co-locating Content & Analytics Tagging has no named owner | No owner is recorded for the Execution item 'Dev: Co-locating Content & Analytics Tagging'. This constrains accountability for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 90 | Assign a named accountable owner or workstream lead. | Execution | 5 | Execution row 5 ¦ task='Dev: Co-locating Content & Analytics Tagging' ¦ priority=Critical ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Creating new content_types and updating existing content_types in ContentStack'
CON-0194 | PRG-0103 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Co-locating Content & Analytics Tagging | Data Quality / Taxonomy Constraint | Dev: Co-locating Content & Analytics Tagging has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 90 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 5 | Execution row 5 ¦ task='Dev: Co-locating Content & Analytics Tagging' ¦ priority=Critical ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Creating new content_types and updating existing content_types in ContentStack'
CON-0195 | PRG-0104 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Applying Analytics Tracking to V2 Components | Accountability Constraint | Dev: Applying Analytics Tracking to V2 Components has no named owner | No owner is recorded for the Execution item 'Dev: Applying Analytics Tracking to V2 Components'. This constrains accountability for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 6 | Execution row 6 ¦ task='Dev: Applying Analytics Tracking to V2 Components' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No ¦ comment='Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable)'
CON-0196 | PRG-0104 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC |  | Dev: Applying Analytics Tracking to V2 Components | Data Quality / Taxonomy Constraint | Dev: Applying Analytics Tracking to V2 Components has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA, OMCOM, Bula-tsela, Malawi / Entire Site / All / TBC. | Critical | Critical | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 6 | Execution row 6 ¦ task='Dev: Applying Analytics Tracking to V2 Components' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No ¦ comment='Awaits co-location of Content with Analytics Tagging in ContentStack (where applicable)'
CON-0197 | PRG-0105 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Accountability Constraint | Dev: DevOps Quality Gate Pipeline has no named owner | No owner is recorded for the Execution item 'Dev: DevOps Quality Gate Pipeline'. This constrains accountability for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 7 | Execution row 7 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0198 | PRG-0105 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Data Quality / Taxonomy Constraint | Dev: DevOps Quality Gate Pipeline has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 7 | Execution row 7 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0199 | PRG-0106 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Accountability Constraint | Dev: DevOps Quality Gate Pipeline has no named owner | No owner is recorded for the Execution item 'Dev: DevOps Quality Gate Pipeline'. This constrains accountability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 8 | Execution row 8 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0200 | PRG-0106 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: DevOps Quality Gate Pipeline | Data Quality / Taxonomy Constraint | Dev: DevOps Quality Gate Pipeline has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 8 | Execution row 8 ¦ task='Dev: DevOps Quality Gate Pipeline' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0201 | PRG-0107 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Accountability Constraint | QE: Automated Testing Framework has no named owner | No owner is recorded for the Execution item 'QE: Automated Testing Framework'. This constrains accountability for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 9 | Execution row 9 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0202 | PRG-0107 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Data Quality / Taxonomy Constraint | QE: Automated Testing Framework has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 9 | Execution row 9 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0203 | PRG-0108 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Accountability Constraint | Dev/QE: DevOps - Integrate Automated Testing has no named owner | No owner is recorded for the Execution item 'Dev/QE: DevOps - Integrate Automated Testing'. This constrains accountability for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Assign a named accountable owner or workstream lead. | Execution | 10 | Execution row 10 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0204 | PRG-0108 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Data Quality / Taxonomy Constraint | Dev/QE: DevOps - Integrate Automated Testing has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 10 | Execution row 10 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0205 | PRG-0109 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Accountability Constraint | QE: Automated Testing Framework has no named owner | No owner is recorded for the Execution item 'QE: Automated Testing Framework'. This constrains accountability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 11 | Execution row 11 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0206 | PRG-0109 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | QE: Automated Testing Framework | Data Quality / Taxonomy Constraint | QE: Automated Testing Framework has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 11 | Execution row 11 ¦ task='QE: Automated Testing Framework' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0207 | PRG-0110 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Accountability Constraint | Dev/QE: DevOps - Integrate Automated Testing has no named owner | No owner is recorded for the Execution item 'Dev/QE: DevOps - Integrate Automated Testing'. This constrains accountability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Assign a named accountable owner or workstream lead. | Execution | 12 | Execution row 12 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0208 | PRG-0110 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev/QE: DevOps - Integrate Automated Testing | Data Quality / Taxonomy Constraint | Dev/QE: DevOps - Integrate Automated Testing has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | High | High | Not Started | 60 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 12 | Execution row 12 ¦ task='Dev/QE: DevOps - Integrate Automated Testing' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0209 | PRG-0111 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Accountability Constraint | Dev: Observability Dashboard Templates for Sites has no named owner | No owner is recorded for the Execution item 'Dev: Observability Dashboard Templates for Sites'. This constrains accountability for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 13 | Execution row 13 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0210 | PRG-0111 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Data Quality / Taxonomy Constraint | Dev: Observability Dashboard Templates for Sites has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 13 | Execution row 13 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=No
CON-0211 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Accountability Constraint | Dev: Observability Dashboard Templates for Sites has no named owner | No owner is recorded for the Execution item 'Dev: Observability Dashboard Templates for Sites'. This constrains accountability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Assign a named accountable owner or workstream lead. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
CON-0212 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Data Quality / Taxonomy Constraint | Dev: Observability Dashboard Templates for Sites has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
CON-0213 | PRG-0113 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Accountability Constraint | Dev: Styling Backwards Compatibility - V2 ModularPage has no named owner | No owner is recorded for the Execution item 'Dev: Styling Backwards Compatibility - V2 ModularPage'. This constrains accountability for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named accountable owner or workstream lead. | Execution | 18 | Execution row 18 ¦ task='Dev: Styling Backwards Compatibility - V2 ModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
CON-0214 | PRG-0113 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Data Quality / Taxonomy Constraint | Dev: Styling Backwards Compatibility - V2 ModularPage has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 18 | Execution row 18 ¦ task='Dev: Styling Backwards Compatibility - V2 ModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
CON-0215 | PRG-0114 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Accountability Constraint | Dev: Styling Backwards Compatibility - V2 ArticleModularPage has no named owner | No owner is recorded for the Execution item 'Dev: Styling Backwards Compatibility - V2 ArticleModularPage'. This constrains accountability for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named accountable owner or workstream lead. | Execution | 19 | Execution row 19 ¦ task='Dev: Styling Backwards Compatibility - V2 ArticleModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
CON-0216 | PRG-0114 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Data Quality / Taxonomy Constraint | Dev: Styling Backwards Compatibility - V2 ArticleModularPage has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 19 | Execution row 19 ¦ task='Dev: Styling Backwards Compatibility - V2 ArticleModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
CON-0217 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Effort / Capacity Constraint | Dev: Export Analytics Data into Tableau has incomplete or non-standard effort estimate | The effort value for Dev: Export Analytics Data into Tableau is recorded as '~5', not a clean numeric day value. This constrains capacity planning for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0218 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Confidence / Planning Constraint | Dev: Export Analytics Data into Tableau has low delivery confidence | The confidence level for Dev: Export Analytics Data into Tableau is 40%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0219 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Accountability Constraint | Dev: Export Analytics Data into Tableau has no named owner | No owner is recorded for the Execution item 'Dev: Export Analytics Data into Tableau'. This constrains accountability for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named accountable owner or workstream lead. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0220 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Data Quality / Taxonomy Constraint | Dev: Export Analytics Data into Tableau has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Effort text / estimate. This constrains clean ingestion and reporting for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0221 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Technical Access / Data Constraint | Dev: Export Analytics Data into Tableau is constrained by unresolved data/source access detail | The source notes indicate that Dev: Export Analytics Data into Tableau requires clarity on data sources, destination, or access credentials. This constrains implementation for Execution / Public Web / All / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Confirm source systems, destination, credentials, and responsible technical owner. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0222 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Confidence / Planning Constraint | Dev: Export Analytics Data into Tableau has low delivery confidence | The confidence level for Dev: Export Analytics Data into Tableau is 40%, which is low for roadmap commitment. This constrains predictability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0223 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Accountability Constraint | Dev: Export Analytics Data into Tableau has no named owner | No owner is recorded for the Execution item 'Dev: Export Analytics Data into Tableau'. This constrains accountability for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named accountable owner or workstream lead. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0224 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Data Quality / Taxonomy Constraint | Dev: Export Analytics Data into Tableau has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0225 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Technical Access / Data Constraint | Dev: Export Analytics Data into Tableau is constrained by unresolved data/source access detail | The source notes indicate that Dev: Export Analytics Data into Tableau requires clarity on data sources, destination, or access credentials. This constrains implementation for Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Confirm source systems, destination, credentials, and responsible technical owner. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
CON-0226 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Accountability Constraint | Dev: Configuring Web Transformation Page Template in ContentStack has no named owner | No owner is recorded for the Execution item 'Dev: Configuring Web Transformation Page Template in ContentStack'. This constrains accountability for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named accountable owner or workstream lead. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
CON-0227 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Data Quality / Taxonomy Constraint | Dev: Configuring Web Transformation Page Template in ContentStack has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
CON-0228 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Accountability Constraint | Dev: Update Page Rendering Pipeline to support WT pages has no named owner | No owner is recorded for the Execution item 'Dev: Update Page Rendering Pipeline to support WT pages'. This constrains accountability for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Assign a named accountable owner or workstream lead. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
CON-0229 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Data Quality / Taxonomy Constraint | Dev: Update Page Rendering Pipeline to support WT pages has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Critical | Critical | Not Started | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
CON-0230 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Schedule Constraint | Dev: Navigation components updates public Web has incomplete schedule detail | The planned schedule for Dev: Navigation components updates public Web is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
CON-0231 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Confidence / Planning Constraint | Dev: Navigation components updates public Web has low delivery confidence | The confidence level for Dev: Navigation components updates public Web is 40%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
CON-0232 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Accountability Constraint | Dev: Navigation components updates public Web has no named owner | No owner is recorded for the Execution item 'Dev: Navigation components updates public Web'. This constrains accountability for Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named accountable owner or workstream lead. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
CON-0233 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Data Quality / Taxonomy Constraint | Dev: Navigation components updates public Web has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Critical | Critical | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
CON-0234 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Schedule Constraint | QE : Automated Testing Framework (LS) has incomplete schedule detail | The planned schedule for QE : Automated Testing Framework (LS) is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 60 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0235 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Accountability Constraint | QE : Automated Testing Framework (LS) has no named owner | No owner is recorded for the Execution item 'QE : Automated Testing Framework (LS)'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 60 | Assign a named accountable owner or workstream lead. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0236 | PRG-0120 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | QE : Automated Testing Framework (LS) | Data Quality / Taxonomy Constraint | QE : Automated Testing Framework (LS) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 60 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 25 | Execution row 25 ¦ task='QE : Automated Testing Framework (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=60% ¦ upstream=No
CON-0237 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Schedule Constraint | Dev :Observability Dashboards for various sites (LS) has incomplete schedule detail | The planned schedule for Dev :Observability Dashboards for various sites (LS) is not fully confirmed. Start date status: Missing; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0238 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Confidence / Planning Constraint | Dev :Observability Dashboards for various sites (LS) has low delivery confidence | The confidence level for Dev :Observability Dashboards for various sites (LS) is 50%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0239 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Accountability Constraint | Dev :Observability Dashboards for various sites (LS) has no named owner | No owner is recorded for the Execution item 'Dev :Observability Dashboards for various sites (LS)'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 50 | Assign a named accountable owner or workstream lead. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0240 | PRG-0121 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev :Observability Dashboards for various sites (LS) | Data Quality / Taxonomy Constraint | Dev :Observability Dashboards for various sites (LS) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date missing; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 26 | Execution row 26 ¦ task='Dev :Observability Dashboards for various sites (LS)' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0241 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Schedule Constraint | Dev : Modular Template (LS) has incomplete schedule detail | The planned schedule for Dev : Modular Template (LS) is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
CON-0242 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Confidence / Planning Constraint | Dev : Modular Template (LS) has low delivery confidence | The confidence level for Dev : Modular Template (LS) is 50%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
CON-0243 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Accountability Constraint | Dev : Modular Template (LS) has no named owner | No owner is recorded for the Execution item 'Dev : Modular Template (LS)'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Assign a named accountable owner or workstream lead. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
CON-0244 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Data Quality / Taxonomy Constraint | Dev : Modular Template (LS) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
CON-0245 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Schedule Constraint | Dev : Modular Page Components (LS) has incomplete schedule detail | The planned schedule for Dev : Modular Page Components (LS) is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0246 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Effort / Capacity Constraint | Dev : Modular Page Components (LS) has incomplete or non-standard effort estimate | The effort value for Dev : Modular Page Components (LS) is recorded as '~5', not a clean numeric day value. This constrains capacity planning for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0247 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Confidence / Planning Constraint | Dev : Modular Page Components (LS) has low delivery confidence | The confidence level for Dev : Modular Page Components (LS) is 40%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0248 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Accountability Constraint | Dev : Modular Page Components (LS) has no named owner | No owner is recorded for the Execution item 'Dev : Modular Page Components (LS)'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named accountable owner or workstream lead. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0249 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Data Quality / Taxonomy Constraint | Dev : Modular Page Components (LS) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing; Effort text / estimate. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0250 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Schedule Constraint | Dev Applying analytics tracking to CMS (LS) has incomplete schedule detail | The planned schedule for Dev Applying analytics tracking to CMS (LS) is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0251 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Effort / Capacity Constraint | Dev Applying analytics tracking to CMS (LS) has incomplete or non-standard effort estimate | The effort value for Dev Applying analytics tracking to CMS (LS) is recorded as '~5', not a clean numeric day value. This constrains capacity planning for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0252 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Confidence / Planning Constraint | Dev Applying analytics tracking to CMS (LS) has low delivery confidence | The confidence level for Dev Applying analytics tracking to CMS (LS) is 40%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0253 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Accountability Constraint | Dev Applying analytics tracking to CMS (LS) has no named owner | No owner is recorded for the Execution item 'Dev Applying analytics tracking to CMS (LS)'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Assign a named accountable owner or workstream lead. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0254 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Data Quality / Taxonomy Constraint | Dev Applying analytics tracking to CMS (LS) has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing; Effort text / estimate. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
CON-0255 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Schedule Constraint | Dev: OMCOZA -Licence cutover has incomplete schedule detail | The planned schedule for Dev: OMCOZA -Licence cutover is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 60 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
CON-0256 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Accountability Constraint | Dev: OMCOZA -Licence cutover has no named owner | No owner is recorded for the Execution item 'Dev: OMCOZA -Licence cutover'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 60 | Assign a named accountable owner or workstream lead. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
CON-0257 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Data Quality / Taxonomy Constraint | Dev: OMCOZA -Licence cutover has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 60 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
CON-0258 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Schedule Constraint | Dev : Tableau Analytics has incomplete schedule detail | The planned schedule for Dev : Tableau Analytics is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0259 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Confidence / Planning Constraint | Dev : Tableau Analytics has low delivery confidence | The confidence level for Dev : Tableau Analytics is 50%, which is low for roadmap commitment. This constrains predictability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0260 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Accountability Constraint | Dev : Tableau Analytics has no named owner | No owner is recorded for the Execution item 'Dev : Tableau Analytics'. This constrains accountability for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Assign a named accountable owner or workstream lead. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0261 | PRG-0126 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Tableau Analytics | Data Quality / Taxonomy Constraint | Dev : Tableau Analytics has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Cluster missing or broad; Start date tbc; End date missing. This constrains clean ingestion and reporting for Execution / Public Web / OMCOZA / Personal / All / TBC. | Critical | Critical | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Execution | 32 | Execution row 32 ¦ task='Dev : Tableau Analytics' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=No
CON-0262 | PRG-0127 | Publishing | Bernice | Public Web | OMCOM | Entire Site | All / TBC |  | Take live in V2 new platform | Data Quality / Taxonomy Constraint | Take live in V2 new platform has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOM / Entire Site / All / TBC. | High | High | N/A | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 4 | Publishing row 4 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No
CON-0263 | PRG-0128 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Testing in V2 new platform and log bugs | Data Quality / Taxonomy Constraint | Testing in V2 new platform and log bugs has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. | High | High | Not Started | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 5 | Publishing row 5 ¦ task='Testing in V2 new platform and log bugs' ¦ priority=High ¦ status=Not Started ¦ confidence=100% ¦ upstream=No ¦ comment='Need to work with Web developers for bug fixes'
CON-0264 | PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Schedule Constraint | Take live in V2 new platform has incomplete schedule detail | The planned schedule for Take live in V2 new platform is not fully confirmed. Start date status: TBC; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. | High | High | N/A | 80 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 6 | Publishing row 6 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No ¦ comment='Go live date will be determined in the next PI Planning'
CON-0265 | PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Effort / Capacity Constraint | Take live in V2 new platform has incomplete or non-standard effort estimate | The effort value for Take live in V2 new platform is recorded as 'Invalid source formula', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. | High | High | N/A | 80 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 6 | Publishing row 6 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No ¦ comment='Go live date will be determined in the next PI Planning'
CON-0266 | PRG-0129 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Take live in V2 new platform | Data Quality / Taxonomy Constraint | Take live in V2 new platform has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; Start date tbc; End date missing; Effort invalid source formula. This constrains clean ingestion and reporting for Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. | High | High | N/A | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 6 | Publishing row 6 ¦ task='Take live in V2 new platform' ¦ priority=High ¦ status=N/A ¦ confidence=80% ¦ upstream=No ¦ comment='Go live date will be determined in the next PI Planning'
CON-0267 | PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure based on all as-is pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure based on all as-is pages (keep/remove/consolidate) is not fully confirmed. Start date status: Missing; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 10 | Publishing row 10 ¦ task='Record URL structure based on all as-is pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0268 | PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure based on all as-is pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure based on all as-is pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 10 | Publishing row 10 ¦ task='Record URL structure based on all as-is pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0269 | PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure based on all as-is pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; Start date missing; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 10 | Publishing row 10 ¦ task='Record URL structure based on all as-is pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0270 | PRG-0134 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Start moving as-is pages over to Beta | Data Quality / Taxonomy Constraint | Start moving as-is pages over to Beta has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | High | High | In Progress | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 11 | Publishing row 11 ¦ task='Start moving as-is pages over to Beta' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Design' ¦ comment='Confirm pages and URLs for "as-is" pages before I can start moving'
CON-0271 | PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining Personal pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining Personal pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 12 | Publishing row 12 ¦ task='Record URL structure for all remaining Personal pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0272 | PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining Personal pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining Personal pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 12 | Publishing row 12 ¦ task='Record URL structure for all remaining Personal pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0273 | PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining Personal pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 12 | Publishing row 12 ¦ task='Record URL structure for all remaining Personal pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0274 | PRG-0136 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 13 | Publishing row 13 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0275 | PRG-0136 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Personal / All / TBC. | High | High | Not Started | 70 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 13 | Publishing row 13 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0276 | PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining Corporate pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 14 | Publishing row 14 ¦ task='Record URL structure for all remaining Corporate pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0277 | PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining Corporate pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 14 | Publishing row 14 ¦ task='Record URL structure for all remaining Corporate pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0278 | PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 14 | Publishing row 14 ¦ task='Record URL structure for all remaining Corporate pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0279 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 40%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0280 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0281 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Corporate / All / TBC. | High | High | Not Started | 40 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0282 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 30%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / Wealth / All / TBC. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0283 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Wealth / All / TBC. | High | High | Not Started | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0284 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Wealth / All / TBC. | High | High | Not Started | 30 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0285 | PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining Utility pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining Utility pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 17 | Publishing row 17 ¦ task='Record URL structure for all remaining Utility pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0286 | PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining Utility pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining Utility pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 17 | Publishing row 17 ¦ task='Record URL structure for all remaining Utility pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0287 | PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining Utility pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 17 | Publishing row 17 ¦ task='Record URL structure for all remaining Utility pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0288 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 30%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0289 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0290 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | High | High | Not Started | 30 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0291 | PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining About us pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining About us pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 19 | Publishing row 19 ¦ task='Record URL structure for all remaining About us pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0292 | PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining About us pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining About us pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 19 | Publishing row 19 ¦ task='Record URL structure for all remaining About us pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0293 | PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining About us pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 19 | Publishing row 19 ¦ task='Record URL structure for all remaining About us pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0294 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 30%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0295 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0296 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / About Us / All / TBC. | High | High | Not Started | 30 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0297 | PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining Careers pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining Careers pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 21 | Publishing row 21 ¦ task='Record URL structure for all remaining Careers pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0298 | PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining Careers pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining Careers pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 21 | Publishing row 21 ¦ task='Record URL structure for all remaining Careers pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0299 | PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining Careers pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 21 | Publishing row 21 ¦ task='Record URL structure for all remaining Careers pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0300 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 30%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0301 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0302 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Careers / All / TBC. | High | High | Not Started | 30 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0303 | PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Schedule Constraint | Record URL structure for all remaining Business pages (keep/remove/consolidate) has incomplete schedule detail | The planned schedule for Record URL structure for all remaining Business pages (keep/remove/consolidate) is not fully confirmed. Start date status: Exact; end date status: Missing. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 23 | Publishing row 23 ¦ task='Record URL structure for all remaining Business pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0304 | PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Effort / Capacity Constraint | Record URL structure for all remaining Business pages (keep/remove/consolidate) has incomplete or non-standard effort estimate | The effort value for Record URL structure for all remaining Business pages (keep/remove/consolidate) is recorded as 'Missing', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 23 | Publishing row 23 ¦ task='Record URL structure for all remaining Business pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0305 | PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Data Quality / Taxonomy Constraint | Record URL structure for all remaining Business pages (keep/remove/consolidate) has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad; End date missing; Effort missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 23 | Publishing row 23 ¦ task='Record URL structure for all remaining Business pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
CON-0306 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Confidence / Planning Constraint | Start building new template pages has low delivery confidence | The confidence level for Start building new template pages is 30%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 30 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0307 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Data Quality / Taxonomy Constraint | Start building new template pages has taxonomy or data-quality gaps | The item has data-quality flags: Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 30 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0308 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Sequencing Constraint | Start building new template pages is constrained by delivery sequencing | The source notes show that Start building new template pages can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOZA / Business / All / TBC. | High | High | Not Started | 30 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0309 | PRG-0148 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Confidence / Planning Constraint | Add new Nav, Footer and update IA has low delivery confidence | The confidence level for Add new Nav, Footer and update IA is 50%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMCOM / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 25 | Publishing row 25 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0310 | PRG-0148 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Data Quality / Taxonomy Constraint | Add new Nav, Footer and update IA has taxonomy or data-quality gaps | The item has data-quality flags: Area/Journey missing or broad; Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOM / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 25 | Publishing row 25 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0311 | PRG-0148 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Sequencing Constraint | Add new Nav, Footer and update IA is constrained by delivery sequencing | The source notes show that Add new Nav, Footer and update IA can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMCOM / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 25 | Publishing row 25 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0312 | PRG-0149 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Confidence / Planning Constraint | Add new Nav, Footer and update IA has low delivery confidence | The confidence level for Add new Nav, Footer and update IA is 50%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMAI (Alternatives) / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 26 | Publishing row 26 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0313 | PRG-0149 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Data Quality / Taxonomy Constraint | Add new Nav, Footer and update IA has taxonomy or data-quality gaps | The item has data-quality flags: Area/Journey missing or broad; Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMAI (Alternatives) / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 26 | Publishing row 26 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0314 | PRG-0149 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Sequencing Constraint | Add new Nav, Footer and update IA is constrained by delivery sequencing | The source notes show that Add new Nav, Footer and update IA can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / OMAI (Alternatives) / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 26 | Publishing row 26 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0315 | PRG-0150 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Confidence / Planning Constraint | Add new Nav, Footer and update IA has low delivery confidence | The confidence level for Add new Nav, Footer and update IA is 50%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / Bula Tsela / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 27 | Publishing row 27 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0316 | PRG-0150 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Data Quality / Taxonomy Constraint | Add new Nav, Footer and update IA has taxonomy or data-quality gaps | The item has data-quality flags: Area/Journey missing or broad; Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / Bula Tsela / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 27 | Publishing row 27 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0317 | PRG-0150 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Sequencing Constraint | Add new Nav, Footer and update IA is constrained by delivery sequencing | The source notes show that Add new Nav, Footer and update IA can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / Bula Tsela / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 27 | Publishing row 27 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0318 | PRG-0151 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Confidence / Planning Constraint | Add new Nav, Footer and update IA has low delivery confidence | The confidence level for Add new Nav, Footer and update IA is 50%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / LTD / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 28 | Publishing row 28 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0319 | PRG-0151 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Data Quality / Taxonomy Constraint | Add new Nav, Footer and update IA has taxonomy or data-quality gaps | The item has data-quality flags: Area/Journey missing or broad; Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / LTD / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 28 | Publishing row 28 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0320 | PRG-0151 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Sequencing Constraint | Add new Nav, Footer and update IA is constrained by delivery sequencing | The source notes show that Add new Nav, Footer and update IA can only proceed after a prior state or milestone is reached. Evidence: Work can only begin once all upstream teams have completed their work. This constrains execution order for Publishing / Public Web / LTD / All / TBC / All / TBC. | Medium | Medium | Not Started | 50 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 28 | Publishing row 28 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
CON-0321 | PRG-0152 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC |  | Publishing requirements for OMAR, logged on OMAR tab | Confidence / Planning Constraint | Publishing requirements for OMAR, logged on OMAR tab has low delivery confidence | The confidence level for Publishing requirements for OMAR, logged on OMAR tab is 10%, which is low for roadmap commitment. This constrains predictability for Publishing / Public Web / OMAR / All / TBC / All / TBC. | Medium | Medium | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Publishing | 29 | Publishing row 29 ¦ task='Publishing requirements for OMAR, logged on OMAR tab' ¦ priority=Medium ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab.'
CON-0322 | PRG-0152 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC |  | Publishing requirements for OMAR, logged on OMAR tab | Data Quality / Taxonomy Constraint | Publishing requirements for OMAR, logged on OMAR tab has taxonomy or data-quality gaps | The item has data-quality flags: Area/Journey missing or broad; Cluster missing or broad. This constrains clean ingestion and reporting for Publishing / Public Web / OMAR / All / TBC / All / TBC. | Medium | Medium | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 29 | Publishing row 29 ¦ task='Publishing requirements for OMAR, logged on OMAR tab' ¦ priority=Medium ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab.'
CON-0323 | PRG-0152 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC |  | Publishing requirements for OMAR, logged on OMAR tab | Sequencing Constraint | Publishing requirements for OMAR, logged on OMAR tab is constrained by delivery sequencing | The source notes show that Publishing requirements for OMAR, logged on OMAR tab can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab.. This constrains execution order for Publishing / Public Web / OMAR / All / TBC / All / TBC. | Medium | Medium | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 29 | Publishing row 29 ¦ task='Publishing requirements for OMAR, logged on OMAR tab' ¦ priority=Medium ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab.'
CON-0324 | PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Schedule Constraint | Add all new redirects for the site has incomplete schedule detail | The planned schedule for Add all new redirects for the site is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for Publishing / Public Web / OMCOZA / Entire Site / Entire Site. | Medium | TBC | Not Started |  | Confirm start date, end date, and whether the item is committed for the current roadmap. | Publishing | 30 | Publishing row 30 ¦ task='Add all new redirects for the site' ¦ priority=TBC ¦ status=Not Started ¦ upstream=TBC ¦ comment='Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.'
CON-0325 | PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Effort / Capacity Constraint | Add all new redirects for the site has incomplete or non-standard effort estimate | The effort value for Add all new redirects for the site is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for Publishing / Public Web / OMCOZA / Entire Site / Entire Site. | Medium | TBC | Not Started |  | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | Publishing | 30 | Publishing row 30 ¦ task='Add all new redirects for the site' ¦ priority=TBC ¦ status=Not Started ¦ upstream=TBC ¦ comment='Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.'
CON-0326 | PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Confidence / Planning Constraint | Add all new redirects for the site has no confidence rating | No confidence level is recorded for Add all new redirects for the site. This constrains delivery certainty and prioritisation for Publishing / Public Web / OMCOZA / Entire Site / Entire Site. | Medium | TBC | Not Started |  | Capture confidence level and rationale. | Publishing | 30 | Publishing row 30 ¦ task='Add all new redirects for the site' ¦ priority=TBC ¦ status=Not Started ¦ upstream=TBC ¦ comment='Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.'
CON-0327 | PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Data Quality / Taxonomy Constraint | Add all new redirects for the site has taxonomy or data-quality gaps | The item has data-quality flags: Start date tbc; End date tbc; Effort tbc; Priority missing. This constrains clean ingestion and reporting for Publishing / Public Web / OMCOZA / Entire Site / Entire Site. | Medium | TBC | Not Started |  | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Publishing | 30 | Publishing row 30 ¦ task='Add all new redirects for the site' ¦ priority=TBC ¦ status=Not Started ¦ upstream=TBC ¦ comment='Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.'
CON-0328 | PRG-0153 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site |  | Add all new redirects for the site | Sequencing Constraint | Add all new redirects for the site is constrained by delivery sequencing | The source notes show that Add all new redirects for the site can only proceed after a prior state or milestone is reached. Evidence: Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.. This constrains execution order for Publishing / Public Web / OMCOZA / Entire Site / Entire Site. | Medium | TBC | Not Started |  | Add the prerequisite milestone to the integrated plan and link it to this item. | Publishing | 30 | Publishing row 30 ¦ task='Add all new redirects for the site' ¦ priority=TBC ¦ status=Not Started ¦ upstream=TBC ¦ comment='Redirect entry needs to be added for all URLs that were changed. This can only be added once the new site is live.'
CON-0329 | PRG-0154 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Penetration Testing Discussion and confirmation | Accountability Constraint | Penetration Testing Discussion and confirmation has no named owner | No owner is recorded for the Go-Live Readiness item 'Penetration Testing Discussion and confirmation'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | High | High | Complete | 100 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 4 | Go-Live Readiness row 4 ¦ task='Penetration Testing Discussion and confirmation' ¦ priority=High ¦ status=Complete ¦ confidence=100% ¦ upstream=No ¦ comment='Penetration Testing has to be done, at no cost to us, we just have to send URL' for testing - URL of sites must be sent Security Team'
CON-0330 | PRG-0154 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Penetration Testing Discussion and confirmation | Data Quality / Taxonomy Constraint | Penetration Testing Discussion and confirmation has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | High | High | Complete | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 4 | Go-Live Readiness row 4 ¦ task='Penetration Testing Discussion and confirmation' ¦ priority=High ¦ status=Complete ¦ confidence=100% ¦ upstream=No ¦ comment='Penetration Testing has to be done, at no cost to us, we just have to send URL' for testing - URL of sites must be sent Security Team'
CON-0331 | PRG-0155 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Quality Assurance Approval | Accountability Constraint | Quality Assurance Approval has no named owner | No owner is recorded for the Go-Live Readiness item 'Quality Assurance Approval'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 100 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 5 | Go-Live Readiness row 5 ¦ task='Quality Assurance Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
CON-0332 | PRG-0155 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Quality Assurance Approval | Data Quality / Taxonomy Constraint | Quality Assurance Approval has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 5 | Go-Live Readiness row 5 ¦ task='Quality Assurance Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
CON-0333 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Accountability Constraint | Security Approvals has no named owner | No owner is recorded for the Go-Live Readiness item 'Security Approvals'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | TBC | 100 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
CON-0334 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Data Quality / Taxonomy Constraint | Security Approvals has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Status missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | TBC | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
CON-0335 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Sequencing Constraint | Security Approvals is constrained by delivery sequencing | The source notes show that Security Approvals can only proceed after a prior state or milestone is reached. Evidence: All deliveries must be in QA State. This constrains execution order for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | TBC | 100 | Add the prerequisite milestone to the integrated plan and link it to this item. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
CON-0336 | PRG-0157 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Internal Communication ( Call Centre) - Marketing Team Driven | Accountability Constraint | Internal Communication ( Call Centre) - Marketing Team Driven has no named owner | No owner is recorded for the Go-Live Readiness item 'Internal Communication ( Call Centre) - Marketing Team Driven'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 70 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 7 | Go-Live Readiness row 7 ¦ task='Internal Communication ( Call Centre) - Marketing Team Driven' ¦ priority=Low ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T'
CON-0337 | PRG-0157 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Internal Communication ( Call Centre) - Marketing Team Driven | Data Quality / Taxonomy Constraint | Internal Communication ( Call Centre) - Marketing Team Driven has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 7 | Go-Live Readiness row 7 ¦ task='Internal Communication ( Call Centre) - Marketing Team Driven' ¦ priority=Low ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T'
CON-0338 | PRG-0157 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Internal Communication ( Call Centre) - Marketing Team Driven | Sequencing Constraint | Internal Communication ( Call Centre) - Marketing Team Driven is constrained by delivery sequencing | The source notes show that Internal Communication ( Call Centre) - Marketing Team Driven can only proceed after a prior state or milestone is reached. Evidence: All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T. This constrains execution order for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 70 | Add the prerequisite milestone to the integrated plan and link it to this item. | Go-Live Readiness | 7 | Go-Live Readiness row 7 ¦ task='Internal Communication ( Call Centre) - Marketing Team Driven' ¦ priority=Low ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T'
CON-0339 | PRG-0158 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Service Now Update | Accountability Constraint | Service Now Update has no named owner | No owner is recorded for the Go-Live Readiness item 'Service Now Update'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 80 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 8 | Go-Live Readiness row 8 ¦ task='Service Now Update' ¦ priority=Low ¦ status=Not Started ¦ confidence=80% ¦ upstream=No
CON-0340 | PRG-0158 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Service Now Update | Data Quality / Taxonomy Constraint | Service Now Update has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 80 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 8 | Go-Live Readiness row 8 ¦ task='Service Now Update' ¦ priority=Low ¦ status=Not Started ¦ confidence=80% ¦ upstream=No
CON-0341 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Confidence / Planning Constraint | Executive Approval has low delivery confidence | The confidence level for Executive Approval is 50%, which is low for roadmap commitment. This constrains predictability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
CON-0342 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Accountability Constraint | Executive Approval has no named owner | No owner is recorded for the Go-Live Readiness item 'Executive Approval'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
CON-0343 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Data Quality / Taxonomy Constraint | Executive Approval has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
CON-0344 | PRG-0160 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Change Management Go Ahead | Confidence / Planning Constraint | Change Management Go Ahead has low delivery confidence | The confidence level for Change Management Go Ahead is 50%, which is low for roadmap commitment. This constrains predictability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Go-Live Readiness | 10 | Go-Live Readiness row 10 ¦ task='Change Management Go Ahead' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='All work by teams must be completed'
CON-0345 | PRG-0160 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Change Management Go Ahead | Accountability Constraint | Change Management Go Ahead has no named owner | No owner is recorded for the Go-Live Readiness item 'Change Management Go Ahead'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 10 | Go-Live Readiness row 10 ¦ task='Change Management Go Ahead' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='All work by teams must be completed'
CON-0346 | PRG-0160 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Change Management Go Ahead | Data Quality / Taxonomy Constraint | Change Management Go Ahead has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 10 | Go-Live Readiness row 10 ¦ task='Change Management Go Ahead' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='All work by teams must be completed'
CON-0347 | PRG-0161 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Customer Experience Tool | Confidence / Planning Constraint | Customer Experience Tool has low delivery confidence | The confidence level for Customer Experience Tool is 10%, which is low for roadmap commitment. This constrains predictability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | Go-Live Readiness | 11 | Go-Live Readiness row 11 ¦ task='Customer Experience Tool' ¦ priority=Low ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Tool Evaluating' ¦ comment='Tool still in evaluation tool'
CON-0348 | PRG-0161 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Customer Experience Tool | Accountability Constraint | Customer Experience Tool has no named owner | No owner is recorded for the Go-Live Readiness item 'Customer Experience Tool'. This constrains accountability for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 10 | Assign a named accountable owner or workstream lead. | Go-Live Readiness | 11 | Go-Live Readiness row 11 ¦ task='Customer Experience Tool' ¦ priority=Low ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Tool Evaluating' ¦ comment='Tool still in evaluation tool'
CON-0349 | PRG-0161 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Customer Experience Tool | Data Quality / Taxonomy Constraint | Customer Experience Tool has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | Go-Live Readiness | 11 | Go-Live Readiness row 11 ¦ task='Customer Experience Tool' ¦ priority=Low ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Tool Evaluating' ¦ comment='Tool still in evaluation tool'
CON-0350 | PRG-0161 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Customer Experience Tool | Tooling Constraint | Customer Experience Tool is constrained by tool evaluation | The source notes indicate the tool is still under evaluation for Customer Experience Tool. This constrains readiness and implementation planning for Go-Live Readiness / Public Web / All / All / All. | Medium | Low | Not Started | 10 | Confirm selected tool, owner, implementation date, and acceptance criteria. | Go-Live Readiness | 11 | Go-Live Readiness row 11 ¦ task='Customer Experience Tool' ¦ priority=Low ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Tool Evaluating' ¦ comment='Tool still in evaluation tool'
CON-0351 | PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Accountability Constraint | Confirm Engagement Cycle with SEO Team has no named owner | No owner is recorded for the SEO / Analytics item 'Confirm Engagement Cycle with SEO Team'. This constrains accountability for SEO / Analytics / Public Web / All / All / All. | High | High | In Progress | 100 | Assign a named accountable owner or workstream lead. | SEO Analytics | 4 | SEO Analytics row 4 ¦ task='Confirm Engagement Cycle with SEO Team' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=No ¦ comment='Final Approval will be provided by the CMO'
CON-0352 | PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Data Quality / Taxonomy Constraint | Confirm Engagement Cycle with SEO Team has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for SEO / Analytics / Public Web / All / All / All. | High | High | In Progress | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | SEO Analytics | 4 | SEO Analytics row 4 ¦ task='Confirm Engagement Cycle with SEO Team' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=No ¦ comment='Final Approval will be provided by the CMO'
CON-0353 | PRG-0163 | SEO / Analytics | TBC | Public Web | All | All | All |  | SEO Requirements to Dev Team | Accountability Constraint | SEO Requirements to Dev Team has no named owner | No owner is recorded for the SEO / Analytics item 'SEO Requirements to Dev Team'. This constrains accountability for SEO / Analytics / Public Web / All / All / All. | High | High | TBC | 100 | Assign a named accountable owner or workstream lead. | SEO Analytics | 5 | SEO Analytics row 5 ¦ task='SEO Requirements to Dev Team' ¦ priority=High ¦ status=TBC ¦ confidence=100% ¦ upstream=No
CON-0354 | PRG-0163 | SEO / Analytics | TBC | Public Web | All | All | All |  | SEO Requirements to Dev Team | Data Quality / Taxonomy Constraint | SEO Requirements to Dev Team has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Status missing. This constrains clean ingestion and reporting for SEO / Analytics / Public Web / All / All / All. | High | High | TBC | 100 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | SEO Analytics | 5 | SEO Analytics row 5 ¦ task='SEO Requirements to Dev Team' ¦ priority=High ¦ status=TBC ¦ confidence=100% ¦ upstream=No
CON-0355 | PRG-0164 | OMAR | TBC | Public Web | OMAR | OMAR | OMAR | OMAR / TBC | Engagement required to communicate recalibration of project to various OMAR Stakeholder | Accountability Constraint | Engagement required to communicate recalibration of project to various OMAR Stakeholder has no named owner | No owner is recorded for the OMAR item 'Engagement required to communicate recalibration of project to various OMAR Stakeholder'. This constrains accountability for OMAR / Public Web / OMAR / OMAR / OMAR. | Critical | Critical | In Progress | 70 | Assign a named accountable owner or workstream lead. | OMAR | 4 | OMAR row 4 ¦ task='Engagement required to communicate recalibration of project to various OMAR Stakeholder' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=No ¦ dependency='Nothing , we need a clear communications plan for OMAR' ¦ comment='Engagement with OMAR teams are required in order to assist them with the recalibration of their plans, the plan must take into account Navigation and plan changes'
CON-0356 | PRG-0164 | OMAR | TBC | Public Web | OMAR | OMAR | OMAR | OMAR / TBC | Engagement required to communicate recalibration of project to various OMAR Stakeholder | Data Quality / Taxonomy Constraint | Engagement required to communicate recalibration of project to various OMAR Stakeholder has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / OMAR / OMAR. | Critical | Critical | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 4 | OMAR row 4 ¦ task='Engagement required to communicate recalibration of project to various OMAR Stakeholder' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=No ¦ dependency='Nothing , we need a clear communications plan for OMAR' ¦ comment='Engagement with OMAR teams are required in order to assist them with the recalibration of their plans, the plan must take into account Navigation and plan changes'
CON-0357 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0358 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0359 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0360 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0361 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0362 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0363 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0364 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0365 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0366 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0367 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0368 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0369 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0370 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0371 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0372 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0373 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0374 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Kenya / Kenya. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0375 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0376 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0377 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0378 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0379 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0380 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0381 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0382 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0383 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0384 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0385 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0386 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Rwanda / Rwanda. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0387 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0388 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0389 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0390 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0391 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0392 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Uganda / Uganda. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0393 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0394 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0395 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0396 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0397 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0398 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Sequencing Constraint | Publishing of all pages in V2 New platform is constrained by delivery sequencing | The source notes show that Publishing of all pages in V2 New platform can only proceed after a prior state or milestone is reached. Evidence: Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This constrains execution order for OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | High | High | Not Started | 10 | Add the prerequisite milestone to the integrated plan and link it to this item. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
CON-0399 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Schedule Constraint | Publishing of all pages in V2 New platform has incomplete schedule detail | The planned schedule for Publishing of all pages in V2 New platform is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
CON-0400 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Effort / Capacity Constraint | Publishing of all pages in V2 New platform has incomplete or non-standard effort estimate | The effort value for Publishing of all pages in V2 New platform is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
CON-0401 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Confidence / Planning Constraint | Publishing of all pages in V2 New platform has low delivery confidence | The confidence level for Publishing of all pages in V2 New platform is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
CON-0402 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Accountability Constraint | Publishing of all pages in V2 New platform has no named owner | No owner is recorded for the OMAR item 'Publishing of all pages in V2 New platform'. This constrains accountability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
CON-0403 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Data Quality / Taxonomy Constraint | Publishing of all pages in V2 New platform has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
CON-0404 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Confidence / Planning Constraint | Travel Insurance Sales Migration has low delivery confidence | The confidence level for Travel Insurance Sales Migration is 40%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0405 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Accountability Constraint | Travel Insurance Sales Migration has no named owner | No owner is recorded for the OMAR item 'Travel Insurance Sales Migration'. This constrains accountability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Assign a named accountable owner or workstream lead. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0406 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Data Quality / Taxonomy Constraint | Travel Insurance Sales Migration has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0407 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Confidence / Planning Constraint | Mvest has low delivery confidence | The confidence level for Mvest is 40%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0408 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Accountability Constraint | Mvest has no named owner | No owner is recorded for the OMAR item 'Mvest'. This constrains accountability for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Assign a named accountable owner or workstream lead. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0409 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Data Quality / Taxonomy Constraint | Mvest has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Ghana / Ghana. | High | High | In Progress | 40 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
CON-0410 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Confidence / Planning Constraint | Personal Loan Application has low delivery confidence | The confidence level for Personal Loan Application is 50%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0411 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Accountability Constraint | Personal Loan Application has no named owner | No owner is recorded for the OMAR item 'Personal Loan Application'. This constrains accountability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Assign a named accountable owner or workstream lead. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0412 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Data Quality / Taxonomy Constraint | Personal Loan Application has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0413 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Confidence / Planning Constraint | Personal Loan Repayment Calculator has low delivery confidence | The confidence level for Personal Loan Repayment Calculator is 50%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0414 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Accountability Constraint | Personal Loan Repayment Calculator has no named owner | No owner is recorded for the OMAR item 'Personal Loan Repayment Calculator'. This constrains accountability for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Assign a named accountable owner or workstream lead. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0415 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Data Quality / Taxonomy Constraint | Personal Loan Repayment Calculator has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Namibia / Namibia. | High | High | In Progress | 50 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
CON-0416 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Schedule Constraint | Migration of Secure Web has incomplete schedule detail | The planned schedule for Migration of Secure Web is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0417 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Effort / Capacity Constraint | Migration of Secure Web has incomplete or non-standard effort estimate | The effort value for Migration of Secure Web is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0418 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Confidence / Planning Constraint | Migration of Secure Web has low delivery confidence | The confidence level for Migration of Secure Web is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0419 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Accountability Constraint | Migration of Secure Web has no named owner | No owner is recorded for the OMAR item 'Migration of Secure Web'. This constrains accountability for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0420 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Data Quality / Taxonomy Constraint | Migration of Secure Web has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0421 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Resource Constraint | Migration of Secure Web is constrained by shared or limited resources | The source notes indicate resource pressure for Migration of Secure Web: Resource constraints 2 people looking after 2 platforms. This constrains delivery capacity for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
CON-0422 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Schedule Constraint | Service Transactions has incomplete schedule detail | The planned schedule for Service Transactions is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
CON-0423 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Effort / Capacity Constraint | Service Transactions has incomplete or non-standard effort estimate | The effort value for Service Transactions is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
CON-0424 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Confidence / Planning Constraint | Service Transactions has no confidence rating | No confidence level is recorded for Service Transactions. This constrains delivery certainty and prioritisation for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Capture confidence level and rationale. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
CON-0425 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Accountability Constraint | Service Transactions has no named owner | No owner is recorded for the OMAR item 'Service Transactions'. This constrains accountability for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Assign a named accountable owner or workstream lead. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
CON-0426 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Data Quality / Taxonomy Constraint | Service Transactions has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Secure Web / OMAR / Namibia / Namibia. | High | High | Not Started |  | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
CON-0427 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Schedule Constraint | Eswatini Funeral has incomplete schedule detail | The planned schedule for Eswatini Funeral is not fully confirmed. Start date status: Exact; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
CON-0428 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Effort / Capacity Constraint | Eswatini Funeral has incomplete or non-standard effort estimate | The effort value for Eswatini Funeral is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
CON-0429 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Accountability Constraint | Eswatini Funeral has no named owner | No owner is recorded for the OMAR item 'Eswatini Funeral'. This constrains accountability for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Assign a named accountable owner or workstream lead. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
CON-0430 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Data Quality / Taxonomy Constraint | Eswatini Funeral has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; Country taxonomy mismatch: source domain Ghana vs area Eswatini; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / eSwatini / eSwatini. | High | High | In Progress | 70 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
CON-0431 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Schedule Constraint | Funeral Claims - Servicing Journey has incomplete schedule detail | The planned schedule for Funeral Claims - Servicing Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0432 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Effort / Capacity Constraint | Funeral Claims - Servicing Journey has incomplete or non-standard effort estimate | The effort value for Funeral Claims - Servicing Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0433 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Confidence / Planning Constraint | Funeral Claims - Servicing Journey has low delivery confidence | The confidence level for Funeral Claims - Servicing Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0434 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Accountability Constraint | Funeral Claims - Servicing Journey has no named owner | No owner is recorded for the OMAR item 'Funeral Claims - Servicing Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Assign a named accountable owner or workstream lead. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0435 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Data Quality / Taxonomy Constraint | Funeral Claims - Servicing Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0436 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Resource Constraint | Funeral Claims - Servicing Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Funeral Claims - Servicing Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0437 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Schedule Constraint | Motor claims - Service Journey has incomplete schedule detail | The planned schedule for Motor claims - Service Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0438 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Effort / Capacity Constraint | Motor claims - Service Journey has incomplete or non-standard effort estimate | The effort value for Motor claims - Service Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0439 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Confidence / Planning Constraint | Motor claims - Service Journey has low delivery confidence | The confidence level for Motor claims - Service Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0440 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Accountability Constraint | Motor claims - Service Journey has no named owner | No owner is recorded for the OMAR item 'Motor claims - Service Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Assign a named accountable owner or workstream lead. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0441 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Data Quality / Taxonomy Constraint | Motor claims - Service Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0442 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Resource Constraint | Motor claims - Service Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Motor claims - Service Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | In Progress | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0443 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Schedule Constraint | Home owners claims- Service Journey has incomplete schedule detail | The planned schedule for Home owners claims- Service Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0444 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Effort / Capacity Constraint | Home owners claims- Service Journey has incomplete or non-standard effort estimate | The effort value for Home owners claims- Service Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0445 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Confidence / Planning Constraint | Home owners claims- Service Journey has low delivery confidence | The confidence level for Home owners claims- Service Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0446 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Accountability Constraint | Home owners claims- Service Journey has no named owner | No owner is recorded for the OMAR item 'Home owners claims- Service Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0447 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Data Quality / Taxonomy Constraint | Home owners claims- Service Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0448 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Resource Constraint | Home owners claims- Service Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Home owners claims- Service Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0449 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Schedule Constraint | Home content claims Service Journey has incomplete schedule detail | The planned schedule for Home content claims Service Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0450 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Effort / Capacity Constraint | Home content claims Service Journey has incomplete or non-standard effort estimate | The effort value for Home content claims Service Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0451 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Confidence / Planning Constraint | Home content claims Service Journey has low delivery confidence | The confidence level for Home content claims Service Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0452 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Accountability Constraint | Home content claims Service Journey has no named owner | No owner is recorded for the OMAR item 'Home content claims Service Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0453 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Data Quality / Taxonomy Constraint | Home content claims Service Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0454 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Resource Constraint | Home content claims Service Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Home content claims Service Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0455 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Schedule Constraint | Credit Life has incomplete schedule detail | The planned schedule for Credit Life is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0456 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Effort / Capacity Constraint | Credit Life has incomplete or non-standard effort estimate | The effort value for Credit Life is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0457 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Confidence / Planning Constraint | Credit Life has low delivery confidence | The confidence level for Credit Life is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0458 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Accountability Constraint | Credit Life has no named owner | No owner is recorded for the OMAR item 'Credit Life'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0459 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Data Quality / Taxonomy Constraint | Credit Life has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0460 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Resource Constraint | Credit Life is constrained by shared or limited resources | The source notes indicate resource pressure for Credit Life: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0461 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Schedule Constraint | Funeral Claims - Sales Journey has incomplete schedule detail | The planned schedule for Funeral Claims - Sales Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0462 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Effort / Capacity Constraint | Funeral Claims - Sales Journey has incomplete or non-standard effort estimate | The effort value for Funeral Claims - Sales Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0463 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Confidence / Planning Constraint | Funeral Claims - Sales Journey has low delivery confidence | The confidence level for Funeral Claims - Sales Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0464 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Accountability Constraint | Funeral Claims - Sales Journey has no named owner | No owner is recorded for the OMAR item 'Funeral Claims - Sales Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0465 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Data Quality / Taxonomy Constraint | Funeral Claims - Sales Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0466 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Resource Constraint | Funeral Claims - Sales Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Funeral Claims - Sales Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0467 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Schedule Constraint | Motor claims - Sales Journey has incomplete schedule detail | The planned schedule for Motor claims - Sales Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0468 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Effort / Capacity Constraint | Motor claims - Sales Journey has incomplete or non-standard effort estimate | The effort value for Motor claims - Sales Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0469 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Confidence / Planning Constraint | Motor claims - Sales Journey has low delivery confidence | The confidence level for Motor claims - Sales Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0470 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Accountability Constraint | Motor claims - Sales Journey has no named owner | No owner is recorded for the OMAR item 'Motor claims - Sales Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0471 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Data Quality / Taxonomy Constraint | Motor claims - Sales Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0472 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Resource Constraint | Motor claims - Sales Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Motor claims - Sales Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0473 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Schedule Constraint | Home owners claims- Sales Journey has incomplete schedule detail | The planned schedule for Home owners claims- Sales Journey is not fully confirmed. Start date status: TBC; end date status: TBC. This constrains roadmap sequencing for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm start date, end date, and whether the item is committed for the current roadmap. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0474 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Effort / Capacity Constraint | Home owners claims- Sales Journey has incomplete or non-standard effort estimate | The effort value for Home owners claims- Sales Journey is recorded as 'TBC', not a clean numeric day value. This constrains capacity planning for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Convert the effort into an agreed numeric day estimate or mark it explicitly as TBC. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0475 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Confidence / Planning Constraint | Home owners claims- Sales Journey has low delivery confidence | The confidence level for Home owners claims- Sales Journey is 10%, which is low for roadmap commitment. This constrains predictability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Review assumptions, blockers, and resourcing before treating the date as reliable. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0476 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Accountability Constraint | Home owners claims- Sales Journey has no named owner | No owner is recorded for the OMAR item 'Home owners claims- Sales Journey'. This constrains accountability for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Assign a named accountable owner or workstream lead. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0477 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Data Quality / Taxonomy Constraint | Home owners claims- Sales Journey has taxonomy or data-quality gaps | The item has data-quality flags: Owner missing; Start date tbc; End date tbc; Effort tbc; Upstream dependency marked yes but detail missing; OMAR country domain normalised to OMAR. This constrains clean ingestion and reporting for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Resolve the flagged taxonomy/data fields before platform upload if the target system requires complete classifications. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
CON-0478 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Resource Constraint | Home owners claims- Sales Journey is constrained by shared or limited resources | The source notes indicate resource pressure for Home owners claims- Sales Journey: Resources shared between Botswana and Eswatini. This constrains delivery capacity for OMAR / Public Web / OMAR / Botswana / Botswana. | High | High | Not Started | 10 | Confirm resource allocation, competing commitments, and whether additional support is required. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'

## UPLOAD_Dependencies
Dependency_ID | Linked_Programme_Record_ID | Workstream | Owner | Channel | Domain | Area_Journey | Cluster | Market | Related_Deliverable | Dependency_Type | Title | Detailed_Description | Dependency_Status | Priority | Status | Confidence_Percent | Required_Action | Source_Sheet | Source_Row | Source_Evidence
DEP-0001 | PRG-0001 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Navigation |  | Design navigation structure based on the IA | Upstream Delivery Dependency | Design navigation structure based on the IA depends on upstream delivery | Design navigation structure based on the IA is dependent on the upstream deliverable or team input recorded as: Though we have an agreed structure, there is a dependency on brand alignment. Even though there is structure, we may not have stressed tested everything.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Navigation. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 4 | Design Standards row 4 ¦ task='Design navigation structure based on the IA' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='Though we have an agreed structure, there is a dependency on brand alignment. Even though there is structure, we may not have stressed tested everything.' ¦ comment='This is about 90% complete, there is some changes based on testing and brand alignment (based on the approved interim brand). The DS team has paused this until we provide the amended nav structure.'
DEP-0002 | PRG-0002 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Navigation |  | Complete footer navigation structure based on the IA | Upstream Delivery Dependency | Complete footer navigation structure based on the IA depends on upstream delivery | Complete footer navigation structure based on the IA is dependent on the upstream deliverable or team input recorded as: Structure is agreed, we just need to finalise it with the actual AI and Nav items to display. We also need to remove the ribbon logo and update it as per the interim brand.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Navigation. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 5 | Design Standards row 5 ¦ task='Complete footer navigation structure based on the IA' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='Structure is agreed, we just need to finalise it with the actual AI and Nav items to display. We also need to remove the ribbon logo and update it as per the interim brand.' ¦ comment='This is about 70% complete, just need to align to approved interim Brand CI'
DEP-0003 | PRG-0003 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Landing Page Template | Upstream Delivery Dependency | Design Landing Page Template depends on upstream delivery | Design Landing Page Template is dependent on the upstream deliverable or team input recorded as: This requires input and alignment from who will be providing feedback and approval of templates like this.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | Critical | In Progress | 60 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 6 | Design Standards row 6 ¦ task='Design Landing Page Template' ¦ priority=Critical ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
DEP-0004 | PRG-0003 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Landing Page Template | Approval Dependency | Design Landing Page Template requires external input or approval | The source notes show that Design Landing Page Template requires additional input, approval, access, or collaboration before completion. Evidence: This requires input and alignment from who will be providing feedback and approval of templates like this.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | Critical | In Progress | 60 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 6 | Design Standards row 6 ¦ task='Design Landing Page Template' ¦ priority=Critical ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
DEP-0005 | PRG-0004 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Section Page Template | Upstream Delivery Dependency | Design Section Page Template depends on upstream delivery | Design Section Page Template is dependent on the upstream deliverable or team input recorded as: This requires input and alignment from who will be providing feedback and approval of templates like this.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | High | In Progress | 60 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 7 | Design Standards row 7 ¦ task='Design Section Page Template' ¦ priority=High ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
DEP-0006 | PRG-0004 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Section Page Template | Approval Dependency | Design Section Page Template requires external input or approval | The source notes show that Design Section Page Template requires additional input, approval, access, or collaboration before completion. Evidence: This requires input and alignment from who will be providing feedback and approval of templates like this.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | High | In Progress | 60 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 7 | Design Standards row 7 ¦ task='Design Section Page Template' ¦ priority=High ¦ status=In Progress ¦ confidence=60% ¦ upstream=Yes ¦ dependency='This requires input and alignment from who will be providing feedback and approval of templates like this.' ¦ comment='This work has started'
DEP-0007 | PRG-0005 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Finalise Category Page Template | Upstream Delivery Dependency | Finalise Category Page Template depends on upstream delivery | Finalise Category Page Template is dependent on the upstream deliverable or team input recorded as: This needs to be further stress tested, but Retirement and Funeral is in a place where we are communicating this to DS.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | High | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 8 | Design Standards row 8 ¦ task='Finalise Category Page Template' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='This needs to be further stress tested, but Retirement and Funeral is in a place where we are communicating this to DS.' ¦ comment='This is about 90% with the 2 categories designed.'
DEP-0008 | PRG-0006 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Finalise Product Page Template | Upstream Delivery Dependency | Finalise Product Page Template depends on upstream delivery | Finalise Product Page Template is dependent on the upstream deliverable or team input recorded as: This needs to be further stress tested, but Max Investments, Funeral Plan and FlexiSave is in a place where we are communicating this to DS.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | High | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 9 | Design Standards row 9 ¦ task='Finalise Product Page Template' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='This needs to be further stress tested, but Max Investments, Funeral Plan and FlexiSave is in a place where we are communicating this to DS.' ¦ comment='This is about 90% done with 3 product pages completed.'
DEP-0009 | PRG-0008 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: All Calculators | Upstream Delivery Dependency | Design Utility Template: All Calculators depends on upstream delivery | Design Utility Template: All Calculators is dependent on the upstream deliverable or team input recorded as: There is a lot of calculators that require a lot of input across different product and business clusters.. This affects Design Standards / Public Web / OMCOZA / Personal / Templates. | Open | High | In Progress | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 11 | Design Standards row 11 ¦ task='Design Utility Template: All Calculators' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There is a lot of calculators that require a lot of input across different product and business clusters.' ¦ comment='The work has started for both desktop and mobile.'
DEP-0010 | PRG-0008 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: All Calculators | Collaboration / Input Dependency | Design Utility Template: All Calculators requires external input or approval | The source notes show that Design Utility Template: All Calculators requires additional input, approval, access, or collaboration before completion. Evidence: There is a lot of calculators that require a lot of input across different product and business clusters.. This affects Design Standards / Public Web / OMCOZA / Personal / Templates. | Open | High | In Progress | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 11 | Design Standards row 11 ¦ task='Design Utility Template: All Calculators' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There is a lot of calculators that require a lot of input across different product and business clusters.' ¦ comment='The work has started for both desktop and mobile.'
DEP-0011 | PRG-0009 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: Calculators Page | Upstream Delivery Dependency | Design Utility Template: Calculators Page depends on upstream delivery | Design Utility Template: Calculators Page is dependent on the upstream deliverable or team input recorded as: There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.. This affects Design Standards / Public Web / OMCOZA / Personal / Templates. | Open | High | In Progress | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 12 | Design Standards row 12 ¦ task='Design Utility Template: Calculators Page' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.' ¦ comment='This work has started.'
DEP-0012 | PRG-0009 | Design Standards | Justin | Public Web | OMCOZA | Personal | Templates |  | Design Utility Template: Calculators Page | Collaboration / Input Dependency | Design Utility Template: Calculators Page requires external input or approval | The source notes show that Design Utility Template: Calculators Page requires additional input, approval, access, or collaboration before completion. Evidence: There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.. This affects Design Standards / Public Web / OMCOZA / Personal / Templates. | Open | High | In Progress | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 12 | Design Standards row 12 ¦ task='Design Utility Template: Calculators Page' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='There needs to be alignment around skinning and improving the experience. This does require input from business, product and tech.' ¦ comment='This work has started.'
DEP-0013 | PRG-0010 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Tenant |  | Design Tenant Template | Upstream Delivery Dependency | Design Tenant Template depends on upstream delivery | Design Tenant Template is dependent on the upstream deliverable or team input recorded as: This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Tenant. | Open | High | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 13 | Design Standards row 13 ¦ task='Design Tenant Template' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards.'
DEP-0014 | PRG-0010 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Tenant |  | Design Tenant Template | Collaboration / Input Dependency | Design Tenant Template requires external input or approval | The source notes show that Design Tenant Template requires additional input, approval, access, or collaboration before completion. Evidence: This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Tenant. | Open | High | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 13 | Design Standards row 13 ¦ task='Design Tenant Template' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='This requires understanding of the tenants and what they need. So at the moment we can reference OM Bank and Rewards.'
DEP-0015 | PRG-0012 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Template: Careers | Upstream Delivery Dependency | Design Utility Template: Careers depends on upstream delivery | Design Utility Template: Careers is dependent on the upstream deliverable or team input recorded as: This may require input from HC but if we are migrating the content as-is, then this could be a simple process.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | Medium | Not Started | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 15 | Design Standards row 15 ¦ task='Design Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='This may require input from HC but if we are migrating the content as-is, then this could be a simple process.'
DEP-0016 | PRG-0012 | Design Standards | Justin | Public Web | OMCOZA | Entire Site | Templates |  | Design Utility Template: Careers | Collaboration / Input Dependency | Design Utility Template: Careers requires external input or approval | The source notes show that Design Utility Template: Careers requires additional input, approval, access, or collaboration before completion. Evidence: This may require input from HC but if we are migrating the content as-is, then this could be a simple process.. This affects Design Standards / Public Web / OMCOZA / Entire Site / Templates. | Open | Medium | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 15 | Design Standards row 15 ¦ task='Design Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='This may require input from HC but if we are migrating the content as-is, then this could be a simple process.'
DEP-0017 | PRG-0013 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation structure based on the IA | Upstream Delivery Dependency | Design navigation structure based on the IA depends on upstream delivery | Design navigation structure based on the IA is dependent on the upstream deliverable or team input recorded as: Initial designs have been done, it requires further discussion of how the pieces need to fit.. This affects Design Standards / Secure Web / MyOM / Entire Site / Navigation. | Open | High | In Progress | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 16 | Design Standards row 16 ¦ task='Design navigation structure based on the IA' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Initial designs have been done, it requires further discussion of how the pieces need to fit.' ¦ comment='Initial designs has started.'
DEP-0018 | PRG-0013 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation structure based on the IA | Collaboration / Input Dependency | Design navigation structure based on the IA requires external input or approval | The source notes show that Design navigation structure based on the IA requires additional input, approval, access, or collaboration before completion. Evidence: Initial designs have been done, it requires further discussion of how the pieces need to fit.. This affects Design Standards / Secure Web / MyOM / Entire Site / Navigation. | Open | High | In Progress | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Standards | 16 | Design Standards row 16 ¦ task='Design navigation structure based on the IA' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Initial designs have been done, it requires further discussion of how the pieces need to fit.' ¦ comment='Initial designs has started.'
DEP-0019 | PRG-0014 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation |  | Design navigation solution to allow access to other secure sites | Unspecified Upstream Dependency | Design navigation solution to allow access to other secure sites has an unnamed upstream dependency | Design navigation solution to allow access to other secure sites is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects Design Standards / Secure Web / MyOM / Entire Site / Navigation and prevents clean dependency tracking. | Open | High | In Progress | 70 | Capture the specific upstream deliverable, owner, and required completion date. | Design Standards | 17 | Design Standards row 17 ¦ task='Design navigation solution to allow access to other secure sites' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes
DEP-0020 | PRG-0015 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise generic copy standards | Upstream Delivery Dependency | Finalise generic copy standards depends on upstream delivery | Finalise generic copy standards is dependent on the upstream deliverable or team input recorded as: Alignment with Group Marketing. This affects Design Standards / TBC / Old Mutual Design Standards / Generic / Copy. | Closed / Monitor | Critical | Ready | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 18 | Design Standards row 18 ¦ task='Finalise generic copy standards' ¦ priority=Critical ¦ status=Ready ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='We are ready for sign off, it is aligned to brand and are requesting us to send to them for their records.'
DEP-0021 | PRG-0016 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy |  | Finalise SEO + AIEO standards | Upstream Delivery Dependency | Finalise SEO + AIEO standards depends on upstream delivery | Finalise SEO + AIEO standards is dependent on the upstream deliverable or team input recorded as: Alignment with Group Marketing. This affects Design Standards / TBC / Old Mutual Design Standards / Generic / Copy. | Closed / Monitor | Critical | Ready | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 19 | Design Standards row 19 ¦ task='Finalise SEO + AIEO standards' ¦ priority=Critical ¦ status=Ready ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='SEO is also in progress with their own standards, so our standards will be a living process and document'
DEP-0022 | PRG-0017 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | CI |  | Align DS to iterim Brand CI | Upstream Delivery Dependency | Align DS to iterim Brand CI depends on upstream delivery | Align DS to iterim Brand CI is dependent on the upstream deliverable or team input recorded as: Alignment with Group Marketing. This affects Design Standards / TBC / Old Mutual Design Standards / Generic / CI. | Open | High | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 20 | Design Standards row 20 ¦ task='Align DS to iterim Brand CI' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Alignment with Group Marketing' ¦ comment='The Interim Brand CI has been approved, luckily no major changes and just need align DS to brand.'
DEP-0023 | PRG-0018 | Design Standards | Justin | Public Web | OMCOZA | OM Bank | Tenant |  | Design OM Bank Tenant site (structure) | Upstream Delivery Dependency | Design OM Bank Tenant site (structure) depends on upstream delivery | Design OM Bank Tenant site (structure) is dependent on the upstream deliverable or team input recorded as: Alignment with OM Bank but also OMF. This affects Design Standards / Public Web / OMCOZA / OM Bank / Tenant. | Open | Low | Not Started | 20 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 21 | Design Standards row 21 ¦ task='Design OM Bank Tenant site (structure)' ¦ priority=Low ¦ status=Not Started ¦ confidence=20% ¦ upstream=Yes ¦ dependency='Alignment with OM Bank but also OMF' ¦ comment='We need to have initial conversations around OM Bank and if OMF falls under their domain which means they will need to design and build out their screens and IA.'
DEP-0024 | PRG-0019 | Design Standards | Justin | Public Web | OMCOZA | Rewards | Tenant |  | Design Rewards Tenant Site | Upstream Delivery Dependency | Design Rewards Tenant Site depends on upstream delivery | Design Rewards Tenant Site is dependent on the upstream deliverable or team input recorded as: Rewards is in progress with a redeisgn / revamp. So we will be using their existing structure and content.. This affects Design Standards / Public Web / OMCOZA / Rewards / Tenant. | Open | Low | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 22 | Design Standards row 22 ¦ task='Design Rewards Tenant Site' ¦ priority=Low ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Rewards is in progress with a redeisgn / revamp. So we will be using their existing structure and content.' ¦ comment='For the initial migration - we are keeping to their existing structure and content while they go through their redesign.'
DEP-0025 | PRG-0020 | Design Standards | Justin | Public Web | OMCOZA | Insure / iWyze | Tenant |  | Design iWyze Tenant Product Page Template | Upstream Delivery Dependency | Design iWyze Tenant Product Page Template depends on upstream delivery | Design iWyze Tenant Product Page Template is dependent on the upstream deliverable or team input recorded as: Alignment with OMF as well as the actual tenant.. This affects Design Standards / Public Web / OMCOZA / Insure / iWyze / Tenant. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Standards | 23 | Design Standards row 23 ¦ task='Design iWyze Tenant Product Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Alignment with OMF as well as the actual tenant.'
DEP-0026 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Retirement. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
DEP-0027 | PRG-0021 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Retirement. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 4 | Design Delivery row 4 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need stakeholder sessions in diaries already locked in for the the programme duration. Sign-off process defined.' ¦ comment='Dependencies * Stakeholder socialisation and buy-in: Must be completed prior to engagement commencing. * Active stakeholder participation is required throughout: As extended team members and thinking partners, not passive reviewers. * A clearly defined sign-off process: Must be in place before work begins. Risks * SEO standards not finalised: SEO governance is still being developed. Content decisions may need to be revisited as standards are finalised, making this a living document process rather than a single sign-off. * Tenant hierarchy misalignment: Some clusters (e.g. OM Insure) have not yet aligned to sharing a platform / real estate with internal tenant brands (e.g. iWyze). This has the potential to create structural conflict in our section and category templates and may require additional stakeholder resolution time. * Scope creep: Timelines are based on an agreed list of sites (OMCOZA, OMCOM, Bula Tsela, and LTD) and agreed scope. Any additional sites or out-of-scope requests will require a formal timeline and resource extension. Web and My Old Mutual (Secure): Unfamiliar territory - Additional timeshas been allocated to them, however, we have a number of unknowns in those two streams.'
DEP-0028 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Funeral. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0029 | PRG-0022 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Funeral. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 5 | Design Delivery row 5 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0030 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0031 | PRG-0023 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Investment > Flexi Save. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 6 | Design Delivery row 6 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0032 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Upstream Delivery Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on upstream delivery | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Entire Site. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0033 | PRG-0024 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires external input or approval | The source notes show that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Entire Site. | Open | Critical | In Progress | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 7 | Design Delivery row 7 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0034 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Upstream Delivery Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on upstream delivery | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Entire Site. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0035 | PRG-0025 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires external input or approval | The source notes show that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Entire Site. | Open | Critical | In Progress | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 8 | Design Delivery row 8 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0036 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Upstream Delivery Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on upstream delivery | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0037 | PRG-0026 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires external input or approval | The source notes show that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Entire Site. | Open | Critical | In Progress | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 9 | Design Delivery row 9 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0038 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Upstream Delivery Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) depends on upstream delivery | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0039 | PRG-0027 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site |  | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Approval Dependency | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires external input or approval | The source notes show that Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Entire Site. | Open | Critical | In Progress | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 10 | Design Delivery row 10 ¦ task='Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0040 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Upstream Delivery Dependency | Audience landing with enhanced copy depends on upstream delivery | Audience landing with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0041 | PRG-0029 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing |  | Audience landing with enhanced copy | Approval Dependency | Audience landing with enhanced copy requires external input or approval | The source notes show that Audience landing with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Personal Landing. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 12 | Design Delivery row 12 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0042 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Invest. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0043 | PRG-0030 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Invest. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 13 | Design Delivery row 13 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0044 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / OM Bank. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0045 | PRG-0031 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank |  | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / OM Bank. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 14 | Design Delivery row 14 ¦ task='L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0046 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Insure. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0047 | PRG-0032 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Insure. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 15 | Design Delivery row 15 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0048 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / About us. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0049 | PRG-0033 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / About us. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 16 | Design Delivery row 16 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0050 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Careers. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0051 | PRG-0034 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / Careers. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 17 | Design Delivery row 17 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0052 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Upstream Delivery Dependency | Mapping of new IA and Footer to sxisting site structure depends on upstream delivery | Mapping of new IA and Footer to sxisting site structure is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0053 | PRG-0035 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Dependency | Mapping of new IA and Footer to sxisting site structure requires external input or approval | The source notes show that Mapping of new IA and Footer to sxisting site structure requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOM / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 18 | Design Delivery row 18 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0054 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Upstream Delivery Dependency | Mapping of new IA and Footer to sxisting site structure depends on upstream delivery | Mapping of new IA and Footer to sxisting site structure is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0055 | PRG-0036 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Dependency | Mapping of new IA and Footer to sxisting site structure requires external input or approval | The source notes show that Mapping of new IA and Footer to sxisting site structure requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / Bula Tsela / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 19 | Design Delivery row 19 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0056 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Upstream Delivery Dependency | Mapping of new IA and Footer to sxisting site structure depends on upstream delivery | Mapping of new IA and Footer to sxisting site structure is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0057 | PRG-0037 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site |  | Mapping of new IA and Footer to sxisting site structure | Approval Dependency | Mapping of new IA and Footer to sxisting site structure requires external input or approval | The source notes show that Mapping of new IA and Footer to sxisting site structure requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / Learn Think Do (LTD) / Entire Site / Entire Site. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 20 | Design Delivery row 20 ¦ task='Mapping of new IA and Footer to sxisting site structure' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0058 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Upstream Delivery Dependency | Audience landing with enhanced copy depends on upstream delivery | Audience landing with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. | Open | Critical | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0059 | PRG-0038 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing |  | Audience landing with enhanced copy | Approval Dependency | Audience landing with enhanced copy requires external input or approval | The source notes show that Audience landing with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Wealth Landing. | Open | Critical | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 21 | Design Delivery row 21 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0060 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Invest. | Open | Critical | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0061 | PRG-0039 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Invest. | Open | Critical | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 22 | Design Delivery row 22 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0062 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Plan. | Open | Critical | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0063 | PRG-0040 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Plan. | Open | Critical | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 23 | Design Delivery row 23 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0064 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / About. | Open | Critical | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0065 | PRG-0041 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / About. | Open | Critical | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 24 | Design Delivery row 24 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0066 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Insights. | Open | Critical | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0067 | PRG-0042 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Wealth / Insights. | Open | Critical | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 25 | Design Delivery row 25 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0068 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Upstream Delivery Dependency | Audience landing with enhanced copy depends on upstream delivery | Audience landing with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0069 | PRG-0043 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing |  | Audience landing with enhanced copy | Approval Dependency | Audience landing with enhanced copy requires external input or approval | The source notes show that Audience landing with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Corporate Landing. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 26 | Design Delivery row 26 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0070 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Employees. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0071 | PRG-0044 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Employees. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 27 | Design Delivery row 27 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0072 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Employers. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0073 | PRG-0045 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Employers. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 28 | Design Delivery row 28 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0074 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Services. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0075 | PRG-0046 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Corporate / Services. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 29 | Design Delivery row 29 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0076 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Upstream Delivery Dependency | Audience landing with enhanced copy depends on upstream delivery | Audience landing with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Business Landing. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0077 | PRG-0047 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing |  | Audience landing with enhanced copy | Approval Dependency | Audience landing with enhanced copy requires external input or approval | The source notes show that Audience landing with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Business Landing. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 30 | Design Delivery row 30 ¦ task='Audience landing with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0078 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Insure. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0079 | PRG-0048 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Insure. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 31 | Design Delivery row 31 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0080 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Invest. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0081 | PRG-0049 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Invest. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 32 | Design Delivery row 32 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0082 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Protect. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0083 | PRG-0050 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Protect. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 33 | Design Delivery row 33 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0084 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Guarantee. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0085 | PRG-0051 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Guarantee. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 34 | Design Delivery row 34 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0086 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Upstream Delivery Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy depends on upstream delivery | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Tools. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0087 | PRG-0052 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools |  | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Approval Dependency | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires external input or approval | The source notes show that L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Business / Tools. | Open | Critical | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 35 | Design Delivery row 35 ¦ task='L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0088 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Upstream Delivery Dependency | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. depends on upstream delivery | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. | Open | Critical | TBC | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0089 | PRG-0053 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual |  | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Approval Dependency | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. requires external input or approval | The source notes show that Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMCOZA / Personal / My OldMutual. | Open | Critical | TBC | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 36 | Design Delivery row 36 ¦ task='Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.' ¦ priority=Critical ¦ status=TBC ¦ confidence=70% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0090 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Upstream Delivery Dependency | Socilaisation of defined IA and Page templates for handover. depends on upstream delivery | Socilaisation of defined IA and Page templates for handover. is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. | Open | High | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0091 | PRG-0054 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Approval Dependency | Socilaisation of defined IA and Page templates for handover. requires external input or approval | The source notes show that Socilaisation of defined IA and Page templates for handover. requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMAR: Kenya / Entire Site / Entire Site. | Open | High | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 37 | Design Delivery row 37 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0092 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Upstream Delivery Dependency | Socilaisation of defined IA and Page templates for handover. depends on upstream delivery | Socilaisation of defined IA and Page templates for handover. is dependent on the upstream deliverable or team input recorded as: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. | Open | High | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0093 | PRG-0055 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site |  | Socilaisation of defined IA and Page templates for handover. | Approval Dependency | Socilaisation of defined IA and Page templates for handover. requires external input or approval | The source notes show that Socilaisation of defined IA and Page templates for handover. requires additional input, approval, access, or collaboration before completion. Evidence: We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.. This affects Design Delivery / Public Web / OMAR: Zimbabwe / Entire Site / Entire Site. | Open | High | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Design Delivery | 38 | Design Delivery row 38 ¦ task='Socilaisation of defined IA and Page templates for handover.' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='We need Stakeholder sessions in diaries already locked in for the July Start. Sign-off process defined.'
DEP-0094 | PRG-0056 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Retirement |  | Copy enhancement + link mapping dependent on design activities | Upstream Delivery Dependency | Copy enhancement + link mapping dependent on design activities depends on upstream delivery | Copy enhancement + link mapping dependent on design activities is dependent on the upstream deliverable or team input recorded as: Design readiness. This affects Content Readiness / Public Web / OMCOZA / Personal / Retirement. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Content Readiness | 4 | Content Readiness row 4 ¦ task='Copy enhancement + link mapping dependent on design activities' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Design readiness'
DEP-0095 | PRG-0057 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Funeral |  | Copy enhancement + link mapping dependent on design activities | Upstream Delivery Dependency | Copy enhancement + link mapping dependent on design activities depends on upstream delivery | Copy enhancement + link mapping dependent on design activities is dependent on the upstream deliverable or team input recorded as: Design readiness. This affects Content Readiness / Public Web / OMCOZA / Personal / Funeral. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Content Readiness | 5 | Content Readiness row 5 ¦ task='Copy enhancement + link mapping dependent on design activities' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Design readiness'
DEP-0096 | PRG-0058 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Invest Flexi Save |  | Copy enhancement + link mapping dependent on design activities | Upstream Delivery Dependency | Copy enhancement + link mapping dependent on design activities depends on upstream delivery | Copy enhancement + link mapping dependent on design activities is dependent on the upstream deliverable or team input recorded as: Design readiness. This affects Content Readiness / Public Web / OMCOZA / Personal / Invest Flexi Save. | Open | Critical | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Content Readiness | 6 | Content Readiness row 6 ¦ task='Copy enhancement + link mapping dependent on design activities' ¦ priority=Critical ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Design readiness'
DEP-0097 | PRG-0059 | Content Readiness | Natalie Patel | Public Web | OMCOZA | Personal | Personal landing page |  | Copy enhancement + link mapping dependent on design activities | Upstream Delivery Dependency | Copy enhancement + link mapping dependent on design activities depends on upstream delivery | Copy enhancement + link mapping dependent on design activities is dependent on the upstream deliverable or team input recorded as: Design readiness. This affects Content Readiness / Public Web / OMCOZA / Personal / Personal landing page. | Open | Critical | In Progress | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Content Readiness | 7 | Content Readiness row 7 ¦ task='Copy enhancement + link mapping dependent on design activities' ¦ priority=Critical ¦ status=In Progress ¦ confidence=100% ¦ upstream=Yes ¦ dependency='Design readiness'
DEP-0098 | PRG-0060 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All |  | Portfolio View | Upstream Delivery Dependency | Portfolio View depends on upstream delivery | Portfolio View is dependent on the upstream deliverable or team input recorded as: Part of the design work that is underway - not included in the number of journeys currently tracked. This affects Feature Delivery / Secure Web / Shared / Platform / Dashboard Views ( Porffolio Views) / All. | Open | High | In Progress | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Feature Delivery | 4 | Feature Delivery row 4 ¦ task='Portfolio View' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Part of the design work that is underway - not included in the number of journeys currently tracked' ¦ comment='The dedicated Servicing team has limited availability, with three resources only confirmed until 10 September and one QE rolling off in August. This creates a significant delivery risk, as all required work must be completed'
DEP-0099 | PRG-0062 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Content Updates | Upstream Delivery Dependency | Content Updates depends on upstream delivery | Content Updates is dependent on the upstream deliverable or team input recorded as: Content Updates to be confirmed. This affects Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | Open | High | Blocked | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Feature Delivery | 6 | Feature Delivery row 6 ¦ task='Content Updates' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Content Updates to be confirmed' ¦ comment='.'
DEP-0100 | PRG-0063 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All |  | Journeys Optimization | Upstream Delivery Dependency | Journeys Optimization depends on upstream delivery | Journeys Optimization is dependent on the upstream deliverable or team input recorded as: Journey Optimisation to be confirmed. This affects Feature Delivery / Secure Web / Shared / Platform / Servicing Transaction in Sec Web / All. | Open | High | Blocked | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Feature Delivery | 7 | Feature Delivery row 7 ¦ task='Journeys Optimization' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Journey Optimisation to be confirmed' ¦ comment='.'
DEP-0101 | PRG-0072 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Easy Plus Sales Jorurney on Public Web | Upstream Delivery Dependency | Easy Plus Sales Jorurney on Public Web depends on upstream delivery | Easy Plus Sales Jorurney on Public Web is dependent on the upstream deliverable or team input recorded as: product page has to be updated before this journey can be migrated. This affects Feature Delivery / Public Web / OMCOZA / Personal / L&S. | Open | High | Blocked | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Feature Delivery | 16 | Feature Delivery row 16 ¦ task='Easy Plus Sales Jorurney on Public Web' ¦ priority=High ¦ status=Blocked ¦ confidence=10% ¦ upstream=Yes ¦ dependency='product page has to be updated before this journey can be migrated' ¦ comment='.'
DEP-0102 | PRG-0074 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S |  | Find Advisor | Upstream Delivery Dependency | Find Advisor depends on upstream delivery | Find Advisor is dependent on the upstream deliverable or team input recorded as: Design - Impact of of new templates on Find Advisor flow. This affects Feature Delivery / Public Web / OMCOZA / Personal / L&S. | Open | High | In Progress | 90 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Feature Delivery | 18 | Feature Delivery row 18 ¦ task='Find Advisor' ¦ priority=High ¦ status=In Progress ¦ confidence=90% ¦ upstream=Yes ¦ dependency='Design - Impact of of new templates on Find Advisor flow' ¦ comment='TBC'
DEP-0103 | PRG-0082 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop CI Updates onto OMDSv2 | Upstream Delivery Dependency | Design and Develop CI Updates onto OMDSv2 depends on upstream delivery | Design and Develop CI Updates onto OMDSv2 is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | High | Blocked | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 4 | Design Systems row 4 ¦ task='Design and Develop CI Updates onto OMDSv2' ¦ priority=High ¦ status=Blocked ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0104 | PRG-0083 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Upstream Delivery Dependency | Design and Develop Top Navigation Component Updates depends on upstream delivery | Design and Develop Top Navigation Component Updates is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Critical | In Progress | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 5 | Design Systems row 5 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery' ¦ comment='Started, but had to pause due to rework upstream.'
DEP-0105 | PRG-0084 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop Top Navigation Component Updates | Upstream Delivery Dependency | Design and Develop Top Navigation Component Updates depends on upstream delivery | Design and Develop Top Navigation Component Updates is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Secure Web / All / All / All. | Open | Critical | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 6 | Design Systems row 6 ¦ task='Design and Develop Top Navigation Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0106 | PRG-0085 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Footer Component Updates | Upstream Delivery Dependency | Design and Develop Footer Component Updates depends on upstream delivery | Design and Develop Footer Component Updates is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Critical | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 7 | Design Systems row 7 ¦ task='Design and Develop Footer Component Updates' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0107 | PRG-0086 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Card Component Updates | Upstream Delivery Dependency | Design and Develop Card Component Updates depends on upstream delivery | Design and Develop Card Component Updates is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 8 | Design Systems row 8 ¦ task='Design and Develop Card Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0108 | PRG-0087 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Category Page Template | Upstream Delivery Dependency | Design and Develop Category Page Template depends on upstream delivery | Design and Develop Category Page Template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | High | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 9 | Design Systems row 9 ¦ task='Design and Develop Category Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0109 | PRG-0088 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Product Detail Page Template | Upstream Delivery Dependency | Design and Develop Product Detail Page Template depends on upstream delivery | Design and Develop Product Detail Page Template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | High | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 10 | Design Systems row 10 ¦ task='Design and Develop Product Detail Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0110 | PRG-0089 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Article Page Template | Upstream Delivery Dependency | Design and Develop Article Page Template depends on upstream delivery | Design and Develop Article Page Template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | High | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 11 | Design Systems row 11 ¦ task='Design and Develop Article Page Template' ¦ priority=High ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0111 | PRG-0090 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Hero Banner Component Updates | Upstream Delivery Dependency | Design and Develop Hero Banner Component Updates depends on upstream delivery | Design and Develop Hero Banner Component Updates is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 12 | Design Systems row 12 ¦ task='Design and Develop Hero Banner Component Updates' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0112 | PRG-0091 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Landing page template | Upstream Delivery Dependency | Design and Develop Landing page template depends on upstream delivery | Design and Develop Landing page template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 13 | Design Systems row 13 ¦ task='Design and Develop Landing page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0113 | PRG-0092 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Section page template | Upstream Delivery Dependency | Design and Develop Section page template depends on upstream delivery | Design and Develop Section page template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 14 | Design Systems row 14 ¦ task='Design and Develop Section page template' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0114 | PRG-0093 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Contact Us | Upstream Delivery Dependency | Design and Develop Utility Template: Contact Us depends on upstream delivery | Design and Develop Utility Template: Contact Us is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 15 | Design Systems row 15 ¦ task='Design and Develop Utility Template: Contact Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0115 | PRG-0094 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: All Calculators | Upstream Delivery Dependency | Design and Develop Utility Template: All Calculators depends on upstream delivery | Design and Develop Utility Template: All Calculators is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 16 | Design Systems row 16 ¦ task='Design and Develop Utility Template: All Calculators' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0116 | PRG-0095 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Calculators Page | Upstream Delivery Dependency | Design and Develop Utility Template: Calculators Page depends on upstream delivery | Design and Develop Utility Template: Calculators Page is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 17 | Design Systems row 17 ¦ task='Design and Develop Utility Template: Calculators Page' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0117 | PRG-0096 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Templates: About Us | Upstream Delivery Dependency | Design and Develop Utility Templates: About Us depends on upstream delivery | Design and Develop Utility Templates: About Us is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 18 | Design Systems row 18 ¦ task='Design and Develop Utility Templates: About Us' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0118 | PRG-0097 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop Utility Template: Careers | Upstream Delivery Dependency | Design and Develop Utility Template: Careers depends on upstream delivery | Design and Develop Utility Template: Careers is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 19 | Design Systems row 19 ¦ task='Design and Develop Utility Template: Careers' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0119 | PRG-0098 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Add copy standards to OMDS | Upstream Delivery Dependency | Add copy standards to OMDS depends on upstream delivery | Add copy standards to OMDS is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 20 | Design Systems row 20 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0120 | PRG-0099 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Add copy standards to OMDS | Upstream Delivery Dependency | Add copy standards to OMDS depends on upstream delivery | Add copy standards to OMDS is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Secure Web / All / All / All. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 21 | Design Systems row 21 ¦ task='Add copy standards to OMDS' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0121 | PRG-0100 | Design Systems | Brent van Zitters | Public Web | All | All | All |  | Design and Develop tenant template | Upstream Delivery Dependency | Design and Develop tenant template depends on upstream delivery | Design and Develop tenant template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Public Web / All / All / All. | Open | Medium | TBC | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 22 | Design Systems row 22 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0122 | PRG-0101 | Design Systems | Brent van Zitters | Secure Web | All | All | All |  | Design and Develop tenant template | Upstream Delivery Dependency | Design and Develop tenant template depends on upstream delivery | Design and Develop tenant template is dependent on the upstream deliverable or team input recorded as: Foundational elements from Design Delivery. This affects Design Systems / Secure Web / All / All / All. | Open | Medium | TBC | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Design Systems | 23 | Design Systems row 23 ¦ task='Design and Develop tenant template' ¦ priority=Medium ¦ status=TBC ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Foundational elements from Design Delivery'
DEP-0123 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Upstream Delivery Dependency | Implement OMCOM into production depends on upstream delivery | Implement OMCOM into production is dependent on the upstream deliverable or team input recorded as: Stakeholder sign off. This affects Execution / Public Web / OMCOM / All / OM. | Open | High | In Progress | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
DEP-0124 | PRG-0102 | Execution | TBC | Public Web | OMCOM | All | OM |  | Implement OMCOM into production | Approval Dependency | Implement OMCOM into production requires external input or approval | The source notes show that Implement OMCOM into production requires additional input, approval, access, or collaboration before completion. Evidence: Stakeholder sign off. This affects Execution / Public Web / OMCOM / All / OM. | Open | High | In Progress | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 4 | Execution row 4 ¦ task='Implement OMCOM into production' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Stakeholder sign off' ¦ comment='Awaiting stakeholder approval'
DEP-0125 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Upstream Delivery Dependency | Dev: Observability Dashboard Templates for Sites depends on upstream delivery | Dev: Observability Dashboard Templates for Sites is dependent on the upstream deliverable or team input recorded as: V2 DesignSystem update. This affects Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Open | Critical | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
DEP-0126 | PRG-0112 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Observability Dashboard Templates for Sites | Collaboration / Input Dependency | Dev: Observability Dashboard Templates for Sites requires external input or approval | The source notes show that Dev: Observability Dashboard Templates for Sites requires additional input, approval, access, or collaboration before completion. Evidence: V2 DesignSystem update. This affects Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Open | Critical | Not Started | 70 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 14 | Execution row 14 ¦ task='Dev: Observability Dashboard Templates for Sites' ¦ priority=Critical ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='V2 DesignSystem update' ¦ comment='Awaiting update to current V2 DesignSystem to allow for different background color'
DEP-0127 | PRG-0113 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ModularPage | Upstream Delivery Dependency | Dev: Styling Backwards Compatibility - V2 ModularPage depends on upstream delivery | Dev: Styling Backwards Compatibility - V2 ModularPage is dependent on the upstream deliverable or team input recorded as: DesignSystem V2 Styling updates for background. This affects Execution / Public Web / All / All / Shared / All / TBC. | Open | Critical | Not Started | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 18 | Execution row 18 ¦ task='Dev: Styling Backwards Compatibility - V2 ModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
DEP-0128 | PRG-0114 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Upstream Delivery Dependency | Dev: Styling Backwards Compatibility - V2 ArticleModularPage depends on upstream delivery | Dev: Styling Backwards Compatibility - V2 ArticleModularPage is dependent on the upstream deliverable or team input recorded as: DesignSystem V2 Styling updates for background. This affects Execution / Public Web / All / All / Shared / All / TBC. | Open | Critical | Not Started | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 19 | Execution row 19 ¦ task='Dev: Styling Backwards Compatibility - V2 ArticleModularPage' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='DesignSystem V2 Styling updates for background'
DEP-0129 | PRG-0115 | Execution | TBC | Public Web | All | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Collaboration / Input Dependency | Dev: Export Analytics Data into Tableau requires external input or approval | The source notes show that Dev: Export Analytics Data into Tableau requires additional input, approval, access, or collaboration before completion. Evidence: Requires understanding of data sources, data destination, access credentials to involved systems. This affects Execution / Public Web / All / All / Shared / All / TBC. | Open | Critical | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 20 | Execution row 20 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
DEP-0130 | PRG-0116 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC |  | Dev: Export Analytics Data into Tableau | Collaboration / Input Dependency | Dev: Export Analytics Data into Tableau requires external input or approval | The source notes show that Dev: Export Analytics Data into Tableau requires additional input, approval, access, or collaboration before completion. Evidence: Requires understanding of data sources, data destination, access credentials to involved systems. This affects Execution / Secure Web / Shared / Platform / All / Shared / All / TBC. | Open | Critical | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 21 | Execution row 21 ¦ task='Dev: Export Analytics Data into Tableau' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=No ¦ comment='Requires understanding of data sources, data destination, access credentials to involved systems'
DEP-0131 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Upstream Delivery Dependency | Dev: Configuring Web Transformation Page Template in ContentStack depends on upstream delivery | Dev: Configuring Web Transformation Page Template in ContentStack is dependent on the upstream deliverable or team input recorded as: Web Transformation Page Template. This affects Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Open | Critical | Not Started | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
DEP-0132 | PRG-0117 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Configuring Web Transformation Page Template in ContentStack | Collaboration / Input Dependency | Dev: Configuring Web Transformation Page Template in ContentStack requires external input or approval | The source notes show that Dev: Configuring Web Transformation Page Template in ContentStack requires additional input, approval, access, or collaboration before completion. Evidence: Web Transformation Page Template. This affects Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Open | Critical | Not Started | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 22 | Execution row 22 ¦ task='Dev: Configuring Web Transformation Page Template in ContentStack' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
DEP-0133 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Upstream Delivery Dependency | Dev: Update Page Rendering Pipeline to support WT pages depends on upstream delivery | Dev: Update Page Rendering Pipeline to support WT pages is dependent on the upstream deliverable or team input recorded as: Web Transformation Page Template. This affects Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Open | Critical | Not Started | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
DEP-0134 | PRG-0118 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC |  | Dev: Update Page Rendering Pipeline to support WT pages | Collaboration / Input Dependency | Dev: Update Page Rendering Pipeline to support WT pages requires external input or approval | The source notes show that Dev: Update Page Rendering Pipeline to support WT pages requires additional input, approval, access, or collaboration before completion. Evidence: Web Transformation Page Template. This affects Execution / Public Web / OMCOZA / Entire Site / All / TBC. | Open | Critical | Not Started | 80 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 23 | Execution row 23 ¦ task='Dev: Update Page Rendering Pipeline to support WT pages' ¦ priority=Critical ¦ status=Not Started ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Web Transformation Page Template' ¦ comment='Requires at least Web Transformation Page Template red-zones'
DEP-0135 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Upstream Delivery Dependency | Dev: Navigation components updates public Web depends on upstream delivery | Dev: Navigation components updates public Web is dependent on the upstream deliverable or team input recorded as: New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component. This affects Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Open | Critical | Not Started | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
DEP-0136 | PRG-0119 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC |  | Dev: Navigation components updates public Web | Collaboration / Input Dependency | Dev: Navigation components updates public Web requires external input or approval | The source notes show that Dev: Navigation components updates public Web requires additional input, approval, access, or collaboration before completion. Evidence: New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component. This affects Execution / Public Web / OMCOZA / All / Shared / All / TBC. | Open | Critical | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 24 | Execution row 24 ¦ task='Dev: Navigation components updates public Web' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Information Architecture for OMCOZA, New Transformation DesignSystem Nav component' ¦ comment='Awaiting completed Information Architecture, Awaiting new Transformation DesignSystem Nav component'
DEP-0137 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Upstream Delivery Dependency | Dev : Modular Template (LS) depends on upstream delivery | Dev : Modular Template (LS) is dependent on the upstream deliverable or team input recorded as: Design Page Template for Category & Product Detail pages. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
DEP-0138 | PRG-0122 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Template (LS) | Collaboration / Input Dependency | Dev : Modular Template (LS) requires external input or approval | The source notes show that Dev : Modular Template (LS) requires additional input, approval, access, or collaboration before completion. Evidence: Design Page Template for Category & Product Detail pages. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 50 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 28 | Execution row 28 ¦ task='Dev : Modular Template (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design Page Template for Category & Product Detail pages' ¦ comment='Awaiting Page Template drop'
DEP-0139 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Upstream Delivery Dependency | Dev : Modular Page Components (LS) depends on upstream delivery | Dev : Modular Page Components (LS) is dependent on the upstream deliverable or team input recorded as: New Transformation DesignSystem components. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
DEP-0140 | PRG-0123 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev : Modular Page Components (LS) | Collaboration / Input Dependency | Dev : Modular Page Components (LS) requires external input or approval | The source notes show that Dev : Modular Page Components (LS) requires additional input, approval, access, or collaboration before completion. Evidence: New Transformation DesignSystem components. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 29 | Execution row 29 ¦ task='Dev : Modular Page Components (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
DEP-0141 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Upstream Delivery Dependency | Dev Applying analytics tracking to CMS (LS) depends on upstream delivery | Dev Applying analytics tracking to CMS (LS) is dependent on the upstream deliverable or team input recorded as: New Transformation DesignSystem components. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
DEP-0142 | PRG-0124 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev Applying analytics tracking to CMS (LS) | Collaboration / Input Dependency | Dev Applying analytics tracking to CMS (LS) requires external input or approval | The source notes show that Dev Applying analytics tracking to CMS (LS) requires additional input, approval, access, or collaboration before completion. Evidence: New Transformation DesignSystem components. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 40 | Confirm the input provider or approver, decision date, and acceptance criteria. | Execution | 30 | Execution row 30 ¦ task='Dev Applying analytics tracking to CMS (LS)' ¦ priority=Critical ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='New Transformation DesignSystem components' ¦ comment='Awaiting new Transformation DesignSystem components. Uncertain on Effort in Days, quantity & complexity of components unknown.'
DEP-0143 | PRG-0125 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC |  | Dev: OMCOZA -Licence cutover | Upstream Delivery Dependency | Dev: OMCOZA -Licence cutover depends on upstream delivery | Dev: OMCOZA -Licence cutover is dependent on the upstream deliverable or team input recorded as: Migrated OMCOZA site. This affects Execution / Public Web / OMCOZA / Personal / All / TBC. | Open | Critical | Not Started | 60 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Execution | 31 | Execution row 31 ¦ task='Dev: OMCOZA -Licence cutover' ¦ priority=Critical ¦ status=Not Started ¦ confidence=60% ¦ upstream=Yes ¦ dependency='Migrated OMCOZA site'
DEP-0144 | PRG-0128 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC |  | Testing in V2 new platform and log bugs | Collaboration / Input Dependency | Testing in V2 new platform and log bugs requires external input or approval | The source notes show that Testing in V2 new platform and log bugs requires additional input, approval, access, or collaboration before completion. Evidence: Need to work with Web developers for bug fixes. This affects Publishing / Public Web / OMAI (Alternatives) / Entire Site / All / TBC. | Open | High | Not Started | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Publishing | 5 | Publishing row 5 ¦ task='Testing in V2 new platform and log bugs' ¦ priority=High ¦ status=Not Started ¦ confidence=100% ¦ upstream=No ¦ comment='Need to work with Web developers for bug fixes'
DEP-0145 | PRG-0130 | Publishing | Bernice | Public Web | OMCOZA | Personal | Funeral |  | Record Funeral URL structure based on proposed sunset/consolidated pages. | Collaboration / Input Dependency | Record Funeral URL structure based on proposed sunset/consolidated pages. requires external input or approval | The source notes show that Record Funeral URL structure based on proposed sunset/consolidated pages. requires additional input, approval, access, or collaboration before completion. Evidence: Work with Justin on the URLs for this section. This affects Publishing / Public Web / OMCOZA / Personal / Funeral. | Open | High | Not Started | 90 | Confirm the input provider or approver, decision date, and acceptance criteria. | Publishing | 7 | Publishing row 7 ¦ task='Record Funeral URL structure based on proposed sunset/consolidated pages.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
DEP-0146 | PRG-0131 | Publishing | Bernice | Public Web | OMCOZA | Personal | Retirement |  | Record Retirement URL structure based on consolidated pages as per new IA. | Collaboration / Input Dependency | Record Retirement URL structure based on consolidated pages as per new IA. requires external input or approval | The source notes show that Record Retirement URL structure based on consolidated pages as per new IA. requires additional input, approval, access, or collaboration before completion. Evidence: Work with Justin on the URLs for this section. This affects Publishing / Public Web / OMCOZA / Personal / Retirement. | Open | High | Not Started | 90 | Confirm the input provider or approver, decision date, and acceptance criteria. | Publishing | 8 | Publishing row 8 ¦ task='Record Retirement URL structure based on consolidated pages as per new IA.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
DEP-0147 | PRG-0132 | Publishing | Bernice | Public Web | OMCOZA | Personal | Flexi Save |  | Record Flexi Save URL structure based on consolidated pages as per new IA. | Collaboration / Input Dependency | Record Flexi Save URL structure based on consolidated pages as per new IA. requires external input or approval | The source notes show that Record Flexi Save URL structure based on consolidated pages as per new IA. requires additional input, approval, access, or collaboration before completion. Evidence: Work with Justin on the URLs for this section. This affects Publishing / Public Web / OMCOZA / Personal / Flexi Save. | Open | High | Not Started | 90 | Confirm the input provider or approver, decision date, and acceptance criteria. | Publishing | 9 | Publishing row 9 ¦ task='Record Flexi Save URL structure based on consolidated pages as per new IA.' ¦ priority=High ¦ status=Not Started ¦ confidence=90% ¦ upstream=No ¦ comment='Work with Justin on the URLs for this section'
DEP-0148 | PRG-0133 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Record URL structure based on all as-is pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure based on all as-is pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure based on all as-is pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 10 | Publishing row 10 ¦ task='Record URL structure based on all as-is pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0149 | PRG-0134 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC |  | Start moving as-is pages over to Beta | Upstream Delivery Dependency | Start moving as-is pages over to Beta depends on upstream delivery | Start moving as-is pages over to Beta is dependent on the upstream deliverable or team input recorded as: Design. This affects Publishing / Public Web / OMCOZA / as-is pages / All / TBC. | Open | High | In Progress | 80 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 11 | Publishing row 11 ¦ task='Start moving as-is pages over to Beta' ¦ priority=High ¦ status=In Progress ¦ confidence=80% ¦ upstream=Yes ¦ dependency='Design' ¦ comment='Confirm pages and URLs for "as-is" pages before I can start moving'
DEP-0150 | PRG-0135 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining Personal pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining Personal pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / Personal / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 12 | Publishing row 12 ¦ task='Record URL structure for all remaining Personal pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0151 | PRG-0136 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Personal / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 13 | Publishing row 13 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0152 | PRG-0137 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / Corporate / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 14 | Publishing row 14 ¦ task='Record URL structure for all remaining Corporate pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0153 | PRG-0138 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Corporate / All / TBC. | Open | High | Not Started | 40 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 15 | Publishing row 15 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=40% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0154 | PRG-0139 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Wealth / All / TBC. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 16 | Publishing row 16 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0155 | PRG-0140 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining Utility pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining Utility pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 17 | Publishing row 17 ¦ task='Record URL structure for all remaining Utility pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0156 | PRG-0141 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Utility pages / All / TBC. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 18 | Publishing row 18 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0157 | PRG-0142 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining About us pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining About us pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / About Us / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 19 | Publishing row 19 ¦ task='Record URL structure for all remaining About us pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0158 | PRG-0143 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / About Us / All / TBC. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 20 | Publishing row 20 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0159 | PRG-0144 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining Careers pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining Careers pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / Careers / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 21 | Publishing row 21 ¦ task='Record URL structure for all remaining Careers pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0160 | PRG-0145 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Careers / All / TBC. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 22 | Publishing row 22 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0161 | PRG-0146 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Upstream Delivery Dependency | Record URL structure for all remaining Business pages (keep/remove/consolidate) depends on upstream delivery | Record URL structure for all remaining Business pages (keep/remove/consolidate) is dependent on the upstream deliverable or team input recorded as: Design/content. This affects Publishing / Public Web / OMCOZA / Business / All / TBC. | Open | High | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 23 | Publishing row 23 ¦ task='Record URL structure for all remaining Business pages (keep/remove/consolidate)' ¦ priority=High ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='Design/content'
DEP-0162 | PRG-0147 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC |  | Start building new template pages | Upstream Delivery Dependency | Start building new template pages depends on upstream delivery | Start building new template pages is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOZA / Business / All / TBC. | Open | High | Not Started | 30 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 24 | Publishing row 24 ¦ task='Start building new template pages' ¦ priority=High ¦ status=Not Started ¦ confidence=30% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0163 | PRG-0148 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Upstream Delivery Dependency | Add new Nav, Footer and update IA depends on upstream delivery | Add new Nav, Footer and update IA is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMCOM / All / TBC / All / TBC. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 25 | Publishing row 25 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0164 | PRG-0149 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Upstream Delivery Dependency | Add new Nav, Footer and update IA depends on upstream delivery | Add new Nav, Footer and update IA is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMAI (Alternatives) / All / TBC / All / TBC. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 26 | Publishing row 26 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0165 | PRG-0150 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Upstream Delivery Dependency | Add new Nav, Footer and update IA depends on upstream delivery | Add new Nav, Footer and update IA is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / Bula Tsela / All / TBC / All / TBC. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 27 | Publishing row 27 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0166 | PRG-0151 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC |  | Add new Nav, Footer and update IA | Upstream Delivery Dependency | Add new Nav, Footer and update IA depends on upstream delivery | Add new Nav, Footer and update IA is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / LTD / All / TBC / All / TBC. | Open | Medium | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 28 | Publishing row 28 ¦ task='Add new Nav, Footer and update IA' ¦ priority=Medium ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Work can only begin once all upstream teams have completed their work'
DEP-0167 | PRG-0152 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC |  | Publishing requirements for OMAR, logged on OMAR tab | Upstream Delivery Dependency | Publishing requirements for OMAR, logged on OMAR tab depends on upstream delivery | Publishing requirements for OMAR, logged on OMAR tab is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects Publishing / Public Web / OMAR / All / TBC / All / TBC. | Open | Medium | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Publishing | 29 | Publishing row 29 ¦ task='Publishing requirements for OMAR, logged on OMAR tab' ¦ priority=Medium ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work. This is also recorded in more detail in the OMAR tab.'
DEP-0168 | PRG-0155 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Quality Assurance Approval | Approval Dependency | Quality Assurance Approval requires external input or approval | The source notes show that Quality Assurance Approval requires additional input, approval, access, or collaboration before completion. Evidence: . This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Go-Live Readiness | 5 | Go-Live Readiness row 5 ¦ task='Quality Assurance Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=100% ¦ upstream=No
DEP-0169 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Upstream Delivery Dependency | Security Approvals depends on upstream delivery | Security Approvals is dependent on the upstream deliverable or team input recorded as: All deliveries must be in QA State. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | TBC | 100 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
DEP-0170 | PRG-0156 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Security Approvals | Approval Dependency | Security Approvals requires external input or approval | The source notes show that Security Approvals requires additional input, approval, access, or collaboration before completion. Evidence: All deliveries must be in QA State. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | TBC | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | Go-Live Readiness | 6 | Go-Live Readiness row 6 ¦ task='Security Approvals' ¦ priority=Low ¦ status=TBC ¦ confidence=100% ¦ upstream=Yes ¦ dependency='All deliveries must be in QA State'
DEP-0171 | PRG-0157 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Internal Communication ( Call Centre) - Marketing Team Driven | Upstream Delivery Dependency | Internal Communication ( Call Centre) - Marketing Team Driven depends on upstream delivery | Internal Communication ( Call Centre) - Marketing Team Driven is dependent on the upstream deliverable or team input recorded as: All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 70 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Go-Live Readiness | 7 | Go-Live Readiness row 7 ¦ task='Internal Communication ( Call Centre) - Marketing Team Driven' ¦ priority=Low ¦ status=Not Started ¦ confidence=70% ¦ upstream=Yes ¦ dependency='All deliveries must be in readiness state for Comms to be reviewed and sent to internal team and External T'
DEP-0172 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Upstream Delivery Dependency | Executive Approval depends on upstream delivery | Executive Approval is dependent on the upstream deliverable or team input recorded as: Approval to go ahead from all other Teams. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
DEP-0173 | PRG-0159 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Executive Approval | Approval Dependency | Executive Approval requires external input or approval | The source notes show that Executive Approval requires additional input, approval, access, or collaboration before completion. Evidence: Approval to go ahead from all other Teams. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 50 | Confirm the input provider or approver, decision date, and acceptance criteria. | Go-Live Readiness | 9 | Go-Live Readiness row 9 ¦ task='Executive Approval' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='Approval to go ahead from all other Teams'
DEP-0174 | PRG-0160 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Change Management Go Ahead | Upstream Delivery Dependency | Change Management Go Ahead depends on upstream delivery | Change Management Go Ahead is dependent on the upstream deliverable or team input recorded as: All work by teams must be completed. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 50 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Go-Live Readiness | 10 | Go-Live Readiness row 10 ¦ task='Change Management Go Ahead' ¦ priority=Low ¦ status=Not Started ¦ confidence=50% ¦ upstream=Yes ¦ dependency='All work by teams must be completed'
DEP-0175 | PRG-0161 | Go-Live Readiness | TBC | Public Web | All | All | All |  | Customer Experience Tool | Upstream Delivery Dependency | Customer Experience Tool depends on upstream delivery | Customer Experience Tool is dependent on the upstream deliverable or team input recorded as: Tool Evaluating. This affects Go-Live Readiness / Public Web / All / All / All. | Open | Low | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | Go-Live Readiness | 11 | Go-Live Readiness row 11 ¦ task='Customer Experience Tool' ¦ priority=Low ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Tool Evaluating' ¦ comment='Tool still in evaluation tool'
DEP-0176 | PRG-0162 | SEO / Analytics | TBC | Public Web | All | All | All |  | Confirm Engagement Cycle with SEO Team | Approval Dependency | Confirm Engagement Cycle with SEO Team requires external input or approval | The source notes show that Confirm Engagement Cycle with SEO Team requires additional input, approval, access, or collaboration before completion. Evidence: Final Approval will be provided by the CMO. This affects SEO / Analytics / Public Web / All / All / All. | Open | High | In Progress | 100 | Confirm the input provider or approver, decision date, and acceptance criteria. | SEO Analytics | 4 | SEO Analytics row 4 ¦ task='Confirm Engagement Cycle with SEO Team' ¦ priority=High ¦ status=In Progress ¦ confidence=100% ¦ upstream=No ¦ comment='Final Approval will be provided by the CMO'
DEP-0177 | PRG-0165 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Botswana / Botswana. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 5 | OMAR row 5 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0178 | PRG-0166 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Ghana / Ghana. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 6 | OMAR row 6 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0179 | PRG-0167 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Kenya | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Kenya / Kenya. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 7 | OMAR row 7 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0180 | PRG-0168 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Namibia / Namibia. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 8 | OMAR row 8 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0181 | PRG-0169 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Rwanda / Rwanda. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 9 | OMAR row 9 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0182 | PRG-0170 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Uganda | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Uganda / Uganda. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 10 | OMAR row 10 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0183 | PRG-0171 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Zimbabwe / Zimbabwe. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 11 | OMAR row 11 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development' ¦ comment='Engagement with OMAR teams is required in order to determine who will be responsible for the publishing work. Work can only begin once all upstream teams have completed their work'
DEP-0184 | PRG-0172 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Publishing of all pages in V2 New platform | Upstream Delivery Dependency | Publishing of all pages in V2 New platform depends on upstream delivery | Publishing of all pages in V2 New platform is dependent on the upstream deliverable or team input recorded as: Design / Design Systems / Development. This affects OMAR / Public Web / OMAR / Namibia / Namibia. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 12 | OMAR row 12 ¦ task='Publishing of all pages in V2 New platform' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Design / Design Systems / Development'
DEP-0185 | PRG-0173 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Travel Insurance Sales Migration | Unspecified Upstream Dependency | Travel Insurance Sales Migration has an unnamed upstream dependency | Travel Insurance Sales Migration is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Ghana / Ghana and prevents clean dependency tracking. | Open | High | In Progress | 40 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 13 | OMAR row 13 ¦ task='Travel Insurance Sales Migration' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
DEP-0186 | PRG-0174 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Ghana | Mvest | Unspecified Upstream Dependency | Mvest has an unnamed upstream dependency | Mvest is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Ghana / Ghana and prevents clean dependency tracking. | Open | High | In Progress | 40 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 14 | OMAR row 14 ¦ task='Mvest' ¦ priority=High ¦ status=In Progress ¦ confidence=40% ¦ upstream=Yes
DEP-0187 | PRG-0175 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Application | Unspecified Upstream Dependency | Personal Loan Application has an unnamed upstream dependency | Personal Loan Application is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Namibia / Namibia and prevents clean dependency tracking. | Open | High | In Progress | 50 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 15 | OMAR row 15 ¦ task='Personal Loan Application' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
DEP-0188 | PRG-0176 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Namibia | Personal Loan Repayment Calculator | Unspecified Upstream Dependency | Personal Loan Repayment Calculator has an unnamed upstream dependency | Personal Loan Repayment Calculator is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Namibia / Namibia and prevents clean dependency tracking. | Open | High | In Progress | 50 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 16 | OMAR row 16 ¦ task='Personal Loan Repayment Calculator' ¦ priority=High ¦ status=In Progress ¦ confidence=50% ¦ upstream=Yes
DEP-0189 | PRG-0177 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Migration of Secure Web | Upstream Delivery Dependency | Migration of Secure Web depends on upstream delivery | Migration of Secure Web is dependent on the upstream deliverable or team input recorded as: Designs for their Secure Web. This affects OMAR / Secure Web / OMAR / Namibia / Namibia. | Open | High | Not Started | 10 | Confirm accountable upstream owner, expected completion date, and readiness criteria. | OMAR | 17 | OMAR row 17 ¦ task='Migration of Secure Web' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ dependency='Designs for their Secure Web' ¦ comment='Resource constraints 2 people looking after 2 platforms'
DEP-0190 | PRG-0178 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Namibia | Service Transactions | Unspecified Upstream Dependency | Service Transactions has an unnamed upstream dependency | Service Transactions is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Secure Web / OMAR / Namibia / Namibia and prevents clean dependency tracking. | Open | High | Not Started |  | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 18 | OMAR row 18 ¦ task='Service Transactions' ¦ priority=High ¦ status=Not Started ¦ upstream=Yes
DEP-0191 | PRG-0179 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Ghana | Eswatini Funeral | Unspecified Upstream Dependency | Eswatini Funeral has an unnamed upstream dependency | Eswatini Funeral is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / eSwatini / eSwatini and prevents clean dependency tracking. | Open | High | In Progress | 70 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 19 | OMAR row 19 ¦ task='Eswatini Funeral' ¦ priority=High ¦ status=In Progress ¦ confidence=70% ¦ upstream=Yes ¦ comment='testing in progress'
DEP-0192 | PRG-0180 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Servicing Journey | Unspecified Upstream Dependency | Funeral Claims - Servicing Journey has an unnamed upstream dependency | Funeral Claims - Servicing Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | In Progress | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 20 | OMAR row 20 ¦ task='Funeral Claims - Servicing Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0193 | PRG-0181 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Service Journey | Unspecified Upstream Dependency | Motor claims - Service Journey has an unnamed upstream dependency | Motor claims - Service Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | In Progress | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 21 | OMAR row 21 ¦ task='Motor claims - Service Journey' ¦ priority=High ¦ status=In Progress ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0194 | PRG-0182 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Service Journey | Unspecified Upstream Dependency | Home owners claims- Service Journey has an unnamed upstream dependency | Home owners claims- Service Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 22 | OMAR row 22 ¦ task='Home owners claims- Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0195 | PRG-0183 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home content claims Service Journey | Unspecified Upstream Dependency | Home content claims Service Journey has an unnamed upstream dependency | Home content claims Service Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 23 | OMAR row 23 ¦ task='Home content claims Service Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0196 | PRG-0184 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Credit Life | Unspecified Upstream Dependency | Credit Life has an unnamed upstream dependency | Credit Life is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 24 | OMAR row 24 ¦ task='Credit Life' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0197 | PRG-0185 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Funeral Claims - Sales Journey | Unspecified Upstream Dependency | Funeral Claims - Sales Journey has an unnamed upstream dependency | Funeral Claims - Sales Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 25 | OMAR row 25 ¦ task='Funeral Claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0198 | PRG-0186 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Motor claims - Sales Journey | Unspecified Upstream Dependency | Motor claims - Sales Journey has an unnamed upstream dependency | Motor claims - Sales Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 26 | OMAR row 26 ¦ task='Motor claims - Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'
DEP-0199 | PRG-0187 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Botswana | Home owners claims- Sales Journey | Unspecified Upstream Dependency | Home owners claims- Sales Journey has an unnamed upstream dependency | Home owners claims- Sales Journey is marked as dependent on upstream work, but the worksheet does not name the upstream deliverable. This affects OMAR / Public Web / OMAR / Botswana / Botswana and prevents clean dependency tracking. | Open | High | Not Started | 10 | Capture the specific upstream deliverable, owner, and required completion date. | OMAR | 27 | OMAR row 27 ¦ task='Home owners claims- Sales Journey' ¦ priority=High ¦ status=Not Started ¦ confidence=10% ¦ upstream=Yes ¦ comment='Resources shared between Botswana and Eswatini'

## REFERENCE_Validation
Programme_Record_ID | Source_Sheet | Source_Row | Workstream | Owner | Channel | Domain | Area_Journey | Cluster | Related_Deliverable | Validation_Issue | Load_Readiness | Suggested_Action | Source_Evidence
PRG-0014 | Design Standards | 17 | Design Standards | Justin | Secure Web | MyOM | Entire Site | Navigation | Design navigation solution to allow access to other secure sites | Upstream dependency marked yes but detail missing | Needs Validation | capture named upstream dependency | Design Standards row 17: Design navigation solution to allow access to other secure sites
PRG-0015 | Design Standards | 18 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy | Finalise generic copy standards | Channel missing | Needs Validation | validate taxonomy fields; track upstream dependency | Design Standards row 18: Finalise generic copy standards
PRG-0016 | Design Standards | 19 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | Copy | Finalise SEO + AIEO standards | Channel missing | Needs Validation | validate taxonomy fields; track upstream dependency | Design Standards row 19: Finalise SEO + AIEO standards
PRG-0017 | Design Standards | 20 | Design Standards | Justin | TBC | Old Mutual Design Standards | Generic | CI | Align DS to iterim Brand CI | Channel missing | Needs Validation | validate taxonomy fields; track upstream dependency | Design Standards row 20: Align DS to iterim Brand CI
PRG-0021 | Design Delivery | 4 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Retirement | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 4: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0022 | Design Delivery | 5 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Funeral | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 5: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0023 | Design Delivery | 6 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Investment > Flexi Save | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 6: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Product landing page with enhanced copy
PRG-0024 | Design Delivery | 7 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 7: Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0025 | Design Delivery | 8 | Design Delivery | TBC | Public Web | OMCOZA | Business | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 8: Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0026 | Design Delivery | 9 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 9: Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0027 | Design Delivery | 10 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Entire Site | Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3) | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 10: Information Architecture Stakeholder Socialisation & Sign Off (L1 - L3)
PRG-0028 | Design Delivery | 11 | Design Delivery | TBC | Public Web | RESOURCE RECRUITMENT | ALL SITES IN SCOPE | ALL SITES IN SCOPE | Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding | Owner missing | Needs Validation | assign owner | Design Delivery row 11: Kick-of recruitment process for additional capacity; Vendor briefing; CV review; Interviews; Candidate selection; Onboarding
PRG-0029 | Design Delivery | 12 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Personal Landing | Audience landing with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 12: Audience landing with enhanced copy
PRG-0030 | Design Delivery | 13 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Invest | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 13: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0031 | Design Delivery | 14 | Design Delivery | TBC | Public Web | OMCOZA | Personal | OM Bank | L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 14: L3+ IA finalisation; Section landing with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0032 | Design Delivery | 15 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Insure | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 15: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0033 | Design Delivery | 16 | Design Delivery | TBC | Public Web | OMCOZA | Personal | About us | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 16: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy
PRG-0034 | Design Delivery | 17 | Design Delivery | TBC | Public Web | OMCOZA | Personal | Careers | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 17: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy
PRG-0035 | Design Delivery | 18 | Design Delivery | TBC | Public Web | OMCOM | Entire Site | Entire Site | Mapping of new IA and Footer to sxisting site structure | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 18: Mapping of new IA and Footer to sxisting site structure
PRG-0036 | Design Delivery | 19 | Design Delivery | TBC | Public Web | Bula Tsela | Entire Site | Entire Site | Mapping of new IA and Footer to sxisting site structure | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 19: Mapping of new IA and Footer to sxisting site structure
PRG-0037 | Design Delivery | 20 | Design Delivery | TBC | Public Web | Learn Think Do (LTD) | Entire Site | Entire Site | Mapping of new IA and Footer to sxisting site structure | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 20: Mapping of new IA and Footer to sxisting site structure
PRG-0038 | Design Delivery | 21 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Wealth Landing | Audience landing with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 21: Audience landing with enhanced copy
PRG-0039 | Design Delivery | 22 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Invest | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 22: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0040 | Design Delivery | 23 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Plan | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 23: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0041 | Design Delivery | 24 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | About | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 24: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy
PRG-0042 | Design Delivery | 25 | Design Delivery | TBC | Public Web | OMCOZA | Wealth | Insights | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 25: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (3+) with enhanced copy; Product landing pages (3+) with enhanced copy
PRG-0043 | Design Delivery | 26 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Corporate Landing | Audience landing with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 26: Audience landing with enhanced copy
PRG-0044 | Design Delivery | 27 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employees | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 27: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0045 | Design Delivery | 28 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Employers | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 28: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0046 | Design Delivery | 29 | Design Delivery | TBC | Public Web | OMCOZA | Corporate | Services | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 29: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0047 | Design Delivery | 30 | Design Delivery | TBC | Public Web | OMCOZA | Business | Business Landing | Audience landing with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 30: Audience landing with enhanced copy
PRG-0048 | Design Delivery | 31 | Design Delivery | TBC | Public Web | OMCOZA | Business | Insure | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 31: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0049 | Design Delivery | 32 | Design Delivery | TBC | Public Web | OMCOZA | Business | Invest | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 32: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0050 | Design Delivery | 33 | Design Delivery | TBC | Public Web | OMCOZA | Business | Protect | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 33: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0051 | Design Delivery | 34 | Design Delivery | TBC | Public Web | OMCOZA | Business | Guarantee | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 34: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0052 | Design Delivery | 35 | Design Delivery | TBC | Public Web | OMCOZA | Business | Tools | L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 35: L3+ IA finalisation; URL mapping (Current vs. New URL mapping (Current pages > New IA pages). outlining consolidated sections and pages that will be removed in the new Information Architecture.; Section landing with enhanced copy; Category landing pages (5+) with enhanced copy; Product landing pages (5+) with enhanced copy
PRG-0053 | Design Delivery | 36 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 36: Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.
PRG-0053 | Design Delivery | 36 | Design Delivery | TBC | Public Web | OMCOZA | Personal | My OldMutual | Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation. | Status missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 36: Public > Secure ¦ Secure > Public Transition.; Access to other secure sites.; Service tree definition (E.g. Product > Payment or Payment Hub > Product selection).; IA + Navigation flow (Primary noun architecture).; Potential Template impact (E.g. Dashboard).; Customer validation.
PRG-0054 | Design Delivery | 37 | Design Delivery | TBC | Public Web | OMAR: Kenya | Entire Site | Entire Site | Socilaisation of defined IA and Page templates for handover. | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 37: Socilaisation of defined IA and Page templates for handover.
PRG-0055 | Design Delivery | 38 | Design Delivery | TBC | Public Web | OMAR: Zimbabwe | Entire Site | Entire Site | Socilaisation of defined IA and Page templates for handover. | Owner missing | Needs Validation | assign owner; track upstream dependency | Design Delivery row 38: Socilaisation of defined IA and Page templates for handover.
PRG-0060 | Feature Delivery | 4 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All | Portfolio View | Start date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 4: Portfolio View
PRG-0060 | Feature Delivery | 4 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All | Portfolio View | End date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 4: Portfolio View
PRG-0060 | Feature Delivery | 4 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Dashboard Views ( Porffolio Views) | All | Portfolio View | Effort tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 4: Portfolio View
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | Channel missing | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | Domain missing | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | Start date tbc | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | End date tbc | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | Effort tbc | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0061 | Feature Delivery | 5 | Feature Delivery | Wayne & Tebogo | TBC | TBC | Dashboard Views ( Porffolio Views) | All | Standards on how to creates views on dashboard | Status missing | Needs Validation | confirm schedule and effort; validate taxonomy fields | Feature Delivery row 5: Standards on how to creates views on dashboard
PRG-0062 | Feature Delivery | 6 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Content Updates | Start date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 6: Content Updates
PRG-0062 | Feature Delivery | 6 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Content Updates | End date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 6: Content Updates
PRG-0062 | Feature Delivery | 6 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Content Updates | Effort tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 6: Content Updates
PRG-0063 | Feature Delivery | 7 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Journeys Optimization | Start date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 7: Journeys Optimization
PRG-0063 | Feature Delivery | 7 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Journeys Optimization | End date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 7: Journeys Optimization
PRG-0063 | Feature Delivery | 7 | Feature Delivery | Wayne & Tebogo | Secure Web | Shared / Platform | Servicing Transaction in Sec Web | All | Journeys Optimization | Effort tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 7: Journeys Optimization
PRG-0072 | Feature Delivery | 16 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Easy Plus Sales Jorurney on Public Web | Start date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 16: Easy Plus Sales Jorurney on Public Web
PRG-0072 | Feature Delivery | 16 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Easy Plus Sales Jorurney on Public Web | End date tbc | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 16: Easy Plus Sales Jorurney on Public Web
PRG-0072 | Feature Delivery | 16 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Easy Plus Sales Jorurney on Public Web | Effort missing | Needs Validation | confirm schedule and effort; track upstream dependency | Feature Delivery row 16: Easy Plus Sales Jorurney on Public Web
PRG-0074 | Feature Delivery | 18 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Find Advisor | Start date text / check | Review | confirm schedule and effort; track upstream dependency | Feature Delivery row 18: Find Advisor
PRG-0074 | Feature Delivery | 18 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Find Advisor | End date text / check | Review | confirm schedule and effort; track upstream dependency | Feature Delivery row 18: Find Advisor
PRG-0074 | Feature Delivery | 18 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Find Advisor | Effort text / estimate | Review | confirm schedule and effort; track upstream dependency | Feature Delivery row 18: Find Advisor
PRG-0076 | Feature Delivery | 20 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Personal Calculator | Status missing | Needs Validation | confirm start readiness | Feature Delivery row 20: Personal Calculator
PRG-0077 | Feature Delivery | 21 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Budget Calculator | Status missing | Needs Validation | confirm start readiness | Feature Delivery row 21: Budget Calculator
PRG-0078 | Feature Delivery | 22 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Income Tax Calculator | Start date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 22: Income Tax Calculator
PRG-0078 | Feature Delivery | 22 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Income Tax Calculator | End date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 22: Income Tax Calculator
PRG-0078 | Feature Delivery | 22 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Income Tax Calculator | Effort text / estimate | Needs Validation | confirm schedule and effort | Feature Delivery row 22: Income Tax Calculator
PRG-0078 | Feature Delivery | 22 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Income Tax Calculator | Status missing | Needs Validation | confirm schedule and effort | Feature Delivery row 22: Income Tax Calculator
PRG-0079 | Feature Delivery | 23 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Retirement Calculator | Start date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 23: Retirement Calculator
PRG-0079 | Feature Delivery | 23 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Retirement Calculator | End date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 23: Retirement Calculator
PRG-0079 | Feature Delivery | 23 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Retirement Calculator | Effort text / estimate | Needs Validation | confirm schedule and effort | Feature Delivery row 23: Retirement Calculator
PRG-0079 | Feature Delivery | 23 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Retirement Calculator | Status missing | Needs Validation | confirm schedule and effort | Feature Delivery row 23: Retirement Calculator
PRG-0080 | Feature Delivery | 24 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | 2 Pot Calculator | Start date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 24: 2 Pot Calculator
PRG-0080 | Feature Delivery | 24 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | 2 Pot Calculator | End date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 24: 2 Pot Calculator
PRG-0080 | Feature Delivery | 24 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | 2 Pot Calculator | Effort text / estimate | Needs Validation | confirm schedule and effort | Feature Delivery row 24: 2 Pot Calculator
PRG-0080 | Feature Delivery | 24 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | 2 Pot Calculator | Status missing | Needs Validation | confirm schedule and effort | Feature Delivery row 24: 2 Pot Calculator
PRG-0081 | Feature Delivery | 25 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Contact Us | Start date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 25: Contact Us
PRG-0081 | Feature Delivery | 25 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Contact Us | End date text / check | Needs Validation | confirm schedule and effort | Feature Delivery row 25: Contact Us
PRG-0081 | Feature Delivery | 25 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Contact Us | Effort text / estimate | Needs Validation | confirm schedule and effort | Feature Delivery row 25: Contact Us
PRG-0081 | Feature Delivery | 25 | Feature Delivery | Wayne & Tebogo | Public Web | OMCOZA | Personal | L&S | Contact Us | Status missing | Needs Validation | confirm schedule and effort | Feature Delivery row 25: Contact Us
PRG-0082 | Design Systems | 4 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop CI Updates onto OMDSv2 | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 4: Design and Develop CI Updates onto OMDSv2
PRG-0082 | Design Systems | 4 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop CI Updates onto OMDSv2 | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 4: Design and Develop CI Updates onto OMDSv2
PRG-0083 | Design Systems | 5 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Top Navigation Component Updates | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 5: Design and Develop Top Navigation Component Updates
PRG-0084 | Design Systems | 6 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop Top Navigation Component Updates | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 6: Design and Develop Top Navigation Component Updates
PRG-0084 | Design Systems | 6 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop Top Navigation Component Updates | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 6: Design and Develop Top Navigation Component Updates
PRG-0085 | Design Systems | 7 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Footer Component Updates | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 7: Design and Develop Footer Component Updates
PRG-0085 | Design Systems | 7 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Footer Component Updates | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 7: Design and Develop Footer Component Updates
PRG-0086 | Design Systems | 8 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Card Component Updates | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 8: Design and Develop Card Component Updates
PRG-0086 | Design Systems | 8 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Card Component Updates | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 8: Design and Develop Card Component Updates
PRG-0087 | Design Systems | 9 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Category Page Template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 9: Design and Develop Category Page Template
PRG-0087 | Design Systems | 9 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Category Page Template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 9: Design and Develop Category Page Template
PRG-0088 | Design Systems | 10 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Product Detail Page Template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 10: Design and Develop Product Detail Page Template
PRG-0088 | Design Systems | 10 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Product Detail Page Template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 10: Design and Develop Product Detail Page Template
PRG-0089 | Design Systems | 11 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Article Page Template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 11: Design and Develop Article Page Template
PRG-0089 | Design Systems | 11 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Article Page Template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 11: Design and Develop Article Page Template
PRG-0090 | Design Systems | 12 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Hero Banner Component Updates | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 12: Design and Develop Hero Banner Component Updates
PRG-0090 | Design Systems | 12 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Hero Banner Component Updates | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 12: Design and Develop Hero Banner Component Updates
PRG-0091 | Design Systems | 13 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Landing page template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 13: Design and Develop Landing page template
PRG-0091 | Design Systems | 13 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Landing page template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 13: Design and Develop Landing page template
PRG-0091 | Design Systems | 13 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Landing page template | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 13: Design and Develop Landing page template
PRG-0092 | Design Systems | 14 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Section page template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 14: Design and Develop Section page template
PRG-0092 | Design Systems | 14 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Section page template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 14: Design and Develop Section page template
PRG-0092 | Design Systems | 14 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Section page template | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 14: Design and Develop Section page template
PRG-0093 | Design Systems | 15 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Contact Us | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 15: Design and Develop Utility Template: Contact Us
PRG-0093 | Design Systems | 15 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Contact Us | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 15: Design and Develop Utility Template: Contact Us
PRG-0093 | Design Systems | 15 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Contact Us | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 15: Design and Develop Utility Template: Contact Us
PRG-0094 | Design Systems | 16 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: All Calculators | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 16: Design and Develop Utility Template: All Calculators
PRG-0094 | Design Systems | 16 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: All Calculators | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 16: Design and Develop Utility Template: All Calculators
PRG-0094 | Design Systems | 16 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: All Calculators | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 16: Design and Develop Utility Template: All Calculators
PRG-0095 | Design Systems | 17 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Calculators Page | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 17: Design and Develop Utility Template: Calculators Page
PRG-0095 | Design Systems | 17 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Calculators Page | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 17: Design and Develop Utility Template: Calculators Page
PRG-0095 | Design Systems | 17 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Calculators Page | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 17: Design and Develop Utility Template: Calculators Page
PRG-0096 | Design Systems | 18 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Templates: About Us | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 18: Design and Develop Utility Templates: About Us
PRG-0096 | Design Systems | 18 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Templates: About Us | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 18: Design and Develop Utility Templates: About Us
PRG-0096 | Design Systems | 18 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Templates: About Us | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 18: Design and Develop Utility Templates: About Us
PRG-0097 | Design Systems | 19 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Careers | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 19: Design and Develop Utility Template: Careers
PRG-0097 | Design Systems | 19 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Careers | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 19: Design and Develop Utility Template: Careers
PRG-0097 | Design Systems | 19 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop Utility Template: Careers | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 19: Design and Develop Utility Template: Careers
PRG-0098 | Design Systems | 20 | Design Systems | Brent van Zitters | Public Web | All | All | All | Add copy standards to OMDS | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 20: Add copy standards to OMDS
PRG-0098 | Design Systems | 20 | Design Systems | Brent van Zitters | Public Web | All | All | All | Add copy standards to OMDS | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 20: Add copy standards to OMDS
PRG-0098 | Design Systems | 20 | Design Systems | Brent van Zitters | Public Web | All | All | All | Add copy standards to OMDS | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 20: Add copy standards to OMDS
PRG-0099 | Design Systems | 21 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Add copy standards to OMDS | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 21: Add copy standards to OMDS
PRG-0099 | Design Systems | 21 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Add copy standards to OMDS | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 21: Add copy standards to OMDS
PRG-0099 | Design Systems | 21 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Add copy standards to OMDS | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 21: Add copy standards to OMDS
PRG-0100 | Design Systems | 22 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop tenant template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 22: Design and Develop tenant template
PRG-0100 | Design Systems | 22 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop tenant template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 22: Design and Develop tenant template
PRG-0100 | Design Systems | 22 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop tenant template | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 22: Design and Develop tenant template
PRG-0100 | Design Systems | 22 | Design Systems | Brent van Zitters | Public Web | All | All | All | Design and Develop tenant template | Status missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 22: Design and Develop tenant template
PRG-0101 | Design Systems | 23 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop tenant template | Start date text / check | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 23: Design and Develop tenant template
PRG-0101 | Design Systems | 23 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop tenant template | End date missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 23: Design and Develop tenant template
PRG-0101 | Design Systems | 23 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop tenant template | Effort invalid source formula | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 23: Design and Develop tenant template
PRG-0101 | Design Systems | 23 | Design Systems | Brent van Zitters | Secure Web | All | All | All | Design and Develop tenant template | Status missing | Needs Validation | confirm schedule and effort; track upstream dependency | Design Systems row 23: Design and Develop tenant template
PRG-0102 | Execution | 4 | Execution | TBC | Public Web | OMCOM | All | OM | Implement OMCOM into production | Owner missing | Needs Validation | assign owner; track upstream dependency | Execution row 4: Implement OMCOM into production
PRG-0103 | Execution | 5 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC | Dev: Co-locating Content & Analytics Tagging | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 5: Dev: Co-locating Content & Analytics Tagging
PRG-0103 | Execution | 5 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC | Dev: Co-locating Content & Analytics Tagging | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 5: Dev: Co-locating Content & Analytics Tagging
PRG-0104 | Execution | 6 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC | Dev: Applying Analytics Tracking to V2 Components | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 6: Dev: Applying Analytics Tracking to V2 Components
PRG-0104 | Execution | 6 | Execution | TBC | Public Web | OMCOZA, OMCOM, Bula-tsela, Malawi | Entire Site | All / TBC | Dev: Applying Analytics Tracking to V2 Components | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 6: Dev: Applying Analytics Tracking to V2 Components
PRG-0105 | Execution | 7 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev: DevOps Quality Gate Pipeline | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 7: Dev: DevOps Quality Gate Pipeline
PRG-0105 | Execution | 7 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev: DevOps Quality Gate Pipeline | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 7: Dev: DevOps Quality Gate Pipeline
PRG-0106 | Execution | 8 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: DevOps Quality Gate Pipeline | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 8: Dev: DevOps Quality Gate Pipeline
PRG-0106 | Execution | 8 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: DevOps Quality Gate Pipeline | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 8: Dev: DevOps Quality Gate Pipeline
PRG-0107 | Execution | 9 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | QE: Automated Testing Framework | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 9: QE: Automated Testing Framework
PRG-0107 | Execution | 9 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | QE: Automated Testing Framework | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 9: QE: Automated Testing Framework
PRG-0108 | Execution | 10 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev/QE: DevOps - Integrate Automated Testing | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 10: Dev/QE: DevOps - Integrate Automated Testing
PRG-0108 | Execution | 10 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev/QE: DevOps - Integrate Automated Testing | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 10: Dev/QE: DevOps - Integrate Automated Testing
PRG-0109 | Execution | 11 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | QE: Automated Testing Framework | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 11: QE: Automated Testing Framework
PRG-0109 | Execution | 11 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | QE: Automated Testing Framework | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 11: QE: Automated Testing Framework
PRG-0110 | Execution | 12 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev/QE: DevOps - Integrate Automated Testing | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 12: Dev/QE: DevOps - Integrate Automated Testing
PRG-0110 | Execution | 12 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev/QE: DevOps - Integrate Automated Testing | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 12: Dev/QE: DevOps - Integrate Automated Testing
PRG-0111 | Execution | 13 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev: Observability Dashboard Templates for Sites | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 13: Dev: Observability Dashboard Templates for Sites
PRG-0111 | Execution | 13 | Execution | TBC | Public Web | Shared / Platform | All / Shared | All / TBC | Dev: Observability Dashboard Templates for Sites | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 13: Dev: Observability Dashboard Templates for Sites
PRG-0112 | Execution | 14 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: Observability Dashboard Templates for Sites | Owner missing | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 14: Dev: Observability Dashboard Templates for Sites
PRG-0112 | Execution | 14 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: Observability Dashboard Templates for Sites | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 14: Dev: Observability Dashboard Templates for Sites
PRG-0113 | Execution | 18 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Styling Backwards Compatibility - V2 ModularPage | Owner missing | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 18: Dev: Styling Backwards Compatibility - V2 ModularPage
PRG-0113 | Execution | 18 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Styling Backwards Compatibility - V2 ModularPage | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 18: Dev: Styling Backwards Compatibility - V2 ModularPage
PRG-0114 | Execution | 19 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Owner missing | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 19: Dev: Styling Backwards Compatibility - V2 ArticleModularPage
PRG-0114 | Execution | 19 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Styling Backwards Compatibility - V2 ArticleModularPage | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 19: Dev: Styling Backwards Compatibility - V2 ArticleModularPage
PRG-0115 | Execution | 20 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Export Analytics Data into Tableau | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 20: Dev: Export Analytics Data into Tableau
PRG-0115 | Execution | 20 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Export Analytics Data into Tableau | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 20: Dev: Export Analytics Data into Tableau
PRG-0115 | Execution | 20 | Execution | TBC | Public Web | All | All / Shared | All / TBC | Dev: Export Analytics Data into Tableau | Effort text / estimate | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 20: Dev: Export Analytics Data into Tableau
PRG-0116 | Execution | 21 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: Export Analytics Data into Tableau | Owner missing | Needs Validation | assign owner; validate taxonomy fields | Execution row 21: Dev: Export Analytics Data into Tableau
PRG-0116 | Execution | 21 | Execution | TBC | Secure Web | Shared / Platform | All / Shared | All / TBC | Dev: Export Analytics Data into Tableau | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields | Execution row 21: Dev: Export Analytics Data into Tableau
PRG-0117 | Execution | 22 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC | Dev: Configuring Web Transformation Page Template in ContentStack | Owner missing | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 22: Dev: Configuring Web Transformation Page Template in ContentStack
PRG-0117 | Execution | 22 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC | Dev: Configuring Web Transformation Page Template in ContentStack | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 22: Dev: Configuring Web Transformation Page Template in ContentStack
PRG-0118 | Execution | 23 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC | Dev: Update Page Rendering Pipeline to support WT pages | Owner missing | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 23: Dev: Update Page Rendering Pipeline to support WT pages
PRG-0118 | Execution | 23 | Execution | TBC | Public Web | OMCOZA | Entire Site | All / TBC | Dev: Update Page Rendering Pipeline to support WT pages | Cluster missing or broad | Needs Validation | assign owner; validate taxonomy fields; track upstream dependency | Execution row 23: Dev: Update Page Rendering Pipeline to support WT pages
PRG-0119 | Execution | 24 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC | Dev: Navigation components updates public Web | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 24: Dev: Navigation components updates public Web
PRG-0119 | Execution | 24 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC | Dev: Navigation components updates public Web | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 24: Dev: Navigation components updates public Web
PRG-0119 | Execution | 24 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC | Dev: Navigation components updates public Web | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 24: Dev: Navigation components updates public Web
PRG-0119 | Execution | 24 | Execution | TBC | Public Web | OMCOZA | All / Shared | All / TBC | Dev: Navigation components updates public Web | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 24: Dev: Navigation components updates public Web
PRG-0120 | Execution | 25 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | QE : Automated Testing Framework (LS) | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 25: QE : Automated Testing Framework (LS)
PRG-0120 | Execution | 25 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | QE : Automated Testing Framework (LS) | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 25: QE : Automated Testing Framework (LS)
PRG-0120 | Execution | 25 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | QE : Automated Testing Framework (LS) | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 25: QE : Automated Testing Framework (LS)
PRG-0120 | Execution | 25 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | QE : Automated Testing Framework (LS) | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 25: QE : Automated Testing Framework (LS)
PRG-0121 | Execution | 26 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev :Observability Dashboards for various sites (LS) | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 26: Dev :Observability Dashboards for various sites (LS)
PRG-0121 | Execution | 26 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev :Observability Dashboards for various sites (LS) | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 26: Dev :Observability Dashboards for various sites (LS)
PRG-0121 | Execution | 26 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev :Observability Dashboards for various sites (LS) | Start date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 26: Dev :Observability Dashboards for various sites (LS)
PRG-0121 | Execution | 26 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev :Observability Dashboards for various sites (LS) | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 26: Dev :Observability Dashboards for various sites (LS)
PRG-0122 | Execution | 28 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Template (LS) | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 28: Dev : Modular Template (LS)
PRG-0122 | Execution | 28 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Template (LS) | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 28: Dev : Modular Template (LS)
PRG-0122 | Execution | 28 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Template (LS) | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 28: Dev : Modular Template (LS)
PRG-0122 | Execution | 28 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Template (LS) | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 28: Dev : Modular Template (LS)
PRG-0123 | Execution | 29 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Page Components (LS) | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 29: Dev : Modular Page Components (LS)
PRG-0123 | Execution | 29 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Page Components (LS) | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 29: Dev : Modular Page Components (LS)
PRG-0123 | Execution | 29 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Page Components (LS) | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 29: Dev : Modular Page Components (LS)
PRG-0123 | Execution | 29 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Page Components (LS) | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 29: Dev : Modular Page Components (LS)
PRG-0123 | Execution | 29 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Modular Page Components (LS) | Effort text / estimate | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 29: Dev : Modular Page Components (LS)
PRG-0124 | Execution | 30 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev Applying analytics tracking to CMS (LS) | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 30: Dev Applying analytics tracking to CMS (LS)
PRG-0124 | Execution | 30 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev Applying analytics tracking to CMS (LS) | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 30: Dev Applying analytics tracking to CMS (LS)
PRG-0124 | Execution | 30 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev Applying analytics tracking to CMS (LS) | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 30: Dev Applying analytics tracking to CMS (LS)
PRG-0124 | Execution | 30 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev Applying analytics tracking to CMS (LS) | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 30: Dev Applying analytics tracking to CMS (LS)
PRG-0124 | Execution | 30 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev Applying analytics tracking to CMS (LS) | Effort text / estimate | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 30: Dev Applying analytics tracking to CMS (LS)
PRG-0125 | Execution | 31 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev: OMCOZA -Licence cutover | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 31: Dev: OMCOZA -Licence cutover
PRG-0125 | Execution | 31 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev: OMCOZA -Licence cutover | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 31: Dev: OMCOZA -Licence cutover
PRG-0125 | Execution | 31 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev: OMCOZA -Licence cutover | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 31: Dev: OMCOZA -Licence cutover
PRG-0125 | Execution | 31 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev: OMCOZA -Licence cutover | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields; track upstream dependency | Execution row 31: Dev: OMCOZA -Licence cutover
PRG-0126 | Execution | 32 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Tableau Analytics | Owner missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 32: Dev : Tableau Analytics
PRG-0126 | Execution | 32 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Tableau Analytics | Cluster missing or broad | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 32: Dev : Tableau Analytics
PRG-0126 | Execution | 32 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Tableau Analytics | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 32: Dev : Tableau Analytics
PRG-0126 | Execution | 32 | Execution | TBC | Public Web | OMCOZA | Personal | All / TBC | Dev : Tableau Analytics | End date missing | Needs Validation | assign owner; confirm schedule and effort; validate taxonomy fields | Execution row 32: Dev : Tableau Analytics
PRG-0127 | Publishing | 4 | Publishing | Bernice | Public Web | OMCOM | Entire Site | All / TBC | Take live in V2 new platform | Cluster missing or broad | Needs Validation | validate taxonomy fields | Publishing row 4: Take live in V2 new platform
PRG-0128 | Publishing | 5 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC | Testing in V2 new platform and log bugs | Cluster missing or broad | Needs Validation | validate taxonomy fields | Publishing row 5: Testing in V2 new platform and log bugs
PRG-0129 | Publishing | 6 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC | Take live in V2 new platform | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields | Publishing row 6: Take live in V2 new platform
PRG-0129 | Publishing | 6 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC | Take live in V2 new platform | Start date tbc | Needs Validation | confirm schedule and effort; validate taxonomy fields | Publishing row 6: Take live in V2 new platform
PRG-0129 | Publishing | 6 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC | Take live in V2 new platform | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields | Publishing row 6: Take live in V2 new platform
PRG-0129 | Publishing | 6 | Publishing | Bernice | Public Web | OMAI (Alternatives) | Entire Site | All / TBC | Take live in V2 new platform | Effort invalid source formula | Needs Validation | confirm schedule and effort; validate taxonomy fields | Publishing row 6: Take live in V2 new platform
PRG-0133 | Publishing | 10 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC | Record URL structure based on all as-is pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 10: Record URL structure based on all as-is pages (keep/remove/consolidate)
PRG-0133 | Publishing | 10 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC | Record URL structure based on all as-is pages (keep/remove/consolidate) | Start date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 10: Record URL structure based on all as-is pages (keep/remove/consolidate)
PRG-0133 | Publishing | 10 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC | Record URL structure based on all as-is pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 10: Record URL structure based on all as-is pages (keep/remove/consolidate)
PRG-0133 | Publishing | 10 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC | Record URL structure based on all as-is pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 10: Record URL structure based on all as-is pages (keep/remove/consolidate)
PRG-0134 | Publishing | 11 | Publishing | Bernice | Public Web | OMCOZA | as-is pages | All / TBC | Start moving as-is pages over to Beta | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 11: Start moving as-is pages over to Beta
PRG-0135 | Publishing | 12 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 12: Record URL structure for all remaining Personal pages (keep/remove/consolidate)
PRG-0135 | Publishing | 12 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 12: Record URL structure for all remaining Personal pages (keep/remove/consolidate)
PRG-0135 | Publishing | 12 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC | Record URL structure for all remaining Personal pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 12: Record URL structure for all remaining Personal pages (keep/remove/consolidate)
PRG-0136 | Publishing | 13 | Publishing | Bernice | Public Web | OMCOZA | Personal | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 13: Start building new template pages
PRG-0137 | Publishing | 14 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 14: Record URL structure for all remaining Corporate pages (keep/remove/consolidate)
PRG-0137 | Publishing | 14 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 14: Record URL structure for all remaining Corporate pages (keep/remove/consolidate)
PRG-0137 | Publishing | 14 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC | Record URL structure for all remaining Corporate pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 14: Record URL structure for all remaining Corporate pages (keep/remove/consolidate)
PRG-0138 | Publishing | 15 | Publishing | Bernice | Public Web | OMCOZA | Corporate | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 15: Start building new template pages
PRG-0139 | Publishing | 16 | Publishing | Bernice | Public Web | OMCOZA | Wealth | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 16: Start building new template pages
PRG-0140 | Publishing | 17 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 17: Record URL structure for all remaining Utility pages (keep/remove/consolidate)
PRG-0140 | Publishing | 17 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 17: Record URL structure for all remaining Utility pages (keep/remove/consolidate)
PRG-0140 | Publishing | 17 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC | Record URL structure for all remaining Utility pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 17: Record URL structure for all remaining Utility pages (keep/remove/consolidate)
PRG-0141 | Publishing | 18 | Publishing | Bernice | Public Web | OMCOZA | Utility pages | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 18: Start building new template pages
PRG-0142 | Publishing | 19 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 19: Record URL structure for all remaining About us pages (keep/remove/consolidate)
PRG-0142 | Publishing | 19 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC | Record URL structure for all remaining About us pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 19: Record URL structure for all remaining About us pages (keep/remove/consolidate)
PRG-0142 | Publishing | 19 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC | Record URL structure for all remaining About us pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 19: Record URL structure for all remaining About us pages (keep/remove/consolidate)
PRG-0143 | Publishing | 20 | Publishing | Bernice | Public Web | OMCOZA | About Us | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 20: Start building new template pages
PRG-0144 | Publishing | 21 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 21: Record URL structure for all remaining Careers pages (keep/remove/consolidate)
PRG-0144 | Publishing | 21 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 21: Record URL structure for all remaining Careers pages (keep/remove/consolidate)
PRG-0144 | Publishing | 21 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC | Record URL structure for all remaining Careers pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 21: Record URL structure for all remaining Careers pages (keep/remove/consolidate)
PRG-0145 | Publishing | 22 | Publishing | Bernice | Public Web | OMCOZA | Careers | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 22: Start building new template pages
PRG-0146 | Publishing | 23 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Cluster missing or broad | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 23: Record URL structure for all remaining Business pages (keep/remove/consolidate)
PRG-0146 | Publishing | 23 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC | Record URL structure for all remaining Business pages (keep/remove/consolidate) | End date missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 23: Record URL structure for all remaining Business pages (keep/remove/consolidate)
PRG-0146 | Publishing | 23 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC | Record URL structure for all remaining Business pages (keep/remove/consolidate) | Effort missing | Needs Validation | confirm schedule and effort; validate taxonomy fields; track upstream dependency | Publishing row 23: Record URL structure for all remaining Business pages (keep/remove/consolidate)
PRG-0147 | Publishing | 24 | Publishing | Bernice | Public Web | OMCOZA | Business | All / TBC | Start building new template pages | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 24: Start building new template pages
PRG-0148 | Publishing | 25 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC | Add new Nav, Footer and update IA | Area/Journey missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 25: Add new Nav, Footer and update IA
PRG-0148 | Publishing | 25 | Publishing | Bernice | Public Web | OMCOM | All / TBC | All / TBC | Add new Nav, Footer and update IA | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 25: Add new Nav, Footer and update IA
PRG-0149 | Publishing | 26 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC | Add new Nav, Footer and update IA | Area/Journey missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 26: Add new Nav, Footer and update IA
PRG-0149 | Publishing | 26 | Publishing | Bernice | Public Web | OMAI (Alternatives) | All / TBC | All / TBC | Add new Nav, Footer and update IA | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 26: Add new Nav, Footer and update IA
PRG-0150 | Publishing | 27 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC | Add new Nav, Footer and update IA | Area/Journey missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 27: Add new Nav, Footer and update IA
PRG-0150 | Publishing | 27 | Publishing | Bernice | Public Web | Bula Tsela | All / TBC | All / TBC | Add new Nav, Footer and update IA | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 27: Add new Nav, Footer and update IA
PRG-0151 | Publishing | 28 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC | Add new Nav, Footer and update IA | Area/Journey missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 28: Add new Nav, Footer and update IA
PRG-0151 | Publishing | 28 | Publishing | Bernice | Public Web | LTD | All / TBC | All / TBC | Add new Nav, Footer and update IA | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 28: Add new Nav, Footer and update IA
PRG-0152 | Publishing | 29 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC | Publishing requirements for OMAR, logged on OMAR tab | Area/Journey missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 29: Publishing requirements for OMAR, logged on OMAR tab
PRG-0152 | Publishing | 29 | Publishing | Bernice | Public Web | OMAR | All / TBC | All / TBC | Publishing requirements for OMAR, logged on OMAR tab | Cluster missing or broad | Needs Validation | validate taxonomy fields; track upstream dependency | Publishing row 29: Publishing requirements for OMAR, logged on OMAR tab
PRG-0153 | Publishing | 30 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site | Add all new redirects for the site | Start date tbc | Needs Validation | confirm schedule and effort | Publishing row 30: Add all new redirects for the site
PRG-0153 | Publishing | 30 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site | Add all new redirects for the site | End date tbc | Needs Validation | confirm schedule and effort | Publishing row 30: Add all new redirects for the site
PRG-0153 | Publishing | 30 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site | Add all new redirects for the site | Effort tbc | Needs Validation | confirm schedule and effort | Publishing row 30: Add all new redirects for the site
PRG-0153 | Publishing | 30 | Publishing | Bernice | Public Web | OMCOZA | Entire Site | Entire Site | Add all new redirects for the site | Priority missing | Needs Validation | confirm schedule and effort | Publishing row 30: Add all new redirects for the site
PRG-0154 | Go-Live Readiness | 4 | Go-Live Readiness | TBC | Public Web | All | All | All | Penetration Testing Discussion and confirmation | Owner missing | Needs Validation | assign owner | Go-Live Readiness row 4: Penetration Testing Discussion and confirmation
PRG-0155 | Go-Live Readiness | 5 | Go-Live Readiness | TBC | Public Web | All | All | All | Quality Assurance Approval | Owner missing | Needs Validation | assign owner | Go-Live Readiness row 5: Quality Assurance Approval
PRG-0156 | Go-Live Readiness | 6 | Go-Live Readiness | TBC | Public Web | All | All | All | Security Approvals | Owner missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 6: Security Approvals
PRG-0156 | Go-Live Readiness | 6 | Go-Live Readiness | TBC | Public Web | All | All | All | Security Approvals | Status missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 6: Security Approvals
PRG-0157 | Go-Live Readiness | 7 | Go-Live Readiness | TBC | Public Web | All | All | All | Internal Communication ( Call Centre) - Marketing Team Driven | Owner missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 7: Internal Communication ( Call Centre) - Marketing Team Driven
PRG-0158 | Go-Live Readiness | 8 | Go-Live Readiness | TBC | Public Web | All | All | All | Service Now Update | Owner missing | Needs Validation | assign owner | Go-Live Readiness row 8: Service Now Update
PRG-0159 | Go-Live Readiness | 9 | Go-Live Readiness | TBC | Public Web | All | All | All | Executive Approval | Owner missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 9: Executive Approval
PRG-0160 | Go-Live Readiness | 10 | Go-Live Readiness | TBC | Public Web | All | All | All | Change Management Go Ahead | Owner missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 10: Change Management Go Ahead
PRG-0161 | Go-Live Readiness | 11 | Go-Live Readiness | TBC | Public Web | All | All | All | Customer Experience Tool | Owner missing | Needs Validation | assign owner; track upstream dependency | Go-Live Readiness row 11: Customer Experience Tool
PRG-0162 | SEO Analytics | 4 | SEO / Analytics | TBC | Public Web | All | All | All | Confirm Engagement Cycle with SEO Team | Owner missing | Needs Validation | assign owner | SEO Analytics row 4: Confirm Engagement Cycle with SEO Team
PRG-0163 | SEO Analytics | 5 | SEO / Analytics | TBC | Public Web | All | All | All | SEO Requirements to Dev Team | Owner missing | Needs Validation | assign owner | SEO Analytics row 5: SEO Requirements to Dev Team
PRG-0163 | SEO Analytics | 5 | SEO / Analytics | TBC | Public Web | All | All | All | SEO Requirements to Dev Team | Status missing | Needs Validation | assign owner | SEO Analytics row 5: SEO Requirements to Dev Team
PRG-0164 | OMAR | 4 | OMAR | TBC | Public Web | OMAR | OMAR | OMAR | Engagement required to communicate recalibration of project to various OMAR Stakeholder | Owner missing | Needs Validation | assign owner | OMAR row 4: Engagement required to communicate recalibration of project to various OMAR Stakeholder
PRG-0165 | OMAR | 5 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 5: Publishing of all pages in V2 New platform
PRG-0165 | OMAR | 5 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 5: Publishing of all pages in V2 New platform
PRG-0165 | OMAR | 5 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 5: Publishing of all pages in V2 New platform
PRG-0165 | OMAR | 5 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 5: Publishing of all pages in V2 New platform
PRG-0165 | OMAR | 5 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 5: Publishing of all pages in V2 New platform
PRG-0166 | OMAR | 6 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 6: Publishing of all pages in V2 New platform
PRG-0166 | OMAR | 6 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 6: Publishing of all pages in V2 New platform
PRG-0166 | OMAR | 6 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 6: Publishing of all pages in V2 New platform
PRG-0166 | OMAR | 6 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 6: Publishing of all pages in V2 New platform
PRG-0166 | OMAR | 6 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 6: Publishing of all pages in V2 New platform
PRG-0167 | OMAR | 7 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 7: Publishing of all pages in V2 New platform
PRG-0167 | OMAR | 7 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 7: Publishing of all pages in V2 New platform
PRG-0167 | OMAR | 7 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 7: Publishing of all pages in V2 New platform
PRG-0167 | OMAR | 7 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 7: Publishing of all pages in V2 New platform
PRG-0167 | OMAR | 7 | OMAR | TBC | Public Web | OMAR | Kenya | Kenya | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 7: Publishing of all pages in V2 New platform
PRG-0168 | OMAR | 8 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 8: Publishing of all pages in V2 New platform
PRG-0168 | OMAR | 8 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 8: Publishing of all pages in V2 New platform
PRG-0168 | OMAR | 8 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 8: Publishing of all pages in V2 New platform
PRG-0168 | OMAR | 8 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 8: Publishing of all pages in V2 New platform
PRG-0168 | OMAR | 8 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 8: Publishing of all pages in V2 New platform
PRG-0169 | OMAR | 9 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 9: Publishing of all pages in V2 New platform
PRG-0169 | OMAR | 9 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 9: Publishing of all pages in V2 New platform
PRG-0169 | OMAR | 9 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 9: Publishing of all pages in V2 New platform
PRG-0169 | OMAR | 9 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 9: Publishing of all pages in V2 New platform
PRG-0169 | OMAR | 9 | OMAR | TBC | Public Web | OMAR | Rwanda | Rwanda | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 9: Publishing of all pages in V2 New platform
PRG-0170 | OMAR | 10 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 10: Publishing of all pages in V2 New platform
PRG-0170 | OMAR | 10 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 10: Publishing of all pages in V2 New platform
PRG-0170 | OMAR | 10 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 10: Publishing of all pages in V2 New platform
PRG-0170 | OMAR | 10 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 10: Publishing of all pages in V2 New platform
PRG-0170 | OMAR | 10 | OMAR | TBC | Public Web | OMAR | Uganda | Uganda | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 10: Publishing of all pages in V2 New platform
PRG-0171 | OMAR | 11 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 11: Publishing of all pages in V2 New platform
PRG-0171 | OMAR | 11 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 11: Publishing of all pages in V2 New platform
PRG-0171 | OMAR | 11 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 11: Publishing of all pages in V2 New platform
PRG-0171 | OMAR | 11 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 11: Publishing of all pages in V2 New platform
PRG-0171 | OMAR | 11 | OMAR | TBC | Public Web | OMAR | Zimbabwe | Zimbabwe | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 11: Publishing of all pages in V2 New platform
PRG-0172 | OMAR | 12 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 12: Publishing of all pages in V2 New platform
PRG-0172 | OMAR | 12 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 12: Publishing of all pages in V2 New platform
PRG-0172 | OMAR | 12 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 12: Publishing of all pages in V2 New platform
PRG-0172 | OMAR | 12 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 12: Publishing of all pages in V2 New platform
PRG-0172 | OMAR | 12 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Publishing of all pages in V2 New platform | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 12: Publishing of all pages in V2 New platform
PRG-0173 | OMAR | 13 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Travel Insurance Sales Migration | Owner missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 13: Travel Insurance Sales Migration
PRG-0173 | OMAR | 13 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Travel Insurance Sales Migration | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 13: Travel Insurance Sales Migration
PRG-0173 | OMAR | 13 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Travel Insurance Sales Migration | OMAR country domain normalised to OMAR | Needs Validation | assign owner; capture named upstream dependency | OMAR row 13: Travel Insurance Sales Migration
PRG-0174 | OMAR | 14 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Mvest | Owner missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 14: Mvest
PRG-0174 | OMAR | 14 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Mvest | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 14: Mvest
PRG-0174 | OMAR | 14 | OMAR | TBC | Public Web | OMAR | Ghana | Ghana | Mvest | OMAR country domain normalised to OMAR | Needs Validation | assign owner; capture named upstream dependency | OMAR row 14: Mvest
PRG-0175 | OMAR | 15 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Application | Owner missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 15: Personal Loan Application
PRG-0175 | OMAR | 15 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Application | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 15: Personal Loan Application
PRG-0175 | OMAR | 15 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Application | OMAR country domain normalised to OMAR | Needs Validation | assign owner; capture named upstream dependency | OMAR row 15: Personal Loan Application
PRG-0176 | OMAR | 16 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Repayment Calculator | Owner missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 16: Personal Loan Repayment Calculator
PRG-0176 | OMAR | 16 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Repayment Calculator | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; capture named upstream dependency | OMAR row 16: Personal Loan Repayment Calculator
PRG-0176 | OMAR | 16 | OMAR | TBC | Public Web | OMAR | Namibia | Namibia | Personal Loan Repayment Calculator | OMAR country domain normalised to OMAR | Needs Validation | assign owner; capture named upstream dependency | OMAR row 16: Personal Loan Repayment Calculator
PRG-0177 | OMAR | 17 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Migration of Secure Web | Owner missing | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 17: Migration of Secure Web
PRG-0177 | OMAR | 17 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Migration of Secure Web | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 17: Migration of Secure Web
PRG-0177 | OMAR | 17 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Migration of Secure Web | End date tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 17: Migration of Secure Web
PRG-0177 | OMAR | 17 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Migration of Secure Web | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 17: Migration of Secure Web
PRG-0177 | OMAR | 17 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Migration of Secure Web | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; track upstream dependency | OMAR row 17: Migration of Secure Web
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0178 | OMAR | 18 | OMAR | TBC | Secure Web | OMAR | Namibia | Namibia | Service Transactions | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 18: Service Transactions
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | Country taxonomy mismatch: source domain Ghana vs area Eswatini | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0179 | OMAR | 19 | OMAR | TBC | Public Web | OMAR | eSwatini | eSwatini | Eswatini Funeral | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 19: Eswatini Funeral
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0180 | OMAR | 20 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Servicing Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 20: Funeral Claims - Servicing Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0181 | OMAR | 21 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Service Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 21: Motor claims - Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0182 | OMAR | 22 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Service Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 22: Home owners claims- Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0183 | OMAR | 23 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home content claims Service Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 23: Home content claims Service Journey
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0184 | OMAR | 24 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Credit Life | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 24: Credit Life
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0185 | OMAR | 25 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Funeral Claims - Sales Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 25: Funeral Claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0186 | OMAR | 26 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Motor claims - Sales Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 26: Motor claims - Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | Owner missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | Start date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | End date tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | Effort tbc | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | Upstream dependency marked yes but detail missing | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey
PRG-0187 | OMAR | 27 | OMAR | TBC | Public Web | OMAR | Botswana | Botswana | Home owners claims- Sales Journey | OMAR country domain normalised to OMAR | Needs Validation | assign owner; confirm schedule and effort; capture named upstream dependency | OMAR row 27: Home owners claims- Sales Journey

## REFERENCE_Source_Audit
Source_Sheet | Used_Range | Workstream_Metadata | Owner_Metadata | Meaningful_Rows_Loaded | Rows_Excluded_As_Blank | Cons_List_Records_for_Workstream | Delta_Source_Tab_vs_Cons_List | Input_Status
Design Standards | A1:N143 | Design Standards | Justin | 20 | 120 | 15 | 5 | Processed as source workstream tab
Design Delivery | A1:N149 | Design Delivery | TBC | 35 | 111 | 16 | 19 | Processed as source workstream tab
Content Readiness | A1:N140 | Content Readiness | Natalie Patel | 4 | 133 | 4 | 0 | Processed as source workstream tab
Feature Delivery | A1:N140 | Feature Delivery | Wayne & Tebogo | 22 | 115 | 22 | 0 | Processed as source workstream tab
Design Systems | A1:N141 | Design Systems | Brent van Zitters | 20 | 118 | 16 | 4 | Processed as source workstream tab
Execution | A1:N144 | Execution | TBC | 25 | 116 | 25 | 0 | Processed as source workstream tab
Publishing | A1:N149 | Publishing | Bernice | 27 | 119 | 19 | 8 | Processed as source workstream tab
Go-Live Readiness | A1:N138 | Go-Live Readiness | TBC | 8 | 127 | 8 | 0 | Processed as source workstream tab
SEO Analytics | A1:N140 | SEO / Analytics | TBC | 2 | 135 | 2 | 0 | Processed as source workstream tab
OMAR | A1:N137 | OMAR | TBC | 24 | 110 | 24 | 0 | Processed as source workstream tab
Cons_List | A1:P265 | Consolidated list |  | 151 |  | 151 |  | Used for reconciliation only; source workstream tabs had more complete record coverage
Sheet1 | A1:E4 | Cover / title only |  | 0 |  |  |  | Excluded from programme upload; no programme rows
Piv | A1:A14 | Pivot label / summary only |  | 0 |  |  |  | Excluded from programme upload; no row-level programme data

## REFERENCE_Taxonomy
Field | Source_Value | Clean_Value | Count | Rule_or_Rationale
Channel | Blank/0 | TBC | 4 | Blank or zero source value normalised to TBC or All/TBC depending on context.
Channel | Public Web | Public Web | 161 | Value retained with whitespace/case cleanup only.
Channel | Secure Web | Secure Web | 22 | Value retained with whitespace/case cleanup only.
Domain | All | All | 33 | Value retained with whitespace/case cleanup only.
Domain | Blank/0 | TBC | 1 | Blank or zero source value normalised to TBC or All/TBC depending on context.
Domain | Botswana | OMAR | 9 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | Bula Tsela | Bula Tsela | 2 | Value retained with whitespace/case cleanup only.
Domain | Ghana | OMAR | 4 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | Kenya | OMAR | 1 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | LTD | LTD | 1 | Value retained with whitespace/case cleanup only.
Domain | Learn Think Do (LTD) | Learn Think Do (LTD) | 1 | Value retained with whitespace/case cleanup only.
Domain | MyOM | MyOM | 2 | Value retained with whitespace/case cleanup only.
Domain | N/A | Shared / Platform | 19 | N/A normalised to shared/platform classification.
Domain | Namibia | OMAR | 6 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | OMAI (Alternatives) | OMAI (Alternatives) | 3 | Value retained with whitespace/case cleanup only.
Domain | OMAR | OMAR | 2 | Value retained with whitespace/case cleanup only.
Domain | OMAR: Kenya | OMAR: Kenya | 1 | Value retained with whitespace/case cleanup only.
Domain | OMAR: Zimbabwe | OMAR: Zimbabwe | 1 | Value retained with whitespace/case cleanup only.
Domain | OMCOM | OMCOM | 4 | Value retained with whitespace/case cleanup only.
Domain | OMCOZA | OMCOZA | 88 | Value retained with whitespace/case cleanup only.
Domain | OMCOZA, OMCOM, Bula-tsela, Malawi | OMCOZA, OMCOM, Bula-tsela, Malawi | 2 | Value retained with whitespace/case cleanup only.
Domain | Old Mutual Design Standards | Old Mutual Design Standards | 3 | Value retained with whitespace/case cleanup only.
Domain | RESOURCE RECRUITMENT | RESOURCE RECRUITMENT | 1 | Value retained with whitespace/case cleanup only.
Domain | Rwanda | OMAR | 1 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | Uganda | OMAR | 1 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Domain | Zimbabwe | OMAR | 1 | Country domain in OMAR source tab normalised to Domain=OMAR and retained in Market/Area/Cluster.
Area/Journey | ALL SITES IN SCOPE | ALL SITES IN SCOPE | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | About Us | About Us | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | About us | About Us | 1 | Value normalised for consistent reporting.
Area/Journey | All | All | 31 | Value retained with whitespace/case cleanup only.
Area/Journey | As is pages | as-is pages | 2 | Value normalised for consistent reporting.
Area/Journey | Blank/0 | All / TBC | 5 | Blank or zero source value normalised to TBC or All/TBC depending on context.
Area/Journey | Botswana | Botswana | 9 | Value retained with whitespace/case cleanup only.
Area/Journey | Business | Business | 9 | Value retained with whitespace/case cleanup only.
Area/Journey | Careers | Careers | 2 | Value retained with whitespace/case cleanup only.
Area/Journey | Corporate | Corporate | 7 | Value retained with whitespace/case cleanup only.
Area/Journey | Dashboard Views ( Porffolio Views) | Dashboard Views ( Porffolio Views) | 2 | Value retained with whitespace/case cleanup only.
Area/Journey | Entire Site | Entire Site | 2 | Value retained with whitespace/case cleanup only.
Area/Journey | Entire site | Entire Site | 23 | Value normalised for consistent reporting.
Area/Journey | Eswatini | eSwatini | 1 | Value normalised for consistent reporting.
Area/Journey | Generic | Generic | 3 | Value retained with whitespace/case cleanup only.
Area/Journey | Ghana | Ghana | 3 | Value retained with whitespace/case cleanup only.
Area/Journey | Insure / iWyze | Insure / iWyze | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | Kenya | Kenya | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | N/A | All / Shared | 13 | N/A normalised to shared/platform classification.
Area/Journey | Namibia | Namibia | 6 | Value retained with whitespace/case cleanup only.
Area/Journey | OM Bank | OM Bank | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | OMAR | OMAR | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | Personal | Personal | 40 | Value retained with whitespace/case cleanup only.
Area/Journey | Rewards | Rewards | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | Rwanda | Rwanda | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | Servicing Transaction in Sec Web | Servicing Transaction in Sec Web | 9 | Value retained with whitespace/case cleanup only.
Area/Journey | Uganda | Uganda | 1 | Value retained with whitespace/case cleanup only.
Area/Journey | Utility pages | Utility pages | 2 | Value retained with whitespace/case cleanup only.
Area/Journey | Wealth | Wealth | 7 | Value retained with whitespace/case cleanup only.
Area/Journey | Zimbabwe | Zimbabwe | 1 | Value retained with whitespace/case cleanup only.
Cluster | ALL SITES IN SCOPE | ALL SITES IN SCOPE | 1 | Value retained with whitespace/case cleanup only.
Cluster | About | About | 1 | Value retained with whitespace/case cleanup only.
Cluster | About us | About us | 1 | Value retained with whitespace/case cleanup only.
Cluster | All | All | 41 | Value retained with whitespace/case cleanup only.
Cluster | Blank/0 | All / TBC | 47 | Blank or zero source value normalised to TBC or All/TBC depending on context.
Cluster | Botswana | Botswana | 9 | Value retained with whitespace/case cleanup only.
Cluster | Business Landing | Business Landing | 1 | Value retained with whitespace/case cleanup only.
Cluster | CI | CI | 1 | Value retained with whitespace/case cleanup only.
Cluster | Careers | Careers | 1 | Value retained with whitespace/case cleanup only.
Cluster | Copy | Copy | 2 | Value retained with whitespace/case cleanup only.
Cluster | Corporate Landing | Corporate Landing | 1 | Value retained with whitespace/case cleanup only.
Cluster | Employees | Employees | 1 | Value retained with whitespace/case cleanup only.
Cluster | Employers | Employers | 1 | Value retained with whitespace/case cleanup only.
Cluster | Entire Site | Entire Site | 6 | Value retained with whitespace/case cleanup only.
Cluster | Entire site | Entire Site | 4 | Value normalised for consistent reporting.
Cluster | Eswatini | eSwatini | 1 | Value normalised for consistent reporting.
Cluster | Flexi Save | Flexi Save | 1 | Value retained with whitespace/case cleanup only.
Cluster | Funeral | Funeral | 3 | Value retained with whitespace/case cleanup only.
Cluster | Ghana | Ghana | 3 | Value retained with whitespace/case cleanup only.
Cluster | Guarantee | Guarantee | 1 | Value retained with whitespace/case cleanup only.
Cluster | Insights | Insights | 1 | Value retained with whitespace/case cleanup only.
Cluster | Insure | Insure | 2 | Value retained with whitespace/case cleanup only.
Cluster | Invest | Invest | 3 | Value retained with whitespace/case cleanup only.
Cluster | Invest Flexi Save | Invest Flexi Save | 1 | Value retained with whitespace/case cleanup only.
Cluster | Investment > Flexi Save | Investment > Flexi Save | 1 | Value retained with whitespace/case cleanup only.
Cluster | Kenya | Kenya | 1 | Value retained with whitespace/case cleanup only.
Cluster | L&S | L&S | 11 | Value retained with whitespace/case cleanup only.
Cluster | My OldMutual | My OldMutual | 1 | Value retained with whitespace/case cleanup only.
Cluster | Namibia | Namibia | 6 | Value retained with whitespace/case cleanup only.
Cluster | Navigation | Navigation | 4 | Value retained with whitespace/case cleanup only.
Cluster | OM | OM | 1 | Value retained with whitespace/case cleanup only.
Cluster | OM BAnk | OM Bank | 1 | Value normalised for consistent reporting.
Cluster | OMAR | OMAR | 1 | Value retained with whitespace/case cleanup only.
Cluster | Personal Landing | Personal Landing | 1 | Value retained with whitespace/case cleanup only.
Cluster | Personal landing page | Personal landing page | 1 | Value retained with whitespace/case cleanup only.
Cluster | Plan | Plan | 1 | Value retained with whitespace/case cleanup only.
Cluster | Protect | Protect | 1 | Value retained with whitespace/case cleanup only.
Cluster | Retirement | Retirement | 3 | Value retained with whitespace/case cleanup only.
Cluster | Rwanda | Rwanda | 1 | Value retained with whitespace/case cleanup only.
Cluster | Services | Services | 1 | Value retained with whitespace/case cleanup only.
Cluster | Templates | Templates | 9 | Value retained with whitespace/case cleanup only.
Cluster | Tenant | Tenant | 4 | Value retained with whitespace/case cleanup only.
Cluster | Tools | Tools | 1 | Value retained with whitespace/case cleanup only.
Cluster | Uganda | Uganda | 1 | Value retained with whitespace/case cleanup only.
Cluster | Wealth Landing | Wealth Landing | 1 | Value retained with whitespace/case cleanup only.
Cluster | Zimbabwe | Zimbabwe | 1 | Value retained with whitespace/case cleanup only.

## REFERENCE_Schema
Sheet | Column_Order | Column_Name | Purpose | Upload_Status
UPLOAD_Master_Data | 1 | Programme_Record_ID | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 2 | Workstream | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 3 | Owner | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 4 | Channel | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 5 | Domain | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 6 | Area_Journey | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 7 | Cluster | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 8 | Market | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 9 | Clean_Task | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 10 | Clean_Description | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 11 | Start_Date | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 12 | End_Date | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 13 | Effort_Days | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 14 | Effort_Days_Text | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 15 | Confidence_Percent | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 16 | Confidence_Band | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 17 | Priority | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 18 | Status | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 19 | Upstream_Dependency | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 20 | Upstream_Deliverable | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 21 | Has_Risk | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 22 | Has_Constraint | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 23 | Has_Dependency | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 24 | Comments | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 25 | Scope_Items | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 26 | Source_Sheet | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 27 | Source_Row | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 28 | Source_Channel | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 29 | Source_Domain | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 30 | Source_Area_Journey | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 31 | Source_Cluster | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Master_Data | 32 | Original_Task | Cleaned programme deliverables/tasks/milestones | Uploadable programme data
UPLOAD_Risks | 1 | Risk_ID | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 2 | Linked_Programme_Record_ID | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 3 | Workstream | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 4 | Owner | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 5 | Channel | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 6 | Domain | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 7 | Area_Journey | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 8 | Cluster | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 9 | Market | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 10 | Related_Deliverable | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 11 | Risk_Type | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 12 | Title | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 13 | Detailed_Description | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 14 | Risk_Severity | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 15 | Priority | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 16 | Status | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 17 | Confidence_Percent | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 18 | Required_Action | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 19 | Source_Sheet | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 20 | Source_Row | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Risks | 21 | Source_Evidence | Risk register derived from source rows and evidence | Uploadable programme risk data
UPLOAD_Constraints | 1 | Constraint_ID | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 2 | Linked_Programme_Record_ID | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 3 | Workstream | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 4 | Owner | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 5 | Channel | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 6 | Domain | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 7 | Area_Journey | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 8 | Cluster | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 9 | Market | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 10 | Related_Deliverable | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 11 | Constraint_Type | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 12 | Title | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 13 | Detailed_Description | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 14 | Constraint_Severity | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 15 | Priority | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 16 | Status | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 17 | Confidence_Percent | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 18 | Required_Action | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 19 | Source_Sheet | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 20 | Source_Row | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Constraints | 21 | Source_Evidence | Constraint register derived from source rows and evidence | Uploadable programme constraint data
UPLOAD_Dependencies | 1 | Dependency_ID | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 2 | Linked_Programme_Record_ID | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 3 | Workstream | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 4 | Owner | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 5 | Channel | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 6 | Domain | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 7 | Area_Journey | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 8 | Cluster | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 9 | Market | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 10 | Related_Deliverable | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 11 | Dependency_Type | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 12 | Title | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 13 | Detailed_Description | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 14 | Dependency_Status | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 15 | Priority | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 16 | Status | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 17 | Confidence_Percent | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 18 | Required_Action | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 19 | Source_Sheet | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 20 | Source_Row | Dependency register derived from source rows and evidence | Uploadable programme dependency data
UPLOAD_Dependencies | 21 | Source_Evidence | Dependency register derived from source rows and evidence | Uploadable programme dependency data
REFERENCE_Validation | 1 | Programme_Record_ID | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 2 | Source_Sheet | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 3 | Source_Row | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 4 | Workstream | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 5 | Owner | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 6 | Channel | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 7 | Domain | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 8 | Area_Journey | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 9 | Cluster | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 10 | Related_Deliverable | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 11 | Validation_Issue | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 12 | Load_Readiness | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 13 | Suggested_Action | Data-quality and taxonomy validation items | Reference only - do not load as programme data
REFERENCE_Validation | 14 | Source_Evidence | Data-quality and taxonomy validation items | Reference only - do not load as programme data